## Task List
QCLAD Detail Requirement Gathering Task List Jun/14th/2024
No | RTM reference | Task | Function Area | 计划开始日期 | Start Date | 计划完成日期 | Due Date | Complete Date | Note | PIC | Responsible Party | Status checked by Henkel | Status checked by Thermofisher
1 | 4.1.1.1.2 | Henkel offer the log in sample request template for reference. | Sample Login/Sample Receipt | 2024-05-08 |  | 2024-05-10 | 2024-06-30 |  | Check with Care & Horace | Care & Horace | Henkel | Completed | Not Started
2 | 4.1.1.3.3 | Henkel need to check label template with Dragon. ( offer QR code rule ) | Sample Login/Sample Receipt |  |  |  | 2024-06-30 |  | Check with Eagle | Frank | Henkel | Completed | Not Started
3 | 4.1.1.3.5 | Henkel offer sample ID naming rules for non-standard Sample .(TF give some sample ID naming rules examples) | Sample Login/Sample Receipt |  |  |  | 2024-06-30 |  | SAP plant code+Sample Type+Date（to day）+SequenceNo based on Plant code & Date & Sample Type TF:SequenceNo should consider plant code? Henkel：Yes,0759 for Dragon | Frank | Henkel | Completed | Completed
4 | 4.1.1.3.5 | TF provide Sample ID naming rules/examples for Henkel to select | Sample Login/Sample Receipt |  |  |  | 2024-06-14 |  | Gu Cheng sent email about the examples | Gu Cheng | TF | Completed | Completed
5 | 4.1.1.7.2 | Henkel need to check function of sample type and sampling plans with Maline. | Sample Login/Sample Receipt |  |  |  | 2024-06-21 |  | Sampling plan set as configurable rules in QCLaD,sample type can be found in workflows TF: is sampling plan means preset test methods for sample(like inspection plan in SAP)? Henkel:No, For sample plan it's like sample quantity, there should be configurable setting for each IDH and can be changed when sample received | Lisa | Henkel | Completed | Completed
6 | 4.1.1.19.1 | Henkel need to check this requirement with Neelima: The system shall provide functionality to allow entry of any irregularities recorded and route sample according to laboratory business rules | Sample Login/Sample Receipt |  |  |  | 2024-06-21 |  | Non-QCLaD user sample login TF: Still don't understand, provide example/more info Henkel:Irregularities record means Notes for non-routing test request | Neelima | Henkel | Completed | Completed
7 | 4.1.2.10.1 | Need check what is the pre-set method limits with Neelima. | Sample Testing/Results Entry |  |  |  | 2024-06-20 |  | Pre-set method = specification |  | Henkel | Completed | Completed
8 | 4.1.2.12.5 | Henkel need check what is the time taken with Neelima & Maline | Sample Testing/Results Entry |  |  |  | 2024-06-20 |  | Actual cycle time |  | Henkel | Completed | Completed
9 | 4.1.2.13.2 | Henkel need check what is the qualified numeric with Neelima. | Sample Testing/Results Entry |  |  |  | 2024-06-20 |  | number 0 - 9 |  | Henkel | Completed | Completed
10 | 4.1.2.12.6 | Video is possible based on last comment from TF. Size details have to be provided. | Sample Testing/Results Entry |  | 2024-06-12 |  | 2024-06-20 |  | This can be implemented in QCLAD.Maximaum size need to be confirmed by TF Size depends on Henkel service capability. |  | TF | Completed | Completed
11 | 4.1.2.23.1 | Henkel needs to confirm: System shall be able to enforce entry of a justification if there is a retest/resample. - If resample is correct word. | Sample Testing/Results Entry |  |  |  | 2024-06-20 |  | Confirmed to be resample |  | Henkel | Completed | Completed
12 | 4.1.2.24.1 | SQC is not in scope. Check if trend chart function is still needed | Sample Testing/Results Entry |  |  |  | 2024-06-21 |  | Check with Thermofisher team for what trend chart they can provide and any additional cost out of SOW? Confirmed with Thermofisher that LIMS only have SQC for trend chart.SQC is a standard module, if it is needed, additional cost will be charged. | Frank | Henkel | Completed | Completed
13 | 4.1.2.25.2 | Henkel need to check the detail about peer review & Approval for test result with Maline | Sample Testing/Results Entry |  |  |  | 2024-06-21 |  | Supervisor review is needed before QCLaD push data to SAP/generate report(for non-standard).Group the material, for some of them need approval, some of them don't. For the setting we can change it. We need the function of peer review and Approval both. TF:clearify which sample types needs approval. Henkel:For IDH,we can set Approval or not. For test method final result, we can set peer review or not. | Frank | Henkel | Completed | Completed
14 | 4.1.2.28.1 | Henkel need to offer dashboard template. | Sample Testing/Results Entry |  |  |  | 2024-07-30 |  | After Dashboard is discussed, come back to it. |  | Henkel | In Progress | Not Started
15 | 4.1.3.1.2 | Henkel need check if all sample type need approve with Neelima. | Authorization |  |  |  | 2024-06-21 |  | Same with 4.1.2.25.2 | Frank | Henkel | Completed | Completed
16 | 4.1.4.5.2 | Henkel need to check if the electrical signature is picture with stakeholders. | Reporting |  |  |  | 2024-06-21 |  | Check with Neelima,not avilable in phase 1,check with TF the feasibility TF: please confirm we won't do it in pilot phase. Feasibility: yes Henkel confirm it is not in pilot scope | Frank | Henkel | Completed | Completed
17 | 4.1.4.5.3 | This is an out of scope function, Henkel needs to confirm if want to implement this function: System shall be able to support end app insert handwritting signature by pad | Reporting |  |  |  | 2024-06-21 |  | Check with Neelima,not avilable in phase 1,check with TF the feasibility TF:feasibility: No Henkel confirm it is not in scope. | Frank | Henkel | Completed | Completed
18 | 4.1.4.5.3 | If Henkel wants to implement this, TF check the how to implement it: System shall be able to support end app insert handwritting signature by pad | Reporting |  |  |  | 2024-06-20 |  | Same with 4.1.4.5.2 | HongTao | TF | Completed | Completed
19 | 4.1.4.6.2 | Henkel need to check the meaning of shedules with team members. | Reporting |  |  |  | 2024-06-21 |  | Check with Neelima,whenever the test is trigger by sample recipt or schedule,the data should be avilable and report will be generated TF: Update in the RTM | Frank | Henkel | Completed | Completed
20 | 4.1.4.10.2 | Henkel need to offer all report template. | Reporting |  |  |  | 2024-07-30 |  |  | Care & Horace | Henkel | In Progress | Not Started
21 | 4.1.4.14.2 | Henkel offer the details and scenario about the notifications and alert messages. | Reporting |  |  |  | 2024-06-30 |  | Check with Neelima,about to expire or below safety stork,alert should be sent to certain group basically in LIMS system. TF: This is for reporting module, what is the purpose of this function in reporting? Henkel:Notication bell icon to display alerts and nofications | Frank | Henkel | Completed | Completed
22 | 4.1.5.1.1 | Henkel add workflow name: System shall be able to manage Raw material sample (ROH) workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | RM test for Incoming | Frank | Henkel | Completed | Completed
23 | 4.1.5.1.2 | Henkel add workflow name: System shall be able to manage semi-finish goods sample/ bulk sample (UNB & UNF) workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Standard in process testing for semi finished and finished goods |  | Henkel | Completed | Completed
24 | 4.1.5.1.3 | Henkel check names: System shall be able to manage finish goods sample (FER) workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Standard finished goods outgoing test. |  | Henkel | Completed | Completed
25 | 4.1.5.1.4 | Henkel check names: System shall be able to manage consumable workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Consumables incoming test |  | Henkel | Completed | Completed
26 | 4.1.5.1.5 | Henkel check names: System shall be able to manage package material workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Package material incoming test |  | Henkel | Completed | Completed
27 | 4.1.5.1.6 | Henkel check names: System shall be able to manage instrument calibration sample workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Instrument calibration sample test |  | Henkel | Completed | Completed
28 | 4.1.5.1.7 | Henkel check names: System shall be able to manage MSA test sample workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Test for MSA |  | Henkel | Completed | Completed
29 | 4.1.5.1.8 | Henkel check names: System shall be able to manage CCMS/SCMS/NCMR investigation sample (QM notification Q1/Q2/Q3) workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Test for SCMS/NCMR /CCMS investigation (Based on SCMS, NCMR, CCMS type) |  | Henkel | Completed | Completed
30 | 4.1.5.1.9 | Henkel check names: System shall be able to manage special test sample (Testing for Customer/Supplier/PD/AE/Other sites/MOC/NPI / Improvement project) workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project |  | Henkel | Completed | Completed
31 | 4.1.5.1.10 | Henkel check names: System shall be able to manageretain sample workflow. | Henkel Sample Type |  |  |  | 2024-06-20 |  | Moving sample/material to storage location |  | Henkel | Completed | Completed
32 | 4.1.6.1.7 | Henkel need to offer these dashboard templates. | Non-testing work requirements |  |  |  | 2024-07-30 |  | After Dashboard is discussed, come back to it. |  | Henkel | In Progress | Not Started
33 | 4.1.7.1.1 | System shall be able to manage external test request using non-standard testing workflow.(more than 3 workflows, henkel need to list) | Special testing requirement management |  |  |  | 2024-06-21 |  | 1.Test for SCMS/NCMR /CCMS investigation 2. Test for NCMR-Shelf life extension 3. Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project | Frank | Henkel | Completed | Completed
34 | 4.1.7.1.3 | System shall be able to allow non-QCLaD users to raise test request(Both side need further discussion with Neelima) | Special testing requirement management |  |  |  | 2024-06-21 |  | Discuss in our weekly meeting TF: 1. Account is needed 2. User should be able to login QCLAD for this function Prossible solution: a. TF provides a template, Henkel request users to send an email to dedicated email address with details attached as per TF's template. QCLAD able to get the fields(If this solution is chosen,one solution shoud be considered that test request is attachment to e-mail and it should be automatically downloaded to a folder) populated from the template b. TF provide a web page where the team can enter the details and submit. On submission QCLAD reads the data, and populate the fields c. Henkel creates a webpage and push the data to QCLAD designated DB and fields. QCLAD pulls the results and starts the process. Henkel need to understand what is possible from TF from technical end and provide a cost estimate for same | Frank & Wendy | Henkel & TF | In Progress | Completed
35 | 4.1.7.1.5 | Henkel need to offer testing request templates. | Special testing requirement management |  |  |  | 2024-06-30 |  |  | Care & Horace | Henkel | Completed | Not Started
36 | 4.1.7.1.9 | Henkel want to check the details of the sample status. | Special testing requirement management |  |  |  | 2024-06-30 |  | Sample approval/sample scanned/sample assigned/sample tested/sample | Frank | Henkel | Completed | Completed
37 | 4.1.7.1.10 | Henkel need to offer Dashboard template about test status, analysis test workload. | Special testing requirement management |  |  |  | 2024-07-30 |  | After Dashboard is discussed, come back to it. |  | Henkel | In Progress | Not Started
38 | 4.2.1.1.18 | Henkel team send us logical rule about the assign task automatically. | Schedular |  |  |  | 2024-06-30 |  | Details will be described within the workflow,ask question from TF team TF: waiting for workflow Henkel:Need to provide priority of rules. | Frank & Neelima | Henkel | Completed | Completed
39 | 4.2.1.1.19 | Henkel team send us the detail information thermofisher listed of OSDP. Noted: Sync daily. (TF list the detail information (mapping fileds required) first) | Schedular |  |  |  | 2024-07-05 |  | Waiting for TF reply, Henkel have provided workflow nothing pending | Neelima | Henkel | Completed | Completed
40 | 4.2.1.1.19 | TF list the detail information (mapping fields required) of OSDP first. | Schedular |  |  |  | 2024-07-30 |  |  | ZhenJuan | TF | Not Started | Not Started
41 | 4.2.1.4.4 | Frequency need to double confirm by TF – testing arrangement | Schedular |  |  |  | 2024-07-01 |  | frequency = Twice a day Comments from Henkel:suggested to assign task automatically after scanning sample Henkel: Task assigned after when sample is scanned and entered lab or |  | TF | Completed | Completed
42 | 4.2.1.8.2 | Henkel need offer shift template | Schedular |  |  |  | 2024-06-30 |  |  | Frank | Henkel | Completed | Not Started
43 | 4.2.1.10.2 | Henkel offer dashboard template, Tony | Schedular |  |  |  | 2024-07-30 |  | After Dashboard is discussed, come back to it. | Lisa | Henkel | In Progress | Not Started
44 | 4.3.2.3.1 | what's Henekel expectation about simplify and stream operation? | Data Capture of Testing Instrument |  | 2024-06-20 |  | 2024-06-20 |  | Only required intruments will be displayed in the sample test based on the SOP, pull the results and display the results. |  | Henkel | Completed | Completed
45 | 4.3.2.4.1 | user need to identifying the sample id in instrument software so that LIMS can match data to samples. | Data Capture of Testing Instrument |  | 2024-06-20 |  | 2024-07-05 |  | User should scan the sample and scan the instrument to do a mapping between the sample and the equipment(Type A and Type B only). Ability to find the OH of the the instrument TF: confirm with Dragon while on site Henkel: check with TF that for Type A should first select instrument and print.For type B,we should type in the batch number.inform Neelima Thermofisher: For Type A,scanning the eqipment label is a possible solution and we need to maintain equipments that can be used for a certain test method.For Type B, It's better to scan the instrument label and then scan samples' label in a sequence. 打QCLaD标签上面有Sample ID，Type B的电脑需要扫码枪扫码在Type B软件中录入Sample ID（0702） |  | Henkel | In Progress | In Progress
46 | 4.4.1.1.1 | seems like sample dashboard | Laboratory Execution |  | 2024-06-20 |  | 2024-06-25 |  | Same as No. 43 |  | Henkel | Completed | Completed
47 | 4.4.1.2.1 | Henkel need to offer 10 feasible SOP so that TF team can creat 10 LES in system. | Laboratory Execution |  | 2024-06-20 |  | before PPB |  | Need to confirm with TF in detail. TF: explain the details with Dragon while on site Henkel: 10 LES will be maintained by Thermofisher in phase B acccording to SOW |  | Henkel | Completed | Completed
48 | 4.4.1.9.1 | what's expectation of follow up? Retest? | Laboratory Execution |  | 2024-06-20 |  | 2024-06-30 | 2024-06-20 | Henkel:System shall allow a comment to enter and specific user to reassign the test to another user. |  | Henkel | Completed | Completed
49 | 4.4.2.1.1 | Henkel need to check use which one solution for handling resampling. | Resampling |  | 2024-06-20 |  | 2024-06-28 |  | Create another sample in the QCLAD, related to the inspection lot (job in the QCLAD) and all the results are sent again to SAP. The result values are updated in SAP. Check with Neelima |  | Henkel | Completed | Completed
50 | 4.7.1.4.1 | does 'update the sample’s workflow information' means modify samples 's attributes? | Sample Tracking |  | 2024-06-20 |  | 2024-06-30 | 2024-06-20 | No, attributes is not been changed but the status may change. Similar to No.36 TF: confirmed |  | Henkel | Completed | Completed
51 | 4.1.1.6 | TF will provide attribute of the sample and Henkel will choose which attributes are needed,4.1.1.20 need to be confirmed after that | Sample Login/Sample Receipt |  | 2024-06-20 |  | 2024-07-30 |  | TF have provided atrributes of the sample to Henkel.Henkel need to check which attribute will be needed. |  | Henkel & TF | In Progress | Completed
52 | 4.4.1.1 | Dashboards showing lab equipment availability. **check if in scope | Laboratory Execution |  | 2024-06-20 |  | 2024-06-30 | 2024-06-20 | Equipment usage can be tracked trhough scanning before and after the usage. |  | Henkel & TF | Completed | Completed
53 | 4.4.1.4 | remotely attach instrument = type B instrument ? | Laboratory Execution |  | 2024-06-20 |  | 2024-06-30 | 2024-06-20 | Henkel:remotely attach instrument = type A and type B instrument |  | Henkel | Completed | Completed
54 | 4.7.1.3 | Noted: can fulfill by folder configuration. | Sample Tracking |  | 2024-06-20 |  | 2024-06-25 |  |  |  |  | Completed | Completed
55 | 4.7.1.6 | does workflow means lifecycle? | Sample Tracking |  | 2024-06-20 |  | 2024-06-25 |  | Lifecycle include multiple workflow |  |  | Completed | Completed
56 | 4.4.1.5 | what's e signature(like peer review)stands for? | Laboratory Execution |  | 2024-06-20 |  | 2024-06-25 |  | Peer review is needed but e signature is out of scope |  |  | Completed | Completed
57 | 4.7.2.5 | thermo SQC function instruction. | Data View and Audit Trail |  | 2024-06-20 |  | 2024-06-25 |  | Not in the scope of QC LaD |  |  | Completed | Completed
58 | 4.7.2.7 | what's third party software? | Data View and Audit Trail |  | 2024-06-20 |  | 2024-06-25 |  | We can download data from QCLaD to excel,pdf,word. We can upload data of third party software as a excel/pdf/word format to QCLaD manually. |  |  | Completed | Completed
59 | 4.7.2.8 | interface means integration? | Data View and Audit Trail |  | 2024-06-20 |  | 2024-06-26 |  | Template TF:checked |  |  | Completed | Completed
60 | 4.7.2.11 | Thermo check local time | Laboratory equipment |  | 2024-06-20 |  | 2024-06-30 | 2024-06-20 | TF:Yes SampleManager lets you specify separate timezones for the server and the client. All dates and times are stored using the timezone settings for the SampleManager server. Retrieved dates and times are converted to the timezone specified for the current operator before being displayed. |  | TF | Completed | Completed
61 | 4.8.1.2 | Need to check maintenance scheduler is in scope with Neelima | Laboratory equipment |  | 2024-06-20 |  | 2024-06-26 |  | It should be in scope.We need the maintainance task to be schedulered, but sending notification to SAP is not in scope. TF:checked |  |  | Completed | Completed
62 | 4.8.1.6 | Henkel need to check NCMR number is not require for instrument | Laboratory equipment |  | 2024-06-20 |  | 2024-06-26 |  | Not required.NCMR is only required by shelf life expiration in SAP. TF:checked |  |  | Completed | Completed
63 | 4.8.2.3 | skill expiry date out of scope in qclad? | personnel |  | 2024-06-20 |  | 2024-06-26 |  | Not in the scope of QC LaD TF:checked |  |  | Completed | Completed
64 | 4.8.3.1 | Henkel need to list other fields. | Stock & Inventory management |  | 2024-06-20 |  | 2024-06-26 |  | In SOP maintained in QCLaD, what fields are required should be clarified by Thermofisher team. TF:checked |  |  | Completed | Completed
65 | 4.8.5.1 | what parameters do we need ro use in calculations? Need to check with Henkel team. | Stock & Inventory management |  | 2024-06-20 |  | 2024-06-26 |  | The same as 4.8.5.4. TF:checked |  |  | Completed | Completed
66 | 4.8.5.4 | What's meaning of the stock solutions? | Stock & Inventory management |  | 2024-06-20 |  | 2024-06-26 |  | System shall automatically deduct the consumption and generate a label clarify expiration date for the new reagent and also be shown in stock inventory.Stock solutions is intermediate solution created from two or more reagents and the SOP of creating the solution should be in SOP in QCLaD. TF:checked |  |  | Completed | Completed
67 | 4.8.5.6 | dragon need maximum amount reminder | Stock & Inventory management |  | 2024-06-20 |  | 2024-06-26 |  | Reminder for minimum and maximum stock based on the master data. TF:checked |  |  | Completed | Completed
68 | 4.8.5.7 | instrument maintenance is out of scope | Stock & Inventory management |  | 2024-06-20 |  | 2024-06-26 |  | The same as 4.8.1.2.This one should be in scope. TF:checked |  |  | Completed | Completed
69 | 4.8.5.7 | automatically assign rule, validation workflow | Stock & Inventory management |  | 2024-06-20 |  | 2024-06-26 |  | 1. LES for agent preparatoin.System shall automatically duduct the consumption. 2. Calibration process for instrument shall be automatic created and assigned to operators. 3. Task shall be auto created and auto assignment for stock below safety stock or about to expired(the date task been created before expiration should be configurable). TF:checked,have a question, how to assign this task for stock Henkel: Automacally assign the task of preparing reagent to QC who will use the reagent today(Typically people who need to do testing with the reagent is able to prepare that.) TF: In QCLAD, system shall auto create LES task and assign task to operator for stock below safety stock or about to expired |  |  | Completed | Completed
52 | 4.9.1.2 | System shall support electronic signature, password checking is required when creating, modifying or removing electronic records.（系统支持在创建、修改、移除记录时触发电子签名并输入密码） | Security & User Access |  | 2024-06-25 |  | 2024-07-01 |  | Only record of Who,when,why changed the master data is needed.Electronic signature, password checking is not required.
53 | 4.9.5.1 | System shall support single sign on for all users.（Henkel user id是想用windows汉高的密码直接登录QCLAD吗？） | Security & User Access |  |  |  | 2024-07-01 |  | Only for white collar is possible.For blue collar, they need user ID and password for QCLaD.
54 | 4.9.1.2 | System shall support electronic signature, password checking is required when creating, modifying or removing electronic records.（系统支持在创建、修改、移除记录时触发电子签名并输入密码） | Security & User Access |  |  |  | 2024-07-01
55 | 4.9.5.3 | HENKEL: one account login to system in multiple devices at same time may required . Need further discuss internally （待确认一个账户是否要能同时登录多设备） | Security & User Access |  |  |  | 2024-07-01 |  | One account for one device or cilent at one time.
56 | 4.9.8.5 | 1、TF Give an example of Site permissions division 2、Henkel Provide a list of permissions for a role, such as the permissions and scope of data that the role needs to view/modify; 1、TF 给个Site权限划分的example 2、Henkel 提供角色的权限清单，例如该角色需要查看/修改数据的权限和范围； | Security & User Access |  |  |  | 2024-07-01
57 | 4.6.1.1.5 | Henkel need to check what's the meaning of report with Neelima | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | Report is pulling data from QCLaD folder with filters.Ask Thermofisher team to clearify whether this 'report' is the same to the report mentioned SOW.And we want Thermofisher team to send sample dashboards and reports for our reference.
58 | 4.6.1.5.3 | What’s the meaning of 'days in available, days out of service'? 怎么理解Days | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | Available days mean how many days instrument are avilable for testing. Days out of serve means number of days not available because of repair or calibration.
59 | 4.6.1.9.2 | what format of the report？The aim of extract data. | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | It's not report but view the data with all the columns and ability to download this.
60 | 4.6.1.10.3 | Why need Σ？ | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | Remove Σ to Maximum time taken between start time in process and end time in case there are mutiple processes.
61 | 4.6.1.10.4 | Time End: sample authorizd time | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | End time should be the time when all final results approved by supervisor and pushed to SAP.
62 | 4.6.1.11.1 | Henkel need to check what's the report of Productivity | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | QC productivity can be valuated according to 3 formulas: QC efficiency 1=Direct QC test LH(IQC+IPQC+OQC,including retest)/QC attendence hours QC efficiency 2=(Direct QC test LH+non-standard QC test LH)/QC attendence hours QC efficiency 3=(Direct QC test LH+non-standard QC test LH+indirect QC LH)/QC attendence hours Standard testing - Direct QC Test Non standard testing - Indirect QC QC attendance hours - based on the shift management
63 | 4.6.1.15.2 | status refers to what? | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | Whether the stock is below the minumum stock and above the maximum stock.
64 | 4.6.1.16.2 | need dashboard. | Dashboard / Report (downloadable) |  |  |  | 2024-07-01 |  | We need retain sample dashboard designed by Henkel, only data is required from TF end.
65 | 4.5 | Thermofisher team need to list fields of master data for inspection plan based on experence, then Henkel will check it and compare to SAP master data for inspeciton plan. | SAP intergration | [7 empty] | TF
66 | 4.5 | Henkel need to check when will the inspection lot of RM synchronised to QCLaD to avoid inspection lot synchronisation before ECOA capture. | SAP intergration | [7 empty] | Henkel
67 | 4.5 | Whether data in QCLaD should be rounded according to SAP rounding rules. | SAP intergration | [7 empty] | Henkel
68 | 4.5 | After the master data is synchronised from SAP, are there any additional fields needed in QCLAD, such as information that is not available in SAP but will be used in QCLAD? | SAP intergration | [7 empty] | Henkel
69 | Viscometer | Henkel Shall provide one sample of viscosity raw data in Excel with viscosity calculation rule(e.g. Last line, average, etc...) and screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-05 |  |  | Horace/Care/Shizhe | Henkel | In Progress
70 | Viscometer | Henkel Shall provide all remaining viscosity raw data in Excel with viscosity calculation rule(e.g. Last line, average, etc...) for all IDH to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-31 |  |  | Horace/Care/Shizhe | Henkel | In Progress
71 | Viscometer | Henkel shall check if the template for MES label can add one barcode with IDH only and another barcode with batch only. If the change of MES label is not feasible Henkel need to print QC LaD label include one IDH barcode and one batch barcode. | Data Gathering |  |  |  | 2024-07-12 |  |  | Horace/Care/Shizhe | Henkel | Not Started
72 | Oil Absorption | Henkel Shall provide one sample of oil absorbtion analyzer report in XRS and screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-05 |  |  | Horace/Care/Shizhe | Henkel | In Progress
73 | TGA | Henkel Shall provide one sample of TGA report in PDF and screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-05 |  |  | Horace/Care/Shizhe | Henkel | In Progress
74 | Particle Sizer | Henkel Shall provide one sample of particle sizer report in PDF and screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-05 |  |  | Horace/Care/Shizhe | Henkel | In Progress
75 | Particle Sizer | Report for particle sizer have dupplicated header. TF need to test if the software can compatible with this situation. Henkel need to contact with instrument manufacturer to check if the template of the report can be changed. | Data Gathering |  |  |  | 2024-07-12 |  |  | Horace/Care/Shizhe | Henkel | Not Started
76 | PH Meter | Manufacturer to decoding data and transfer the data to a distinated location. TF will pull the data from that location. | Data Gathering |  |  |  | 2024-07-31 |  |  | Horace/Care/Shizhe | Henkel | Not Started
77 | Tensile Tester(Local) | Henkel Shall provide one sample of particle sizer report in Word, Excel and PDF with screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-05 |  |  | Horace/Care/Shizhe | Henkel | In Progress
78 | Tensile Tester(Local) | Henkel shall include the pre-heating temperature to the template. | Data Gathering |  | 2024-07-02 |  | 2024-07-02 | 2024-07-02 |  | Horace/Care/Shizhe | Henkel | Completed
79 | Tensile Tester(Local) | Henkel shall include pre-heating temperature and batch No. to all test method | Data Gathering |  | 2024-07-02 |  | 2024-07-31 |  |  | Horace/Care/Shizhe | Henkel | In Progress
80 | Solid Content | Henkel Shall provide one sample of particle sizer report in Excel with screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-05 |  |  | Horace/Care/Shizhe | Henkel | In Progress
81 | Rethometer | Henkel Shall provide one sample of rethometer report in PDF with screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-05 |  |  | Horace/Care/Shizhe | Henkel | In Progress
82 | Rethometer | Henkel Shall provide rest of the template of rethometer report in PDF with screenshot for the related 3rd party software to TF for reference. | Data Gathering |  | 2024-07-02 |  | 2024-07-31 |  |  | Horace/Care/Shizhe | Henkel | In Progress
83 | Rethometer | TF shall proceed the data with certain calculation after pull the data. | Data Gathering |  |  |  | 2024-07-31 |  |  |  | TF | Not Started
84 | Tensile Tester(Zwick) | Henkel shall check with manufacuter how to input batch No., pre-heating tempature and etc. | Data Gathering |  |  |  | 2024-07-31 |  |  | Horace/Care/Shizhe | Henkel | Not Started
85 | Titration | Henkel shall decide go with cable or USB | Data Gathering |  |  |  | 2024-07-31 |  |  | Horace/Care/Shizhe | Henkel | Not Started
Note on J51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Frank Shen is this completed? I am not clear on the provided details?
Note on C74: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Same with No 52