## Task List
QCLAD Detail Requirement Gathering Task List Jun/14th/2024
No | RTM reference | Task | Function Area | 计划开始日期 | Start Date | 计划完成日期 | Due Date | Complete Date | Note | PIC | Responsible Party | Status
1 | 4.1.1.1.2 | Henkel offer the log in sample request template for reference. | Sample Login/Sample Receipt | 2024-05-08 |  | 2024-05-10 | 2024-06-30 |  | Check with Care & Horace | Care & Horace | Henkel | Not Started
2 | 4.1.1.3.3 | Henkel need to check label template with Dragon. ( offer QR code rule ) | Sample Login/Sample Receipt |  |  |  | 2024-06-30 |  | Check with Eagle | Frank | Henkel | Not Started
3 | 4.1.1.3.5 | Henkel offer sample ID naming rules for non-standard Sample .(TF give some sample ID naming rules examples) | Sample Login/Sample Receipt |  |  |  | 2024-06-30 |  | SAP plant code+Sample Type+Date（to day）+SequenceNo based on Plant code & Date & Sample Type TF:SequenceNo should consider plant code? Henkel：Yes,0759 for Dragon | Frank | Henkel | Completed
4 | 4.1.1.3.5 | TF provide Sample ID naming rules/examples for Henkel to select | Sample Login/Sample Receipt |  |  |  | 2024-06-14 |  | Gu Cheng sent email about the examples | Gu Cheng | TF | Completed
5 | 4.1.1.7.2 | Henkel need to check function of sample type and sampling plans with Maline. | Sample Login/Sample Receipt |  |  |  | 2024-06-21 |  | Sampling plan set as configurable rules in QCLaD,sample type can be found in workflows TF: is sampling plan means preset test methods for sample(like inspection plan in SAP)? Henkel:No, For sample plan it's like sample quantity, there should be configurable setting for each IDH and can be changed when sample received | Lisa | Henkel | Completed
6 | 4.1.1.19.1 | Henkel need to check this requirement with Neelima: The system shall provide functionality to allow entry of any irregularities recorded and route sample according to laboratory business rules | Sample Login/Sample Receipt |  |  |  | 2024-06-21 |  | Non-QCLaD user sample login TF: Still don't understand, provide example/more info Henkel:Irregularities record means Notes for non-routing test request | Neelima | Henkel | Not Started
7 | 4.1.2.10.1 | Need check what is the pre-set method limits with Neelima. | Sample Testing/Results Entry | [5 empty] | Pre-set method = specification |  | Henkel | Completed
8 | 4.1.2.12.5 | Henkel need check what is the time taken with Neelima & Maline | Sample Testing/Results Entry | [5 empty] | Actual cycle time |  | Henkel | Completed
9 | 4.1.2.13.2 | Henkel need check what is the qualified numeric with Neelima. | Sample Testing/Results Entry | [5 empty] | number 0 - 9 |  | Henkel | Completed
10 | 4.1.2.12.6 | Video is possible based on last comment from TF. Size details have to be provided. | Sample Testing/Results Entry |  | 2024-06-12 |  |  |  | This can be implemented in QCLAD.Maximaum size need to be confirmed by TF The size depends on Henkel service capability |  | TF | Completed
11 | 4.1.2.23.1 | Henkel needs to confirm: System shall be able to enforce entry of a justification if there is a retest/resample. - If resample is correct word. | Sample Testing/Results Entry | [5 empty] | Confirmed to be resample |  | Henkel | Completed
12 | 4.1.2.24.1 | SQC is not in scope. Check if trend chart function is still needed | Sample Testing/Results Entry |  |  |  | 2024-06-21 |  | Check with Thermofisher team for what trend chart they can provide and any additional cost out of SOW? | Frank | Henkel | Not Started
13 | 4.1.2.25.2 | Henkel need to check the detail about peer review & Approval for test result with Maline | Sample Testing/Results Entry |  |  |  | 2024-06-21 |  | Supervisor review is needed before QCLaD push data to SAP/generate report(for non-standard).Group the material, for some of them need approval, some of them don't. For the setting we can change it. We need the function of peer review and Approval both. TF:clearify which sample types needs approval. Henkel:For IDH,we can set Approval or not. For test method final result, we can set peer review or not. | Frank | Henkel | Completed
14 | 4.1.2.28.1 | Henkel need to offer dashboard template. | Sample Testing/Results Entry | [5 empty] | After Dashboard is discussed, come back to it. |  | Henkel | Not Started
15 | 4.1.3.1.2 | Henkel need check if all sample type need approve with Neelima. | Authorization |  |  |  | 2024-06-21 |  | Same with 4.1.2.25.2 | Frank | Henkel | Completed
16 | 4.1.4.5.2 | Henkel need to check if the electrical signature is picture with stakeholders. | Reporting |  |  |  | 2024-06-21 |  | Check with Neelima,not avilable in phase 1,check with TF the feasibility TF: please confirm we won't do it in pilot phase. Feasibility: yes Henkel confirm it is not in pilot scope | Frank | Henkel | Completed
17 | 4.1.4.5.3 | This is an out of scope function, Henkel needs to confirm if want to implement this function: System shall be able to support end app insert handwritting signature by pad | Reporting |  |  |  | 2024-06-21 |  | Check with Neelima,not avilable in phase 1,check with TF the feasibility TF:feasibility: No Henkel confirm it is not in scope. | Frank | Henkel | Completed
18 | 4.1.4.5.3 | If Henkel wants to implement this, TF check the how to implement it: System shall be able to support end app insert handwritting signature by pad | Reporting | [5 empty] | Same with 4.1.4.5.2 | HongTao | TF | Completed
19 | 4.1.4.6.2 | Henkel need to check the meaning of shedules with team members. | Reporting |  |  |  | 2024-06-21 |  | Check with Neelima,whenever the test is trigger by sample recipt or schedule,the data should be avilable and report will be generated TF: Update in the RTM | Frank | Henkel | Completed
20 | 4.1.4.10.2 | Henkel need to offer all report template. | Reporting |  |  |  | 2024-06-30 |  |  | Care & Horace | Henkel | Not Started
21 | 4.1.4.14.2 | Henkel offer the details and scenario about the notifications and alert messages. | Reporting |  |  |  | 2024-06-30 |  | Check with Neelima,about to expire or below safety stork,alert should be sent to certain group basically in LIMS system. TF: This is for reporting module, what is the purpose of this function in reporting? Henkel:Notication bell icon to display alerts and nofications | Frank | Henkel | Completed
22 | 4.1.5.1.1 | Henkel add workflow name: System shall be able to manage Raw material sample (ROH) workflow. | Henkel Sample Type | [5 empty] | RM test for Incoming | Frank | Henkel | Completed
23 | 4.1.5.1.2 | Henkel add workflow name: System shall be able to manage semi-finish goods sample/ bulk sample (UNB & UNF) workflow. | Henkel Sample Type | [5 empty] | Standard in process testing for semi finished and finished goods |  | Henkel | Completed
24 | 4.1.5.1.3 | Henkel check names: System shall be able to manage finish goods sample (FER) workflow. | Henkel Sample Type | [5 empty] | Standard finished goods outgoing test. |  | Henkel | Completed
25 | 4.1.5.1.4 | Henkel check names: System shall be able to manage consumable workflow. | Henkel Sample Type | [5 empty] | Consumables incoming test |  | Henkel | Completed
26 | 4.1.5.1.5 | Henkel check names: System shall be able to manage package material workflow. | Henkel Sample Type | [5 empty] | Package material incoming test |  | Henkel | Completed
27 | 4.1.5.1.6 | Henkel check names: System shall be able to manage instrument calibration sample workflow. | Henkel Sample Type | [5 empty] | Instrument calibration sample test |  | Henkel | Completed
28 | 4.1.5.1.7 | Henkel check names: System shall be able to manage MSA test sample workflow. | Henkel Sample Type | [5 empty] | Test for MSA |  | Henkel | Completed
29 | 4.1.5.1.8 | Henkel check names: System shall be able to manage CCMS/SCMS/NCMR investigation sample (QM notification Q1/Q2/Q3) workflow. | Henkel Sample Type | [5 empty] | Test for SCMS/NCMR /CCMS investigation (Based on SCMS, NCMR, CCMS type) |  | Henkel | Completed
30 | 4.1.5.1.9 | Henkel check names: System shall be able to manage special test sample (Testing for Customer/Supplier/PD/AE/Other sites/MOC/NPI / Improvement project) workflow. | Henkel Sample Type | [5 empty] | Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project |  | Henkel | Completed
31 | 4.1.5.1.10 | Henkel check names: System shall be able to manageretain sample workflow. | Henkel Sample Type | [5 empty] | Moving sample/material to storage location |  | Henkel | Completed
32 | 4.1.6.1.7 | Henkel need to offer these dashboard templates. | Non-testing work requirements |  |  |  | 2024-06-30 |  | After Dashboard is discussed, come back to it. |  | Henkel | Not Started
33 | 4.1.7.1.1 | System shall be able to manage external test request using non-standard testing workflow.(more than 3 workflows, henkel need to list) | Special testing requirement management |  |  |  | 2024-06-21 |  | 1.Test for SCMS/NCMR /CCMS investigation 2. Test for NCMR-Shelf life extension 3. Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project | Frank | Henkel | Completed
34 | 4.1.7.1.3 | System shall be able to allow non-QCLaD users to raise test request(Both side need further discussion with Neelima) | Special testing requirement management |  |  |  | 2024-06-21 |  | Discuss in our weekly meeting TF: 1. Account is needed 2. User should be able to login QCLAD for this function Prossible solution: a. TF provides a template, Henkel request users to send an email to dedicated email address with details attached as per TF's template. QCLAD able to get the fields populated from the template b. TF provide a web page where the team can enter the details and submit. On submission QCLAD reads the data, and populate the fields c. Henkel creates a webpage and push the data to QCLAD designated DB and fields. QCLAD pulls the results and starts the process. Henkel need to understand what is possible from TF from technical end and provide a cost estimate for same | Frank & Wendy | Henkel & TF | Not Started
35 | 4.1.7.1.5 | Henkel need to offer testing request templates. | Special testing requirement management |  |  |  | 2024-06-30 |  |  | Care & Horace | Henkel | Not Started
36 | 4.1.7.1.9 | Henkel want to check the details of the sample status. | Special testing requirement management |  |  |  | 2024-06-30 |  | Sample approval/sample scanned/sample assigned/sample tested/sample | Frank | Henkel | Completed
37 | 4.1.7.1.10 | Henkel need to offer Dashboard template about test status, analysis test workload. | Special testing requirement management |  |  |  | 2024-06-30 |  | After Dashboard is discussed, come back to it. |  | Henkel | Not Started
38 | 4.2.1.1.18 | Henkel team send us logical rule about the assign task automatically. | Schedular |  |  |  | 2024-06-30 |  | Details will be described within the workflow,ask question from TF team TF: waiting for workflow Henkel:Need to provide priority of rules. | Frank & Neelima | Henkel | Completed
39 | 4.2.1.1.19 | Henkel team send us the detail information thermofisher listed of OSDP. Noted: Sync daily. (TF list the detail information (mapping fileds required) first) | Schedular | [5 empty] | Waiting for TF reply, Henkel have provided workflow nothing pending | Neelima | Henkel | Completed
40 | 4.2.1.1.19 | TF list the detail information (mapping fields required) of OSDP first. | Schedular |  |  |  | 2024-06-30 |  |  | ZhenJuan | TF | Not Started
41 | 4.2.1.4.4 | Frequency need to double confirm by TF – testing arrangement | Schedular | [5 empty] | frequency = Twice a day |  | TF | Completed
42 | 4.2.1.8.2 | Henkel need offer shift template | Schedular |  |  |  | 2024-06-30 |  |  | Frank | Henkel | Not Started
43 | 4.2.1.10.2 | Henkel offer dashboard template, Tony | Schedular |  |  |  | 2024-06-30 |  | After Dashboard is discussed, come back to it. | Lisa | Henkel | Not Started
44 | 4.3.2.3.1 | what's Henekel expectation about simplify and stream operation? | Data Capture of Testing Instrument | [5 empty] | Only required intruments will be displayed in the sample test based on the SOP, pull the results and display the results. |  | Henkel | Completed
45 | 4.3.2.4.1 | user need to identifying the sample id in instrument software so that LIMS can match data to samples. | Data Capture of Testing Instrument | [5 empty] | User should scan the sample and scan the instrument to do a mapping between the sample and the equipment(Type A and Type B only). Ability to find the OH of the the instrument TF: confirm with Dragon while on site Henkel: check with TF that for Type A should first select instrument and print.For type B,we should type in the batch number. |  | Henkel | Completed
46 | 4.4.1.1.1 | seems like sample dashboard | Laboratory Execution | [5 empty] | Same as No. 43 |  | Henkel | Completed
47 | 4.4.1.2.1 | Henkel need to offer 10 feasible SOP so that TF team can creat 10 LES in system. | Laboratory Execution |  |  |  | before PPB |  | Need to confirm with TF in detail. TF: explain the details with Dragon while on site Henkel: 10 LES will be maintained by Thermofisher in phase B acccording to SOW |  | Henkel | Not Started
48 | 4.4.1.9.1 | what's expectation of follow up? Retest? | Laboratory Execution | [5 empty] | Need further check with Neelima |  | Henkel | Not Started
49 | 4.4.2.1.1 | Henkel need to check use which one solution for handling resampling. | Resampling | [5 empty] | Need further discussion internally |  | Henkel | Not Started
50 | 4.7.1.4.1 | does 'update the sample’s workflow information' means modify samples 's attributes? | Sample Tracking | [5 empty] | No, attributes is not been changed but the status may change. Similar to No.36 TF: confirm with Dragon while on site |  | Henkel | Completed
51 | 4.1.1.6 | TF will provide attribute of the sample and Henkel will choose which attributes are needed,4.1.1.20 need to be confirmed after that | Sample Login/Sample Receipt | [7 empty] | Henkel & TF | Not Started