## Analysis
Title | Items Number | Title | Items number
SMIDI can do | 1 | SMIDI can do high level | 1
SMIDI cannot do | 9 | SMIDI cannot do high level | 6
Title | effort
SMIDI can do | 28
SMIDI cannot do | 32

## To customer
No. | RTM Reference | Henkel requirements | Priority | Can be done by SMIDI | SMIDI + Customisation - Day | Customisation- Day | Commends
1 | 4.5.1.1 | System shall support download inspection lot from SAP to QCLAD. 1）Create a sample in QCLAD based on the downloaded Inspection Lot, or change an existing sample (JIT process). 2）If the inspection lot in SAP also has multiple activities, then QCLAD needs to create multiple samples. 3）The test item in lot has a field for whether or not to skip the batch (dynamic message), and whether the SMIDI standard function can be written directly to the test table. |  | 1) Yes 2) YES 3) YES | 0 | 10
2 | 4.5.1.2 | System shall support download Batch information from SAP to QCLAD. Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. solution 1:Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. solution 2:Add fields from Batch information to QAIVC table，Pending confirmation by Henkel. |  | Yes, solution 1 | 4 | 4 | solution 1-SMIDI：Add fields from Batch information to QAIVC table,Write directly to the sample table，Need confirmation by Henkel,-- 0days solution 2:Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. -- 4days solution 3-Cus：Put the Batch field into the JSON string downloaded by lot and write it directly to the sample table；-- 0days
3 | 4.5.1.3 | System shall support download Inspection Plan from SAP to QCLAD. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
4 | 4.5.1.4 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the MIC. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
5 | 4.5.1.5 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the specification. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
6 | 4.5.1.6 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the Material master data. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
7 | 4.5.1.7 | System shall support download Plant from SAP to QCLAD. Plant is a separate entity that needs to be downloaded to the Plant table in QCLAD. |  | No | 3 | 3 | SMIDI cannot get info from seperate table
8 | 4.5.1.8 | System shall support download QM notification from SAP to QCLAD. QM notification is a separate entity that needs to be downloaded to the QM notification table in QCLAD. |  | No | 3 | 3 | SMIDI cannot get info from seperate table
9 | 4.5.1.9 | System shall support to upload result value from QCLAD to SAP. 1）When there is a Retest operation done, the result of the last Retest needs to be returned to SAP. 2）once the LIMS post result back to SAP，SAP MIC status should be auto rejected or accepted? 3）system shall support post all the samples result back to SAP, including the resampled sample. 4）related to item 1, whether Smidi can configure that, once inspection lot is downloaded mapped with an existing sample in LIMS; if that sample is authorized with result, then Smidi can also trigger the result pushing to SAP? (JIT process) |  | 1) No 2) Yes 3）Yes 4）Yes | 5 | 6 | 1) No, read these results is impossible. Only the first test result can be send back. 2) Yes, configure in SAP 3) Depending on the SAP setup this is possible.
|  |  |  | SOW:28days | SMIDI:28 + Cus:27 = 55 | 38
|  |  |  | Extra Effort | 27 | 10

## Sheet2
Plant Sync
QM notification Sync
Material Sync
MIC Sync
Inspection plan Sync
Specification Sync
Inspection lot Sync
Results back

## Sheet1
No. | Henkel requirements | Importance | Can SMIDI be done | SMIDI + Customisation - Days of Work Evaluation | Customisation- Days of Work Evaluation | Commends
1 | System shall support download inspection lot from SAP to QCLAD. 1）Create a sample in QCLAD based on the downloaded Inspection Lot, or change an existing sample (JIT process). 2）If the inspection lot in SAP also has multiple activities, then QCLAD needs to create multiple samples. 3）When downloading the Inspection lot, if the lot already has some results in SAP, you need to download the results that already exist in SAP together to QCLAD and store them in the Result table, Same as article 10. 4）The test item in lot has a field for whether or not to skip the batch (dynamic message), and whether the SMIDI standard function can be written directly to the test table. | high | 1) Yes，Pending confirmation by Vinoth，send result back need result confirmation number which comes from SAP. 2) YES 3) No，confirmed by Vinoth 4) YES | SMIDI Total: 30+（TBD） | 10
2 | System shall support download Batch information from SAP to QCLAD. Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. solution 1:Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. solution 2:Add fields from Batch information to QAIVC table，Pending confirmation by Henkel. | middle | No,consider solution 2 smidi cannot get info from seperate table | 4 | 4 | solution 1:Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. -- 4days solution 2-SMIDI：Add fields from Batch information to QAIVC table,Write directly to the sample table，Pending confirmation by Henkel,-- 0days solution 3-Cus：Put the Batch field into the JSON string downloaded by lot and write it directly to the sample table；-- 0days
3 | System shall support download Inspection Plan from SAP to QCLAD. Needs to be synchronised and updated in real time. | high | No，customer want to sync in real time, but In SMIDI is impossible. | 3 | 3
4 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the MIC. Needs to be synchronised and updated in real time. | high | No，customer want to sync in real time, but In SMIDI is impossible. | 3 | 3
5 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the specification. Needs to be synchronised and updated in real time. | high | No，customer want to sync in real time, but In SMIDI is impossible. | 3 | 3
6 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the Material master data. Needs to be synchronised and updated in real time. | high | No，customer want to sync in real time, but In SMIDI is impossible. | 3 | 3
7 | System shall support download Plant from SAP to QCLAD. Plant is a separate entity that needs to be downloaded to the Plant table in QCLAD. | middle | No smidi cannot get info from seperate table | 3 | 3
8 | System shall support download QM notification from SAP to QCLAD. QM notification is a separate entity that needs to be downloaded to the QM notification table in QCLAD. | middle | No smidi cannot get info from seperate table | 3 | 3
9 | System shall support to upload result value from QCLAD to SAP. 1）When there is a Retest operation done, the result of the last Retest needs to be returned to SAP. 2）once the LIMS post result back to SAP，SAP MIC status should be auto rejected or accepted? 3）system shall support post all the samples result back to SAP, including the resampled sample. 4）related to item 1, whether Smidi can configure that, once inspection lot is downloaded mapped with an existing sample in LIMS; if that sample is authorized with result, then Smidi can also trigger the result pushing to SAP? (JIT process) | high | 1) No, read these results is impossible. Only the first one Only the first test result can be send back. 2) Yes，configure in SAP 3）No，confirmation by Vinoth 4）pending，Pending confirmation by Vinoth of EOD | 6 | 6
10 | System shall support to upload result value from SAP to QCLAD. When downloading the Inspection lot, download the results that already exist in SAP to QCLAD as well. | high | No，confirmation by Vinoth | 4 | 4
|  |  | SOW:28days | SMIDI:30(TBD) + Cus:32 = 62 | 42

## SMIDI Discussion_0725
No. | Questions | Translation | Can do? | How to do | Status
1 | Material master：主数据的下载同步是独立的吗？还是必须跟着lot下载时，才会将主数据进行下载；确认同步机制（是否可以实时同步）update是直接更新还是升版更新 | Material master download: is the download synchronization of master data independent? Or must it follow the lot download before the master data will be downloaded; confirm the synchronization mechanism (whether it can be synchronized in real time) update is a direct update or upgraded update | No，customer want to sync in real time, but In SMIDI is impossible. | 1. master data will only sync when inspection lot comes 2. overwrite or new version is configurable | Confirmed
2 | 根据Mat code、plant code and batch no三个字段组合匹配的，是update exiting sample还是创建一个新的；如果是update，则需要将sample结果先回传给SAP，确认SMIDI是怎么做？ | Inspection Lot download：Based on the Mat code, plant code and batch no combination of three fields that match, is it update exiting sample or create a new one; if it's update, then you need to send the sample result back to SAP first to confirm how SMIDI is doing? | pending | send result back need result confirmation number which comes from SAP. | pending
3 | Henkel 存在一个lot对应多个activity no，则对于LIMS创建多个sample，确认SMIDI能否实现？怎么做？ | Inspection Lot download：Henkel there exists a lot corresponding to multiple activity no, then for LIMS need to create multiple samples to confirm that SMIDI can be achieved? How? | Yes | configrable. | confirmed
4 | 对于retest，必须要找最后一个test结果回传，SMIDI标准功能能做到吗？ | Results back：For retest, one has to look for the last test result to pass back, can the SMIDI standard function do that? | No, read these results is impossible. Only the first one | Only the first test result can be send back. | confirmed
5 | lot中的检测项目上有是否跳批字段（动态信息），SMIDI标准功能能否直接写入test表中 | Inspection Lot download：The test item in lot has a field for whether or not to skip a batch (dynamic data), and whether the SMIDI standard function can be written directly to the test table. | Yes | query configuration | confirmed
6 | Batch如果作为单独一张表下载到LIMS，确认SMIDI能不能做 | Batch information download：Batch if downloaded to LIMS as a separate table, confirming that SMIDI can do it | No,consider solution 2 | smidi cannot get info from seperate table | confirmed
7 | Plant 是一张表不是一个字段，确认SMIDI能否做，如果能做，简单说明，给些前置条件； | Plant information download：Plant is a table not a field, confirm if SMIDI can do it and if so, briefly explain and give some preconditions; | No | smidi cannot get info from seperate table | confirmed
8 | 修约规则、跳批规则SMIDI可以下载吗 | Material master download: Rounding Rules, Jump lot Rules SMIDI can be downloaded? | No | Significant figures is ok | confirmed
9 | Inspection Lot下载：Status中含有REL，确认能否用SMIDI做？ | Inspection Lot download：Status contain 'REL' in it, confirm if it can be done with SMIDI? | Yes | smidi can filter lot status | confirmed
10 | Work center： Henkel是multiple的，需求是一个workcenter过来的lot就是一个group，可以做不同的workcenter的组别隔离； | Work center: multiple, the demand is a workcenter over the lot is a group, can Smidi do different workcenter group isolation; | Yes | Can use plant code as group mark | confirmed
11 | Inspection Type包含01PQ、04P，确认在SMIDI中可以维护吗？多个条件一次性去维护Query，SMIDI怎么做？ | Inspection Lot download：Inspection Type contains 01PQ, 04P, confirmed to be maintainable in SMIDI? How does SMIDI do it when multiple conditions go to maintain Query at once? | Yes | multipe filter | confirmed