## CH&EN
No. | Questions | Translation | Can do? | How to do | Status
1 | Material master：主数据的下载同步是独立的吗？还是必须跟着lot下载时，才会将主数据进行下载；确认同步机制（是否可以实时同步）update是直接更新还是升版更新 | Material master download: is the download synchronization of master data independent? Or must it follow the lot download before the master data will be downloaded; confirm the synchronization mechanism (whether it can be synchronized in real time) update is a direct update or upgraded update | No，customer want to sync in real time, but In SMIDI is impossible. | 1. master data will only sync when inspection lot comes 2. overwrite or new version is configurable | Confirmed
2 | 根据Mat code、plant code and batch no三个字段组合匹配的，是update exiting sample还是创建一个新的；如果是update，则需要将sample结果先回传给SAP，确认SMIDI是怎么做？ | Inspection Lot download：Based on the Mat code, plant code and batch no combination of three fields that match, is it update exiting sample or create a new one; if it's update, then you need to send the sample result back to SAP first to confirm how SMIDI is doing? | pending | send result back need result confirmation number which comes from SAP. | pending
3 | Henkel 存在一个lot对应多个activity no，则对于LIMS创建多个sample，确认SMIDI能否实现？怎么做？ | Inspection Lot download：Henkel there exists a lot corresponding to multiple activity no, then for LIMS need to create multiple samples to confirm that SMIDI can be achieved? How? | Yes | configrable. | confirmed
4 | 对于retest，必须要找最后一个test结果回传，SMIDI标准功能能做到吗？ | Results back：For retest, one has to look for the last test result to pass back, can the SMIDI standard function do that? | No, read these results is impossible. Only the first one | Only the first test result can be send back. | confirmed
5 | lot中的检测项目上有是否跳批字段（动态信息），SMIDI标准功能能否直接写入test表中 | Inspection Lot download：The test item in lot has a field for whether or not to skip a batch (dynamic data), and whether the SMIDI standard function can be written directly to the test table. | Yes | query configuration | confirmed
6 | Batch如果作为单独一张表下载到LIMS，确认SMIDI能不能做 | Batch information download：Batch if downloaded to LIMS as a separate table, confirming that SMIDI can do it | No,consider solution 2 | smidi cannot get info from seperate table | confirmed
7 | Plant 是一张表不是一个字段，确认SMIDI能否做，如果能做，简单说明，给些前置条件； | Plant information download：Plant is a table not a field, confirm if SMIDI can do it and if so, briefly explain and give some preconditions; | No | smidi cannot get info from seperate table | confirmed
8 | 修约规则、跳批规则SMIDI可以下载吗 | Material master download: Rounding Rules, Jump lot Rules SMIDI can be downloaded? | No | Significant figures is ok | confirmed
9 | Inspection Lot下载：Status中含有REL，确认能否用SMIDI做？ | Inspection Lot download：Status contain 'REL' in it, confirm if it can be done with SMIDI? | Yes | smidi can filter lot status | confirmed
10 | Work center： Henkel是multiple的，需求是一个workcenter过来的lot就是一个group，可以做不同的workcenter的组别隔离； | Work center: multiple, the demand is a workcenter over the lot is a group, can Smidi do different workcenter group isolation; | Yes | Can use plant code as group mark | confirmed
11 | Inspection Type包含01PQ、04P，确认在SMIDI中可以维护吗？多个条件一次性去维护Query，SMIDI怎么做？ | Inspection Lot download：Inspection Type contains 01PQ, 04P, confirmed to be maintainable in SMIDI? How does SMIDI do it when multiple conditions go to maintain Query at once? | Yes | multipe filter | confirmed

## CH
No. | Questions | Can do? | How to do | Status
1 | Material master：主数据的下载同步是独立的吗？还是必须跟着lot下载时，才会将主数据进行下载；确认同步机制（是否可以实时同步）update是直接更新还是升版更新
2 | 根据Mat code、plant code and batch no三个字段组合匹配的，是update exiting sample还是创建一个新的；如果是update，则需要将sample结果先回传给SAP，确认SMIDI是怎么做？
3 | Henkel 存在一个lot对应多个activity no，则对于LIMS创建多个sample，确认SMIDI能否实现？怎么做？
4 | 对于retest，必须要找最后一个test结果回传，SMIDI标准功能能做到吗？
5 | lot中的检测项目上有是否跳批字段（动态信息），SMIDI标准功能能否直接写入test表中
6 | Batch如果作为单独一张表下载到LIMS，确认SMIDI能不能做
7 | Plant 是一张表不是一个字段，确认SMIDI能否做，如果能做，简单说明，给些前置条件；
8 | 修约规则、跳批规则SMIDI可以下载吗
9 | Inspection Lot下载：Status中含有REL，确认能否用SMIDI做？
10 | Work center： Henkel是multiple的，需求是一个workcenter过来的lot就是一个group，可以做不同的workcenter的组别隔离；
11 | Inspection Type包含01PQ、04P，确认在SMIDI中可以维护吗？多个条件一次性去维护Query，SMIDI怎么做？

## EN
No. | Translation | Can do? | How to do | Status
1 | Material master download: is the download synchronization of master data independent? Or must it follow the lot download before the master data will be downloaded; confirm the synchronization mechanism (whether it can be synchronized in real time) update is a direct update or upgraded update
2 | Inspection Lot download：Based on the Mat code, plant code and batch no combination of three fields that match, is it update exiting sample or create a new one; if it's update, then you need to send the sample result back to SAP first to confirm how SMIDI is doing?
3 | Inspection Lot download：Henkel there exists a lot corresponding to multiple activity no, then for LIMS need to create multiple samples to confirm that SMIDI can be achieved? How?
4 | Results back：For retest, one has to look for the last test result to pass back, can the SMIDI standard function do that?
5 | Inspection Lot download：The test item in lot has a field for whether or not to skip a batch (dynamic data), and whether the SMIDI standard function can be written directly to the test table.
6 | Batch information download：Batch if downloaded to LIMS as a separate table, confirming that SMIDI can do it
7 | Plant information download：Plant is a table not a field, confirm if SMIDI can do it and if so, briefly explain and give some preconditions;
8 | Material master download: Rounding Rules, Jump lot Rules SMIDI can be downloaded?
9 | Inspection Lot download：Status contain 'REL' in it, confirm if it can be done with SMIDI?
10 | Work center: multiple, the demand is a workcenter over the lot is a group, can Smidi do different workcenter group isolation;
11 | Inspection Lot download：Inspection Type contains 01PQ, 04P, confirmed to be maintainable in SMIDI? How does SMIDI do it when multiple conditions go to maintain Query at once?