## Updated Gap Analysis 8.2
No | Key tasks/Milestones | Content | Deliverables | PPA Original | PPA Estimation After workshop | PPA Gap | PPB Original | PPB Estimation After workshop | PPB Gap | SOW No.
1. | Kick-off & General Project Effort | Workshop | Project management alignment, etc | 6 | 6 |  |  |  |  | 1
2. | SampleManager Training | User training | SampleManager Standard Course | 22 | 22 |  |  |  |  | 21
3. | Requirements Gathering Workshops and Architecture analysis | Requirements Gathering, RTM signoff | RTM | 16 | 21 | 5 |  |  |  | 2
|  | Instrument Investigation | Instrument Survey | 8 | 8 |  |  |  |  | 3
4. | Installation and deployment on Dev, Test and Prod servers | Environment installation (Test, PROD) | Finish the installation | 2 | 2 |  | 2 | 2 |  | 18
5. | Function implementation | Sample | System with functions implemented | 63 | 34 |  | 10 | 4 |  | 4,5
|  | Stock |  |  | 13 |  |  |  |  | 4,5
|  | Instrument |  |  | 4 |  |  |  |  | 4,5
|  | Retain |  |  | 2 | 11 |  |  | -6 | 4,5
|  | Security |  |  | 2 |  |  |  |  | 4,5
|  | Training |  |  | 0 |  |  |  |  | 4,5
|  | Other |  |  | 19 |  |  |  |  | 4,5 | Remove two OOO items
|  | Report (6, not statistics) |  | 18 | 18 |  |  |  |  | 9
|  | Label (8) |  | 10 | 10 |  |  |  |  | 10
|  | Workflow (4 + 10) |  | 7 | 24 | 17 | 23 | 26 | 3 | 6 | Add function: Test result copy
|  | Dashboard (1 static) |  | 3 | 16 | 13 |  |  |  | 11
|  | Shift& Scheduler |  | 6 | 16 | 10 | 6 | 23 | 17 | 7
6. | Interfaces | A:SAP | Interfaces modules | 28 | 34 | 6 | 39 | 51 | 12 | 14
B:Vegam, OSDP
7. | Basic Data Entry | Static Data Assistance | Finish the Data entry | 10 | 10 |  | 5 | 5 |  | 12
|  | LES |  |  |  |  | 30 | 30 |  | 8
8. | Instrument Integration | Instrument Integration (A：3+5 | Instrument Integration | 17 | 17 |  | 36 | 36 |  | 13
|  | / B：2+10) | [7 empty] | 16
9. | Documentation | RTM, Functional Specification, Configuration Summary, User Manual for SampleManager, and Instrument connection repository | Deliver the documents | 10 | 10 |  | 6 | 6 |  | 15
10. | System Integration Testing | System Integration Testing | Finish System Integration Testing | 8 | 8 |  | 12 | 12 |  | 17
11. | UAT and Go Live Support | UAT and Go Live Support | Hypercare | 10 | 10 |  |  |  |  | 19
12. | Project Management | Project Plan, Communication, Resource management, Quality Ensurrance, Progress management, Risks, etc. | Weekly status Report | 34 | 34 |  | 28 | 28 |  | 20
13. | Total |  |  | 278 | 340 | 62 | 197 | 223 | 26

## SOW
No | Tasks | Effort Pilot Phase A | Effort Pilot Phase B – Hybrid Model
1 | Kick-off & General Project Effort | 6 | 0
2 | Requirements Gathering Workshops and Architecture analysis | 16 | -
3 | Instrument Survey | 8 | -
4 | Basic configuration for Stock, Scheduler, Instrument calibration setup, Folder, and Roles and Groups etc. | 32 | -
5 | Implementation and Technical Management | 31 | 10
Pilot Phase A:
· Sample Storage and Retention
· Equipment Management
· Inspection Plan Configuration
· Chain of Custody
· Barcode Handling
· Stocks
· Instrument Calibration and Maintenance
· Sample Management
· Sample Tracking and Audit
· Laboratory Management
· Security And User Access Management
Pilot Phase B:
· Notification and alert
· Training module configuration
6 | 14 Workflow Management for Pilot Phase | 7 | 23
Pilot Phase A: 4 workflows
Pilot Phase B: 10 workflows
7 | Sampling Scheduler | 6 | 6
Pilot Phase A: Shift management
Pilot Phase B: Scheduler
8 | 10 Lab Execution System (LES) for Pilot Phase | - | 30
9 | 6 Reports for Pilot Phase | 18 | -
10 | 8 Labels for Pilot Phase | 10 | -
11 | 1 Dashboard for Pilot Phase | 3 | -
12 | Static Data Assistance | 10 | 5
Pilot Phase A - 90% static data assistance coverage
Pilot Phase B - 10 % remaining static data
13 | Instrument Integration x15 – develop the parser to transfer the result data. Assist to establish the connection between instrument and SampleManager and end to end testing. | 17 | 31
Pilot Phase A - 3 Type A and 5 Type B
Pilot Phase B - 2 Type A and 10 Type B
14 | Third party application interface | 28 | 39
Pilot Phase A: SAP
Pilot Phase B: 1X Smartfactory (Vegam), 1-Skillmatrix (OSDP)
15 | Documentation: | 10 | 6
Pilot Phase A: RTM, Functional Specification, Configuration Summary, User Manual for SampleManager, and Instrument connection repository
Pilot Phase B: Document updates as per phase B activities
16 | Parsing external file data (only for one format) | - | 5
17 | System Integration Testing | 8 | 12
18 | Installation and deployment on Dev, Test and Prod servers | 2 | 2
19 | UAT and Go Live Support | 10 | -
20 | Project Management | 34 | 28
21 | SampleManager Training as per section 3.1.2.1 | 22 | -
| Total | 278 | 197
| Total Days (Pilot Phase) | 475

## Pivot Table
Sum of Estimate | 列标签
行标签 | Phase A | Phase B | (空白) | 总计
Business Proc Only
(空白)
Configuration | 74 | 30 |  | 104
Assignment | 1 |  |  | 1
IM Integartion | 0 |  |  | 0
Instrument | 4 |  |  | 4
Interface
LES |  | 0 |  | 0
Report&Label | 0 |  |  | 0
Sample | 30 | 4 |  | 34
Security | 2 |  |  | 2
Stock | 13 |  |  | 13
Workflow | 24 | 26 |  | 50
Customisation | 51 | 23 |  | 74
Assignment | 16 | 23 |  | 39
Dashboard | 16 |  |  | 16
Interface
LES | 5 |  |  | 5
Notification | 2 |  |  | 2
Sample | 12 |  |  | 12
Interface | 34 | 44 |  | 78
IM Integartion
Interface | 34 | 44 |  | 78
(空白)
Non-function | 0 |  |  | 0
IM Integartion | 0 |  |  | 0
Out Of Scope | 80 | 0 | 5 | 85
Dashboard | 45 |  | 5 | 50
Instrument | 2 |  |  | 2
Interface | 15 |  |  | 15
Report&Label | 2 |  |  | 2
Sample | 11 | 0 |  | 11
Stock | 5 |  |  | 5
(空白)
Standard | 6 | 0 | 0 | 6
IM Integartion |  | 0 |  | 0
Instrument | 0 |  |  | 0
LES |  | 0 |  | 0
Report&Label | 0 |  |  | 0
Retain | 2 |  |  | 2
Sample | 4 |  | 0 | 4
Security | 0 | 0 |  | 0
Stock | 0 |  |  | 0
(空白)
(空白)
Assignment
(空白)
总计 | 245 | 97 | 5 | 347

## Requirements Trace Matrix
REQUIREMENTS TRACE MATRIX
[6 empty] | Document Ref: | Appendix 01_Functional Requirements_LIMS - Thermo Fisher
[6 empty] | Version: | 1
[6 empty] | Date: | 2024-06-04
gathering status | Module | Req. No. | URS Ref. | Delivery Phase | Module | Fs Area / Workshop | Requirement | Priority | Type | X-Ref | Owner | Include | Desing Idea | Fields Tables | Complexity | P/Type | Addresses Requirement | Design Conclusion | FDS Ref. | Test Script Ref. | Expanded Details/Comments | Estimate | Comments
complete |  |  | 4.1.1.1 |  |  | Sample Login/Sample Receipt | The system shall provide functionality to log samples using configurable templates In case of plants with Smart factory, Smart factory MES samples are collected in those application for standard testing Samples have to be created using QCLaD for non-standard testing, and for sites where there is no MES or Smart factory. | Must
complete | Sample | R001 | 4.1.1.1.1 | Phase A | Sample Login | 3.2.1.2 | System shall be able to login samples using configurable templates | Must | Configuration |  |  |  | 配置Sample entity template，需要添加字段 | [8 empty] | 6 | 约配置14个实体模板；每个实体模板约30个字段；字段的属性、关联性、公式等信息配置
complete |  |  | 4.1.1.1.2 |  |  | Mark | Henkel offer the sample request template for reference.
complete | Sample | R002 | 4.1.1.1.3 | Phase A | Sample Login | 3.2.1.2 | System shall be able to create samples manually for standard testing. | Must | Configuration |  |  |  | 配置standard testing的工作流，如果要加其他特定功能，不好评估时间 | [8 empty] | /
complete | Sample | R003 | 4.1.1.1.4 | Phase A | Sample Login | 3.2.1.2 | System shall be able to create samples manually for non-standard testing. | Must | Configuration |  |  |  | 配置standard testing的工作流，如果要加其他特定功能，不好评估时间 | [8 empty] | /
complete |  |  | 4.1.1.2 |  |  |  | The system shall provide functionality to log samples automatically based on trigger events in an external system or schedule | Must
complete | Interface | R004 | 4.1.1.2.1 | Phase A |  |  | System shall be able to receive inspection lot from SAP and create sample and test. Refer to 4.5.1.1 |  | Customisation |  |  |  | SMIDI或定制开发接口
complete | Interface | R005 | 4.1.1.2.2 | Phase B |  |  | System shall be able to trigger a resample from MES. |  | Out Of Scope |  |  |  | 定制开发接口，当MES触发ReSample操作时，调用QCLaD接口，将相应sample做Resample操作（重新生产一个新的sample） 样品登录是由SAP接口触发，那MES中触发resample,如何与QCLaD中的sample关联？ | [9 empty] | OOO
complete | Sample | R006 | 4.1.1.2.2 | Phase A |  |  | System shall be able to create sample based on events scheduled within QCLAD. |  | Standard | [12 empty] | 2 | 配置Schedule工作流、流程文件夹、实体模板、后台定时任务、类型
complete |  |  | 4.1.1.3 |  |  |  | The system shall assign a unique sample ID to each sample logged in Unique id has to be pulled from sample label if exists and reuse. If it doesn’t exist, system can create one. | Must
complete | Sample | R007 | 4.1.1.3.1 | Phase A | Sample Login | 3.2.1.2 | System shall assign a unique sample ID to each sample logged in. | Must | Configuration |  |  |  | 配置Sample Idtext的Syntax | [8 empty] | 1 | 约配置ID syntax 14个模板
complete | Sample | R008 | 4.1.1.3.2 | Phase A | Sample receiving | 3.2.1.3 | System shall be able to scan the Labels from MES system and fetch unique ID. |  | Customisation |  |  |  | 定制开发，样品在接收的时候，将MES的标签上的ID存在sample表中，与sample中的id对应 | [8 empty] | 2 | 代码开发，解析MES标签；并开发样品接收界面
complete |  |  | 4.1.1.3.3 |  |  | mark | Henkel need to check label template with Dragon. ( offer QR code rule )
complete | Sample | R009 | 4.1.1.3.4 | Phase A | Sample receiving | 3.2.1.3 | System shall allow user to print QCLaD Labels if the Plant doesn’t use MES system. | Must | Standard |  |  |  | 配置Label和菜单 | [8 empty] | /
complete |  |  | 4.1.1.3.5 |  |  | mark | Henkel already offered sample ID naming rules for non-standard Sample .(TF already provided sample ID naming rules examples)
complete |  |  | 4.1.1.4 |  |  |  | The system shall provide functionality to capture the date and time of sample receipt | Must
complete | Sample | R010 | 4.1.1.4.1 | Phase A | Sample receiving | 3.2.1.3 | System shall be able to retrive the sample receive date and time. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.1.5 |  |  |  | The system shall provide functionality to allow privileged users to cancel samples from the system | Must
complete | Sample | R011 | 4.1.1.5.1 | Phase A |  |  | System shall be able to allow privileged users to cancel samples. | Must | Standard |  |  |  | 配置权限 | [8 empty] | /
complete | Sample | R012 | 4.1.1.5.2 | Phase A |  |  | System shall be able to add a mandatory comment for the cancellation. |  | Out Of Scope | [12 empty] | 1 | OOO
complete |  |  | 4.1.1.6 |  |  |  | The system shall provide functionality to define configurable attributes for a sample which can be modified | Must
complete | Sample | R013 | 4.1.1.6.1 | Phase A | Sample Login | 3.2.1.2 | System shall be able to define configurable attributes for a sample which can be modified. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.1.7 |  |  |  | The system shall provide functionality to allow the definition of sample types and sampling plans. This should include functionality to log in predefined batches of samples at one time in accordance with a defined sampling plan | Must
complete | Sample | R014 | 4.1.1.7.1 | Phase A | Sample Login | 3.2.1.2 | System shall be able to allow the definition of sample types and test schedule. | Must | Standard |  |  |  | 自带功能 | [8 empty] | 1 | 配置type类型和test schedule
complete |  |  | 4.1.1.7.2 |  |  | Mark | Henkel need to check function of sample typle and sampling plans with Maline. Re: sampling plan means sampling quantity
complete | Sample | R015 | 4.1.1.7.3 | Phase A | Sample Login | 3.2.1.2 | System shall be able to log in predefined batches of samples at one time in accordance with a defined sampling plan. | Must | Configuration |  |  |  | 在schedule中配置登样计划，需要配置schedule登样工作流 | [8 empty] | /
complete |  |  | 4.1.1.8 |  |  |  | The system shall provide functionality to log in either single or multiple samples from the same batch | Must
complete | Sample | R016 | 4.1.1.8.1 | Phase A | Sample Login | 3.2.1.2 | System shall be able to log in either single or multiple samples from the same batch. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.1.9 |  |  |  | The system shall provide functionality to manage ‘sample split’ | Must
complete | Sample | R017 | 4.1.1.9.1 | Phase A | Sample Login | 3.2.1.2 | The system shall be able to split samples. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Security | R018 | 4.1.1.9.2 | Phase A |  |  | System shall be able to display the traceability of split samples with a parent sample. |  | Standard | [12 empty] | /
complete |  |  | 4.1.1.10 |  |  |  | The system shall provide functionality to log non routine samples with the user selecting a pre-defined specification or manually assigning tests from a pre- defined test list | Must
complete | Sample | R019 | 4.1.1.10.1 | Phase A | Sample Login | 3.2.1.2 | System shall be able to log in non routine samples. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Sample | R020 | 4.1.1.10.2 | Phase A | Sample Login | 3.2.1.2 | System shall allow specific user to select specifications and test methods for non routine samples. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.1.11 |  |  |  | The system shall provide functionality to manage retesting of samples that have an adverse finding | Must
complete | Sample | R021 | 4.1.1.11.1 | Phase A |  |  | system shall be able to retest. | Must | Configuration |  |  |  | 配置retest功能，retest具体如何实现待商榷 | [8 empty] | 2 | 在各自工作流配置复测功能
complete | Sample | R022 | 4.1.1.11.2 | Phase A |  |  | System shall be record all failure as well as success of parameters in QCLAD. | Must | Standard | [12 empty] | /
complete | Interface | R023 | 4.1.1.11.3 | Phase A |  |  | System shall be push all failure as well as success of parameters to SAP. Refer to 4.5.1.7 |  | Customisation |  |  |  | SMIDI或定制开发接口
complete |  |  | 4.1.1.12 |  |  |  | The system shall provide functionality to manage re-samples and their association with the original sample | Must
complete | Sample | R024 | 4.1.1.12.1 | Phase A |  |  | System shall be able to resample and association with the original sample. | Must | Standard |  |  |  | 配置resample功能，字段与原sample 关联。 resample是不是和接口相关？ | [8 empty] | /
complete |  |  | 4.1.1.13 |  |  |  | The system shall provide functionality to associate specification limits to the tests for a sample | Must
complete | Sample | R025 | 4.1.1.13.1 | Phase A |  |  | System shall be able to associate MLP to the tests for a sample. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Interface | R026 | 4.1.1.13.2 | Phase A |  |  | System shall be receive specification limit to be pulled from SAP. Refer to 4.5.1.3 |  | Customisation |  |  |  | mlp同步，SMIDI或定制开发接口
complete |  |  | 4.1.1.14 |  |  |  | The system shall provide functionality to allow restriction of sample types or sample groups to specific user groups, specialist analysts and restriction can be modified during the sample life cycle | Must
complete | Security | R027 | 4.1.1.14.1 | Phase A |  |  | System shall be able to control data access by group. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Sample | R028 | 4.1.1.14.2 | Phase A |  |  | System shall support modify specialist analysts and group restriction during the sample life cycle. | Must | Configuration |  |  |  | 配置修改测试人的按钮；在entity template中加一个group的修改项 | [8 empty] | 1 | 配置组别、设置界面
complete |  |  | 4.1.1.15 |  |  |  | The system shall provide the capability to enter free text information at Sample log-in | Must
complete | Sample | R029 | 4.1.1.15.1 | Phase A | Sample Login | 3.2.1.2 | System shall be able to allow user to enter comments at Sample log-in. | Must | Configuration |  |  |  | 在entity template中配置一个comment的字段 | [8 empty] | /
complete |  |  | 4.1.1.16 |  |  |  | The system must be able to scan barcode information and transmit this information to the solution using an appropriate system | Must
complete | Sample | R030 | 4.1.1.16.1 | Phase A | Sample receiving | 3.2.1.3 | System shall be able to scan barcode or QRCode and match barcode or QRCode sample in QCLAD system. |  | Customisation |  |  |  | 标准样品是MES标签，非标准样品是QCLaD标签 | [8 empty] | 2 | 系统里新增、匹配字段，界面设计
complete |  |  | 4.1.1.17 |  |  |  | The system should be able to automatically login samples from a schedule or other systems (SAP, Henkel Smart Factory, MES) | Must
complete | Sample | R031 | 4.1.1.17.1 | Phase A |  |  | System shall be automatically login samples from a schedule. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Interface | R032 | 4.1.1.17.2 | Phase A |  |  | System shall be automatically login samples from SAP. Refer to 4.5.1.1 |  | Customisation |  |  |  | SMIDI或定制开发接口 一个检验批是否只对应一个sample？ 是否存在混检？
complete | Interface | R033 | 4.1.1.17.3 | Phase B |  |  | System shall be automatically login samples from MES. |  | Customisation |  |  |  | 定制开发接口，当MES需要登录样品的时候，调用QCLAD的接口，登录相应sample
complete |  |  | 4.1.1.18 |  |  |  | The system shall provide functionality to allow entry / modification of attribute data at point of single or multiple sample receipt using configurable templates. For sites where there is labeling through MES, SFS or labelling solution, sample receipt has to be done by scanning the labels. For non MES/SFS sites, labels created from QCLAD to be used for scanning the sample receipt | Must
complete | Sample | R034 | 4.1.1.18.1 | Phase A | Sample receiving | 3.2.1.3 | Sytem shall be able to allow entry / modification of attribute data at point of single or multiple sample receipt using configurable templates. | Must | Configuration |  |  |  | 扫码收样时修改属性 | [8 empty] | /
complete | Sample | R035 | 4.1.1.18.2 | Phase A | Sample receiving | 3.2.1.3 | System shall be able to receive sample by scanning MES label |  | Customisation |  |  |  | 定制开发，样品在接收的时候，将MES的标签上的ID存在sample表中，与sample中的id对应 | [8 empty] | /
complete | Report&Label | R036 | 4.1.1.18.3 | Phase A | Sample receiving | 3.2.1.3 | System shall be able to create labels for sample scan receiving for non MES samples. | Must | Configuration |  |  |  | 配置标签 | [8 empty] | /
complete |  |  | 4.1.1.19 |  |  |  | The system shall provide functionality to allow entry of any irregularities recorded and route sample according to laboratory business rules | Must
pending | Sample | R037 | 4.1.1.19.1 | Phase A | Result entry | Mark | The system shall provide functionality to allow entry of any irregularities recorded sample according to laboratory business rules. |  | Standard | [12 empty] | /
pending | Sample | R038 | 4.1.1.19.2 | Phase A | Result entry |  | The system shall provide functionality to allow entry of any routine sample according to laboratory business rules. |  | Configuration
complete |  |  | 4.1.1.20 |  |  |  | The system shall provide functionality to allow users to change sample attributes after sample receipt | Must
complete | Sample |  | 4.1.1.20.1 | Phase A |  |  | System shall allow users to modify sample attributes after sample receipt. | Must | Configuration |  |  |  | 用entity template配置可以修改的字段 | [8 empty] | 1 | 在各自工作流配置功能
complete |  |  | 4.1.2.1 |  |  | Sample Testing/Results Entry | The system shall provide two ways to assign works/tests to users: i) Manually, Lab supervisor can allocate the work periodically based on requirements. ii) Automatically, QCLaD arrange work based on pre-defined rules. The rule is Henkel customize, it can be configurable by Henkel site QC supervisor. The rule is based on Henkel resource (QC technician skill, workload, work shift and instrument availability, etc.); iii) function to support QC supervisor stop or modify auto assign task. iv) capability to receive QC technician skills from Henkel Skill Matrix application for automatic task assignment in case the plant has configured Skill matrix application | Must
complete | Assignment |  | 4.1.2.1.1 | Phase A | Test Assign |  | System shall be able to assign tests to an operator manually or automatically. |  | Customisation |  |  |  | 定制开发，手动分配参考PT功能
complete | Assignment |  | 4.1.2.1.2 | Phase B |  |  | Automatically assigning details refer to 4.2.1.1 part. |  | Customisation | [12 empty] | 3
complete | Assignment |  | 4.1.2.1.3 | Phase A | Test Assign |  | System shall support to stop or modify auto assign task. |  | Customisation |  |  |  | 定制开发，修改任务的分配，手动分配，Stop是停止全局的自动分配？ | [8 empty] | 1
complete | Assignment |  | 4.1.2.1.4 | Phase B |  |  | System shall be able to assign test based on the versatility matrix from OSDP system once integrated. |  | Customisation |  |  |  | 定制开发接口，与培训信息表同步，单项集成，OSDP->QCLAD | [8 empty] | 1
complete |  |  | 4.1.2.3 |  |  |  | The system shall provide functionality to reference all results data to the sample | Must
complete | Sample |  | 4.1.2.3.1 | Phase A | Result entry |  | System shall be able to display all results data to the sample. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Interface |  | 4.1.2.3.2 | Phase A |  |  | System shall be able to retrive the result data in CoA data already available in SAP inspection lot. |  | Customisation |  |  |  | 定制开发，QCLAD抓取SAP的coa报告中的结果，存储在result表中 Sample、Test是QCLAD中已经存在的吗？
complete | Interface |  | 4.1.2.3.3 | Phase A |  |  | System shall be able to display the Data recorded within inspection lot, MIC, Spec, Test result from the CoA in SAP even if the data entry is not required in QCLAD. |  | Customisation
complete |  |  | 4.1.2.4 |  |  |  | The system shall provide functionality to calculate results based on reported or recorded data entered against a sample and data obtained from values held externally to the QCLAD. E.g., 1st step, QCLaD capture data from lab instruments (one or multiple instruments), 2nd step, the QCLaD calculate final result based on formular defined by Henkel site admin/user | Must
complete | Sample |  | 4.1.2.4.1 | Phase A | Result entry |  | System shall be able to calculate results based on reported or recorded data which from instruments. | Must | Configuration |  |  |  | 静态数据配置和仪器接口；计算结果是在仪器里做好的传过来的还是要在lims里计算 | [8 empty] | 2 | 计算公式配置
complete |  |  | 4.1.2.5 |  |  |  | The system shall provide functionality to automatically check intermediate values (e.g., raw, recorded and reported data) and final results against specification limits and flag failures Intermediate values: all data in whole testing process, e.g., raw data captured from instrument, recorded-data, data calculated by formular, reported data, data which push to SAP | Must
complete | Sample |  | 4.1.2.5.1 | Phase A | Result entry |  | System shall be able to record all data in whole testing process, including raw data captured from instrument, entry data, data calculated by formular, reported data, data which push to SAP. |  | Standard |  |  |  | 涉及需要定制开发的功能，如推送SAP的数据登录，定制开发是会有日志记录，但其他的数据记录应该是系统标准功能 | [8 empty] | /
complete | Sample |  | 4.1.2.5.2 | Phase A | Result entry |  | System shall be able to mark final results against specification limits and flag failures. | Must | Configuration |  |  |  | MLP中配置超限规则 | [8 empty] | 1 | 配置Flag
complete |  |  | 4.1.2.6 |  |  |  | The system shall provide functionality to manage repeat testing | Must
complete | Interface |  | 4.1.2.6.1 | Phase A |  |  | System shall be able to support to manage repeat testing.(e.g. entry multiple results and then get max or min or average value) |  | Customisation |  |  |  | 是需要在什么时候获取这些最大值最小值平均值？--结果中需要计算 求平均值时有需要去掉最大值最小值后求平均值；定制化公式
complete |  |  | 4.1.2.7 |  |  |  | The system shall provide functionality to enable results entry for multiple tests performed on a single sample | Must
complete | Sample |  | 4.1.2.7.1 | Phase A | Result entry |  | System shall be able to support results entry for multiple tests performed on a single sample. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.8 |  |  |  | The system shall provide functionality to enable results entry for an individual test on a single sample | Must
complete | Sample |  | 4.1.2.8.1 | Phase A | Result entry |  | System shall be able to support results entry for an individual test on a single sample. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.9 |  |  |  | The system shall provide functionality to enable results entry for single or multiple tests performed on multiple samples E.g., GC testing, auto-sampler for multiple samples (sequence must be followed), system support to entry single or multiple test result | Must
complete | Sample |  | 4.1.29.1 | Phase A | Result entry |  | System shall be able to support results entry for single or multiple tests performed on multiple samples. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.10 |  |  |  | The system shall provide functionality to verify entered results data (e.g., pH, sample color, specific gravity) against pre-set method limits E.g., PH pre-set method limits is 0-14, result cannot be 15 | Must
complete | Sample |  | 4.1.2.10.1 | Phase A | Result entry |  | System shall be able to verify entered results data (e.g., pH, sample color, specific gravity) against specification limits. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.11 |  |  |  | The system shall prevent the acceptance of partial or incomplete data entry for results and samples E.g., one test has two parallel samples, system doesn’t allow to report data for only for one sample. | Must
complete | Sample |  | 4.1.2.11.1 | Phase A | Result entry |  | System shall be able to prevent the acceptance of partial or incomplete data entry for results and active samples. | Must | Configuration |  |  |  | 样品文件夹配置，没有完成的sample不出现 | [8 empty] | 1 | 配置流程
complete |  |  | 4.1.2.12 |  |  |  | The system shall provide configurable screens aligned to analytical method steps with potential to lead the user through the operation in a step-by-step manner. This would facilitate data capture in real time Can record time taken as well and have video instruction about how to do test. | Must
complete | LES |  | 4.1.2.12.1 | Phase B |  |  | System shall be able to provide configurable analytical method steps with potential to lead the user through the operation in a step-by-step manner.(LES module) | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | IM Integartion |  | 4.1.2.12.2 | Phase B |  |  | System shall be able to capture instrument data(for Type A) and report from instrument (for Type B) in real time. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | LES |  | 4.1.2.12.3 | Phase B |  |  | System shall be able to upload attachements(including video) in LES. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | LES |  | 4.1.2.12.4 | Phase B |  |  | System shall be able to record start date and end date in LES. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
|  |  | 4.1.2.12.5 |  |  | Mark | Video Size depends on Henkel service provided performance.
complete |  |  | 4.1.2.13 |  |  |  | The system shall be able to accept numeric, qualified numeric, free text, characters, calculated values, file, Boolean and pre-defined list data entry | Must
complete | Sample |  | 4.1.2.13.1 | Phase A | Result entry |  | System shall be able to support multipe analysis type, including numeric, text, characters, calculated, file, Boolean and optional. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.14 |  |  |  | The system shall have the capability to receive data via manual input (for type C and D instrument and when type A and B malfunction), electronic transfer and instrument interface and indicate mode of entry Instrument interface: get data from instrument directly. | Must
complete | Sample |  | 4.1.2.14.1 | Phase A | Result entry |  | System shall be able to entry result data manually. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
| IM Integartion |  | 4.1.2.14.2 | Phase A |  |  | System shall be able to entry result data via instrument automatically. |  | Configuration |  |  |  | Sweeper? | [8 empty] | /
complete |  |  | 4.1.2.15 |  |  |  | The system shall provide a way to manually upload files (Excel, CSV, Xps, xml, Jpg or Pdf format) for documentation | Must
complete | Sample |  | 4.1.2.15.1 | Phase A | Result entry |  | System shall support attachment format: Xps, txt, resx, repx, xml, rtf, jpg, jpeg, img, svg, doc, pdf, ico, png, lbl, resources, caf, csv, log, msg, smpkg. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.16 |  |  |  | The system shall be able to interface with the Henkel type A and B instruments. | Must
complete | IM Integartion |  | 4.1.2.16.1 | Phase A |  |  | System shall be able to interface with the Henkel type A and B instruments. |  | Configuration |  |  |  | Sweeper? | [8 empty] | /
complete |  |  | 4.1.2.17 |  |  |  | The system shall be able to automatically capture results from the Henkel type A and B instruments | Must
complete | IM Integartion |  | 4.1.2.17.1 | Phase A |  |  | System shall be able to automatically capture results from the Henkel type A and B instruments. |  | Configuration |  |  |  | Sweeper? | [8 empty] | /
complete |  |  | 4.1.2.18 |  |  |  | The system should have capability to map the equipment based on test. The equipment should be selected by system based on the test and equipment master data In case of any change, the user can modify based on access | Must
complete | LES |  | 4.1.2.18.1 | Phase B |  |  | System shall be able to selecte equipments based on test method in LES. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | LES |  | 4.1.2.18.2 | Phase B |  |  | System shall be able to allow authorized user to modify instruments in LES. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.19 |  |  |  | The system shall be able to protect the calculation template(s) for the final test results so that they cannot be changed by all users The calculation template(s) to be controlled by user role/rights access | Must
complete | LES |  | 4.1.2.19.1 | Phase B |  |  | System shall only allow authorized users to modify calculation template in LES. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Security |  | 4.1.2.19.2 | Phase B |  |  | System shall support audit traceability in LES. |  | Standard | [12 empty] | /
complete |  |  | 4.1.2.20 |  |  |  | The system shall record the source of any entered data (e.g., instrument ID) and / or the user ID of any user entering data | Must
complete | LES |  | 4.1.2.20.1 | Phase B |  |  | The system shall record the source of any entered data (e.g., instrument ID) and / or the user ID of any user entering data. | Must | Configuration |  |  |  | 在LES中配置仪器选择，和结果抓取配置 | [8 empty] | /
complete |  |  | 4.1.2.21 |  |  |  | The system shall provide the functionality to record multiple users against a test or result (e.g., if a test is performed by two analysts) E.g., OHV test, GAP value and Acid value needed for OHV test, QCLaD allows different person conduct GAP and Acid value at same time and record data in QCLaD. | Must
complete | Sample |  | 4.1.2.21.1 | Phase A | Result entry |  | System shall be able to record multiple users against a test or result. | Must | Standard |  |  |  | 自带功能 | [8 empty] | 1 | 配置文件夹、权限、按钮
complete |  |  | 4.1.2.22 |  |  |  | The system shall manage retesting without loss of original data | Must
complete | Sample |  | 4.1.2.22.1 | Phase A | Retest |  | System shall be able to retest without loss of original data. | Must | Configuration |  |  |  | 在workflow里配置retest，同上 | [8 empty] | /
complete |  |  | 4.1.2.23 |  |  |  | The system shall enforce entry of a justification if there is a retest / repeat | Must
complete | Sample |  | 4.1.2.23.1 | Phase A | Retest |  | System shall be able to enforce entry of a justification if there is a retest/resample. | Must | Configuration |  |  |  | 在workflow里配置comment | [8 empty] | 1 | 在各自工作流配置retest功能，和相关重测流程
complete | Sample |  | 4.1.2.23.2 | Phase A |  |  | system shall be able to record comment as mandatory and it is configurable. | Must | Out Of Scope |  |  |  | 工作流配置弹窗，添加comments字段。 和retest设计相关，多次重测可能会覆盖comments | [8 empty] | 1 | OOO
complete |  |  | 4.1.2.24 |  |  |  | The system shall provide functionality to perform simple trend analysis at Results Entry to identify any atypical results and alert the user accordingly | Wont | Out Of Scope
complete |  |  | 4.1.2.24.1 |  |  | Mark | SQC is not in scope. Henkel need to check with Anson. | Wont | Out Of Scope
complete |  |  | 4.1.2.25 |  |  |  | The system shall be configurable, at the test level, to enforce peer review by a different user to the user that entered the test results | Must
complete | Sample |  | 4.1.2.25.1 | Phase A | Peer review |  | System shall be able to enforce peer review by a different user at the material group level. | Must | Configuration |  |  |  | 在workflow里配置按钮，文件夹筛选 | [8 empty] | 1 | 配置权限、文件夹、菜单按钮；审核功能配置
complete | Sample |  | 4.1.2.25.2 | Phase A | Peer review |  | System shall be able to support peer review by configurable option. | Must | Configuration | [12 empty] | /
complete |  |  | 4.1.2.26 |  |  |  | The system shall allow the peer review of results by Single sample, Multi test and Multi sample, single test where required | Must
complete | Sample |  | 4.1.2.26.1 | Phase A | Peer review |  | System shall allow the peer review of results by Single sample, Multi test and Multi sample, single test where required. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.2.27 |  |  |  | The system must lock test data after peer review to prevent further modification except with appropriate permissions and audit trail | Must
complete | Sample |  | 4.1.2.27.1 | Phase A | Peer review |  | System shall prevent user from further modification on test data after peer review except authorized user and audit trail will be record. | Must | Configuration |  |  |  | 自带功能 | [8 empty] | 1 | 配置权限、文件夹、菜单按钮；审核功能配置
complete |  |  | 4.1.2.28 |  |  |  | The system shall provide planning tools to display and assess laboratory workload, including analyst, sample, instrument assignment and sample testing schedule. | Must
pending |  |  | 4.1.2.28.1 |  |  | Mark | Henkel need to offer dashboard template.
pending | Dashboard |  | 4.1.2.28.2 |  |  |  | System shall provide dashboard. |  | Out Of Scope | [12 empty] | 2
complete |  |  | 4.1.3.1 |  |  | Authorization | The system shall provide configurable functionality to approve individual results | Must
complete | Sample |  | 4.1.3.1.1 | Phase A | Peer review |  | System shall be able to approve individual results. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Sample |  | 4.1.3.1.2 | Phase A | Peer review |  | System shall be able to support configure approve option within workflow. | Must | Configuration |  |  |  | 自带功能 | [8 empty] | 1 | 在相应workflow中配置功能，文件夹配置
complete |  |  | 4.1.3.2 |  |  |  | The system shall allow for the approval of single or multiple samples | Must
complete | Sample |  | 4.1.3.2.1 | Phase A | Peer review |  | System shall be able to approve single or multiple samples. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.3.3 |  |  |  | The system shall prevent users that have peer reviewed results from changing any data on the sample when authorize | Must
complete | Sample |  | 4.1.3.3.1 | Phase A | Peer review |  | System shall prevent user from further modification on test data after peer review. | Must | Configuration |  |  |  | 配置权限，文件夹控制 | [8 empty] | /
complete | Sample |  | 4.1.3.3.2 | Phase A | Peer review |  | System shall be able to return test to tester if result need modification . | Must | Configuration |  |  |  | 配置workflow，加按钮，配文件夹 | [8 empty] | /
complete | Sample |  | 4.1.3.3.3 | Phase A |  |  | System shall be able to support return test to another operator. |  | Out Of Scope |  |  |  | 新增退回人员字段，或者是更改分配人员字段 分配人员是否涉及统计任务量？ | [8 empty] | 3 | OOO
complete |  |  | 4.1.3.4 |  |  |  | The system shall provide configurable system approval functionality to automatically assign an authorization at test level and sample level. | Must
complete | Sample |  | 4.1.3.4.1 | Phase A | Peer review |  | System shall be able to configure system approval functionality at test level and sample level. | Must | Configuration |  |  |  | 配置inspection plan，添加按钮在 test level and sample level. | [8 empty] | 1 | 在样品层面和测试层面分别配置权限、文件夹、菜单按钮；审核功能配置
complete |  |  | 4.1.3.5 |  |  |  | The system shall provide functionality for manual approval at test level, sample level | Must
complete | Sample |  | 4.1.3.5.1 | Phase A | Peer review |  | System shall be able to approval manually at test level and sample level. | Must | Configuration |  |  |  | 配置inspection plan，添加按钮在 test level and sample level. | [8 empty] | /
complete |  |  | 4.1.3.6 |  |  |  | The system shall prevent the sample authorization with incomplete testing and alert defined users to the situation Prevent the sample authorization means if the sample in one incomplete phase (e.g., Testing), it cannot go to next phase. Sample can only in one phase in QCLaD. | Must
complete | Sample |  | 4.1.3.6.1 | Phase B | Peer review |  | System shall prevent the sample authorization with incomplete testing and alert defined users to the situation in folder. | Must | Configuration |  |  |  | 配置workflow，添加提醒 | [8 empty] | 1 | 配置文件夹、权限、按钮
complete | Sample |  | 4.1.3.6.2 | Phase A |  |  | System shall only have one status of a sample in one time. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.3.7 |  |  |  | The system shall allow authorized users to change the status of a sample to allow controlled modifications or entry of data E.g., QCLaD allows user to modify inspection plan of non-standard testing, inspection plan of standard test should come from SAP. | Must
complete | Sample |  | 4.1.3.7.1 | Phase A |  |  | System shall allow authorized users to change the status of a sample to allow controlled modifications or entry data. | Must | Configuration |  |  |  | 权限配置 | [8 empty] | 1
complete |  |  | 4.1.3.8 |  |  |  | The system shall allow certain authorized users to change the proposed user for testing | Must
complete | Sample |  | 4.1.3.8.1 | Phase A |  |  | System shall allow certain authorized users to change the proposed user for testing. | Must | Configuration |  |  |  | 权限配置，添加修改tester的按钮 | [8 empty] | 1
complete |  |  | 4.1.3.9 |  |  |  | The system shall provide a way to check and indicate the results/samples waiting for approval. | Must
complete | Sample |  | 4.1.3.9.1 | Phase A | Peer review |  | System shall provide a way to check and indicate the results/samples waiting for approval. | Must | Configuration |  |  |  | 配置查看界面 | [8 empty] | 1
complete |  |  | 4.1.4.1 |  |  | Reporting | The system shall provide a reporting tool to have users to define report templates by themselves | Must
complete | Report&Label |  | 4.1.4.1.1 | Phase A |  |  | System shall allow users to define report templates by themselves using reporting tool. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.4.10 |  |  |  | The system shall support to generate single sample report, multiple sample report, COA report etc. | Must
complete | Report&Label |  | 4.1.4.10.1 | Phase A |  |  | System shall support to generate single sample report, multiple sample report, COA report. | Must | Configuration |  |  |  | 配置报告模板 | [8 empty] | /
complete |  |  | 4.1.4.10.2 |  |  | Mark | Henkel need to offer all report template.
complete |  |  | 4.1.4.11 |  |  |  | The system shall provide functionality to route the output of reports to screen, printer, file (CSV, XML) or email | Must
| Report&Label |  | 4.1.4.11.1 | Phase A |  |  | System shall be able to route the output of reports to screen, printer, file (CSV, XML, PDF) or email. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.4.12 |  |  |  | The system shall provide functionality to generate reports in various formats (e.g., tabular, matrix, graphical or text) | Must
complete | Report&Label |  | 4.1.4.12.1 | Phase A |  |  | System shall be able to support various formats (e.g., tabular, matrix, graphical or text) in report templates. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.4.13 |  |  |  | The systems performance must not be adversely affected by running reports | Must
complete | Report&Label |  | 4.1.4.13.1 | Phase A |  |  | Systems performance must not be adversely affected by running reports. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Report&Label |  | 4.1.4.13.2 | Phase A |  |  | System shall be able to give warning of response if user selects a range which will take time. |  | Out Of Scope | [12 empty] | 2 | OOO
complete |  |  | 4.1.4.14 |  |  |  | The system shall be capable of sending notifications and alert messages via electronic mail | Must
complete | Sample |  | 4.1.4.14.1 | Phase B |  |  | System shall be able to send notifications and alert messages within folders. | Must | Configuration |  |  |  | 配置文件夹，或工作流触发internal message或邮件 | [8 empty] | 3 | 所有需要的文件夹配置
complete |  |  | 4.1.4.15 |  |  |  | The system shall be capable to generate Henkel customer requested CoA (certificate of analysis) report with customer’s template based on data in QCLaD system. The system should have capability to allow site admin to create customer CoA template based on different customer requirements. The system should have capability to send email with attachment to dedicate E-mail address based on master data configuration | Must
complete | Report&Label |  | 4.1.4.15.1 | Phase A |  |  | System shall allow users to define report templates based on customer or product . | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Report&Label |  | 4.1.4.15.2 | Phase A |  |  | System shall allow user to create and modify report templates. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Report&Label |  | 4.1.4.15.3 | Phase A |  |  | System shall allow user to update version for reprot templates. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Notification |  | 4.1.4.15.4 | Phase A |  |  | System shall be able to send email with attachment to dedicate E-mail address based on master data configuration or store the file in a configurable shared drive automatically. |  | Customisation |  |  |  | 定制开发，报告审批后的pdf文件存储到共享路径，将报告pdf文件加入邮件中发送； 什么时候触发发送？ | [8 empty] | 2
complete |  |  | 4.1.4.2 |  |  |  | The text style or format in the text report shall be edible by the users. | Must
complete | Report&Label |  | 4.1.4.2.1 | Phase A |  |  | System shall be able to provide editable text style or format in the text report. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.4.3 |  |  |  | The system must be able to report on the analyzed data at all levels (e.g., raw, recorded and reported analytical data) | Must
complete | Report&Label |  | 4.1.4.3.1 | Phase A |  |  | System must be able to report on the analyzed data at all levels (e.g., raw, recorded and reported analytical data). | Must | Configuration |  |  |  | 配置report；不知道报告长啥样，不好评估 | [8 empty] | /
complete |  |  | 4.1.4.4 |  |  |  | The system shall collate results from multiple tests for each sample | Must
complete | Report&Label |  | 4.1.4.4.1 | Phase A |  |  | System shall collate results from multiple tests for each sample. | Must | Configuration |  |  |  | 配置report；不知道报告长啥样，不好评估 | [8 empty] | /
complete |  |  | 4.1.4.5 |  |  |  | The system shall be able to support to insert electrical signature, company logo, picture, trending chart, table etc. in the reports. | Must
complete | Report&Label |  | 4.1.4.5.1 | Phase A |  |  | System shall be able to support to insert signature picture, company logo, picture, trending chart, table in the reports. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.1.4.5.2 |  |  |  | System shall be able to support end app insert handwritting signature by pad. | Wont | Out Of Scope
complete |  |  | 4.1.4.6 |  |  |  | The system shall provide functionality to manually or automatically trigger a report in response to, e.g., workflow events, schedules | Must
complete | Sample |  | 4.1.4.6.1 | Phase A |  |  | System shall provide functionality to manually or automatically trigger a report in response to workflow events. |  | Configuration |  |  |  | 自动开报告，需求不复杂的话可以配置工作流 | [8 empty] | 1 | 配置工作流功能
complete |  |  | 4.1.4.7 |  |  |  | The system shall provide a library of pre-defined controlled reports | Must
complete | Report&Label |  | 4.1.4.7.1 | Phase A |  |  | System shall be able to provide a library of report templates. | Must | Configuration |  |  |  | 配置文件夹 | [8 empty] | /
complete |  |  | 4.1.4.8 |  |  |  | The system shall provide ability to generate analytical reports based on the data recorded in QCLAD like date time, QC operators details along with inspection | Must
complete | Report&Label |  | 4.1.4.8.1 | Phase A |  |  | System shall be able to generate analytical reports based on the data recorded in QCLAD like date time, QC operators details along with inspection. | Must | Configuration |  |  |  | 配置报告模板 | [8 empty] | /
complete |  |  | 4.1.4.9 |  |  |  | The system shall provide a way to generate and save “Test Report” template for generation and printing test report of other samples | Must
complete | Report&Label |  | 4.1.4.9.1 | Phase A |  |  | System shall be able to generate and save “Test Report” template. | Must | Configuration |  |  |  | 配置报告模板 | [8 empty] | /
complete | Report&Label |  | 4.1.4.9.2 | Phase A |  |  | System shall be able to print test report of other samples based on templates. | Must | Standard | [12 empty] | /
complete |  |  | 4.1.5.1 |  |  | Henkel Sample Type | The system should be capable to manage all sample types in Henkel, including, Standard test sample to support production: raw material sample (ROH), semi-finish goods sample/ bulk sample (UNB & UNF), finish goods sample (FER). Non-standard test sample: consumable, package material, instrument calibration sample, MSA test sample, CCMS/SCMS/NCMR investigation sample (QM notification Q1/Q2/Q3), special test sample (Testing for Customer/Supplier/PD/AE/Other sites/MOC/NPI / Improvement project), retain sample, etc. | Must
complete | Workflow |  | 4.1.5.1.1 | Phase A |  |  | System shall be able to manage Standard RM test for Incoming workflow. |  | Configuration |  |  |  | 配置workflow，需要先确认能否合并不同样品类型的Lifecycle wkflw | [8 empty] | 7
complete | Workflow |  | 4.1.5.1.2 | Phase A |  |  | System shall be able to manage Standard in process testing for semi finished and finished goods workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 10
complete | Workflow |  | 4.1.5.1.3 | Phase A |  |  | System shall be able to manage Standard finished goods outgoing test workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 4
complete | Workflow |  | 4.1.5.1.4 | Phase A |  |  | System shall be able to manage Consumables incoming test workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 3
complete | Workflow |  | 4.1.5.1.5 | Phase B |  |  | System shall be able to manage package material incoming test workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 4
complete | Workflow |  | 4.1.5.1.6 | Phase B |  |  | System shall be able to manage instrument calibration sample test workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 4
complete | Workflow |  | 4.1.5.1.7 | Phase B |  |  | System shall be able to manage test for MSA workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | /
complete | Workflow |  | 4.1.5.1.8 | Phase B |  |  | System shall be able to manage Certification test for QC technician workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 3
complete | Workflow |  | 4.1.5.1.9 | Phase B |  |  | System shall be able to manage Test for SCMS/NCMR /CCMS investigation workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 4
complete | Workflow |  | 4.1.5.1.10 | Phase B |  |  | System shall be able to manage Test for NCMR-Shelf life extension (RM, SFG, FG, Package material, consumble & Instrument calibration sample) workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 4
complete | Workflow |  | 4.1.5.1.11 | Phase B |  |  | System shall be able to manage Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project (Including, Stability studies (shelf-life study, aging test, reliability test, etc.)) workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 4
complete | Workflow |  | 4.1.5.1.12 | Phase B |  |  | System shall be able to manage Moving sample/material to storage location workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 2
complete | Workflow |  | 4.1.5.1.13 | Phase B |  |  | System shall be able to manage Perform skip lot testing workflow. |  | Configuration |  |  |  | 配置workflow | [8 empty] | 1
complete |  |  | 4.1.6.1 |  |  | Non-testing work requirements | The system should be capable to maintain/arrange storage location of QC retain sample, consumables (reagent, etc.), spare parts. The system should be capable to maintain safety stock of consumables and spare parts, etc. The system should have field to maintain storage condition for retain samples, consumables and spare parts. Send auto notification once the sample near expiration date based on configurable rule. Send auto notification once it’s below safety stock of consumables and spare parts based on configurable rule. | Must
complete | Sample |  | 4.1.6.1.1 | Phase A |  |  | System shall be able to maintain location. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Stock |  | 4.1.6.1.2 | Phase A |  |  | System shall be able to support QC retain sample, consumables and spare parts can select location. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Stock |  | 4.1.6.1.3 | Phase A |  |  | System shall be able to maintain safety stock of consumables and spare parts. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Stock |  | 4.1.6.1.4 | Phase A |  |  | System shall be able to maintain storage condition for retain samples, consumables and spare parts. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Dashboard |  | 4.1.6.1.5 | Phase A |  |  | System shall support dashboard to display and mark in color once the sample near expiration date based on configurable rule. |  | Out Of Scope |  |  |  | Standard；客户想要更多展示效果的dashboard，非系统自带 | [8 empty] | 1 | Using folder is ok
complete | Dashboard |  | 4.1.6.1.6 | Phase A |  |  | System shall support dashboard to display and mark in color once it’s below safety stock of consumables and spare parts based on configurable rule. |  | Out Of Scope |  |  |  | Standard；客户想要更多展示效果的dashboard，非系统自带 | [8 empty] | 2 | Using folder is ok
complete |  |  | 4.1.6.1.7 |  |  | Mark | Henkel need to offer these dashboard templates.
complete |  |  | 4.1.7.1 |  |  | Special testing requirement management | The system should have capability to manage special test request (Testing for Customer/Supplier/PD/AE/Other sites/MOC/NPI / Improvement project, etc.) The system shall be capable of allow QCLaD user and non-QCLaD users to raise test request. Non-QCLaD user should have required user credentials. The system shall have capability to allow user to select which plant to conduct the test, which test needed, when is the expected complete date, etc. System should have capability to allow QC supervisor to approve the test requirement. System should have capability to enter results, report results, generate test report and send test report to requestor’s E-mail address. System should have capability to track the test status, analysis test workload and show it on Dashboard. | Must
complete | Sample |  | 4.1.7.1.1 | Phase A |  |  | System shall be able to manage external test request using non-standard testing workflow.(4.1.5.1.4-4.1.5.13) |  | Customisation |  |  |  | 给外部用户使用登录非标准测试，web端？后期决定方案 | [8 empty] | 5
complete | Sample |  | 4.1.7.1.2 | Phase A |  |  | System shall be able to allow QCLaD users to raise test request. |  | Configuration |  |  |  | 配置workflow，手动登样 | [8 empty] | /
pending |  |  | 4.1.7.1.3 |  |  | Mark | System shall be able to allow non-QCLaD users to raise test request(Both side need further discussion with Neelima)
complete | Sample |  | 4.1.7.1.4 | Phase A |  |  | System shall be able to use template to allow user to select plant, analysis,expected complete date and comments. |  | Configuration |  |  |  | 为每个类型配置sample entity template | [8 empty] | /
complete |  |  | 4.1.7.1.5 |  |  | Mark | Henkel need to offer testing request templates.
complete | Sample |  | 4.1.7.1.6 | Phase A |  |  | System shall be able to allow QC supervisor to approve the test requirement. | Must | Configuration |  |  |  | 是否测试工单确认？配置workflow字段，文件夹筛选。 | [8 empty] | /
complete | Sample |  | 4.1.7.1.7 | Phase A |  |  | System shall be able to enter results, report results, generate test report and send test report to requestor’s E-mail address. |  | Customisation |  |  |  | 定制开发，在相应节点发送邮件给请求者，邮件内容含有附件吗？ | [8 empty] | 3
complete | Dashboard |  | 4.1.7.1.8 | Phase A |  |  | System shall be able to track the test status, analysis test workload and show it on Dashboard. |  | Out Of Scope |  |  |  | 定制开发Dashboard界面， | [8 empty] | 3 | Using folder is ok
complete |  |  | 4.1.7.1.9 |  |  | Mark | Henkel want to check the details of the test status. System shall support this. | [5 empty] | how detailed
complete |  |  | 4.1.7.1.10 |  |  | Mark | Henkel need to offer Dashboard template about test status, analysis test workload.
complete |  |  | 4.2.1.1 |  |  | Schedular | Sample test schedule arrangement way: 1. QC supervisor manual assign task to a user; 2. QCLaD automatic assign task to a user based configured rule (pending test items of standard and non-standard sample, user testing skill, user and test instrument availability, sample status, SAP test skip lot rules, other pending QC works, e.g., calibration, MSA works, etc.). | Must
complete | Sample |  | 4.2.1.1.1 | Phase A | Test Preparation |  | System shall be able to have option for a sample preparation which may be required for some analysis. | Must | Standard | [12 empty] | /
complete | Sample |  | 4.2.1.1.2 | Phase A | Test Preparation |  | System shall be able to assign preparation to an operator. | Must | Customisation |  |  |  | 配置功能
complete | Sample |  | 4.2.1.1.3 | Phase A |  |  | System shall be able to have multiple preparaiton for a analysis. |  | Out Of Scope |  |  |  | 定制开发，新增Test准备记录表，包含仪器字段 | [8 empty] | 2 | OOO
complete | Sample |  | 4.2.1.1.4 | Phase A |  |  | System shall be able to assign multiple instruments for preparation. |  | Out Of Scope |  |  |  | 定制开发，新增Test准备记录表，包含仪器字段 | [8 empty] | 2 | OOO
complete | Sample |  | 4.2.1.1.5 | Phase A |  |  | System shall be able to assign test to an operator for each test. | Must | Customisation |  |  |  | 自带功能
complete | Assignment |  | 4.2.1.1.6 | Phase A | Test Assign |  | System shall be able to have standard time defined for each test assignment. This shall come from the master data to LIMS. | Must | Configuration |  |  |  | 配置字段 | [8 empty] | 1
complete | Sample |  | 4.2.1.1.7 | Phase A |  |  | System shall allow to assign instrument from the list available for the lab for each test by the operator. | Must | Configuration |  |  |  | 自带功能 | [8 empty] | 2
complete | Instrument |  | 4.2.1.1.8 | Phase A |  |  | System shall be able to display all the instruments (typeA, typeB, type C, typeD) based on the location and method. | Must | Configuration |  |  |  | 配置文件夹 | [8 empty] | 1
complete | Sample |  | 4.2.1.1.9 | Phase A |  |  | System shall be able to select instrument by scanning. |  | Standard |  |  |  | 配置标签模板 | [8 empty] | /
complete | LES |  | 4.2.1.1.10 | Phase B |  |  | System shall be able to select multipe instruments in LES. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | LES |  | 4.2.1.1.11 | Phase B |  |  | System shall be able to have option to manually override for the parameters captured. | Must | Standard | [12 empty] | /
complete | Assignment |  | 4.2.1.1.12 | Phase B |  |  | System shall be able to assign test based on the versatility matrix from OSDP system once integrated. |  | Customisation |  |  |  | 自动分配任务详细规则？ | [8 empty] | 2
complete | Assignment |  | 4.2.1.1.13 | Phase B |  |  | System shall be able to assign test based on the sample status (Waiting to start). |  | Customisation |  |  |  | 自动分配任务详细规则？ | [8 empty] | 2
complete | Assignment |  | 4.2.1.1.14 | Phase B |  |  | System shall be able to auto assign for the current date based on the schedule configured. |  | Customisation | [12 empty] | 2
complete | Assignment |  | 4.2.1.1.15 | Phase B |  |  | System shall be able to monitor samples on a certain interval basis and assign it. |  | Customisation |  |  |  | 自动分配任务详细规则？ | [8 empty] | 1
complete | Assignment |  | 4.2.1.1.16 | Phase A | Test Assign |  | System shall be able to assign samples manually. | Must | Customisation |  |  |  | 配置功能 | [8 empty] | 1
complete | Assignment |  | 4.2.1.1.17 | Phase B |  |  | System shall be able to assign samples based on SAP test skip lot rules. |  | Customisation |  |  |  | 跳批是由SAP处理，与QCLaD无关
complete | Assignment |  | 4.2.1.1.18 | Phase B |  |  | System shall be able to assign samples based on other pending QC works. |  | Customisation |  |  |  | 自动分配任务详细规则？ | [8 empty] | 2
complete | Assignment |  | 4.2.1.1.19 |  |  | mark | Henkel team send us logical rule about the assign task automatically.
complete | Assignment |  | 4.2.1.1.20 |  |  | mark | Henkel team send us the detail information thermofisher listed of OSDP. Noted: Sync daily. (TF list the detail information (mapping fileds required) first)
complete | Sample |  | 4.2.1.1.21 | Phase A |  |  | System shall be able to maintain master data which mapping analysis and instrument type. | Must | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.2.1.2 |  |  |  | The system should allow Lab supervisor to determine sample test schedule arrangement way. And the system is capable of allow QC supervisor to stop automatic schedule and change it to manually. | Must
complete | Assignment |  | 4.2.1.2.1 | Phase B |  |  | System shall be able to modify schedule. | Must | Customisation |  |  |  | 自带功能 | [8 empty] | 1
complete |  |  | 4.2.1.3 |  |  |  | The system should have capability to allow QC Supervisor modify testing task sequence based on lab test priority. | Must
complete | Assignment |  | 4.2.1.3.1 | Phase B |  |  | System shall be able to allow key user modify task based on urgency test. | Must | Configuration |  |  |  | 配置字段和按钮
complete |  |  | 4.2.1.4 |  |  |  | Standard testing Pre-schedule: The system should have capability to get SAP inspection lot immediately after release in SAP and prearrange testing schedule based on inspection lot sequence. | Must
complete | Interface |  | 4.2.1.4.1 | Phase A |  |  | system shall be able to create tasks when SAP pushes inspection lot based on configurable interval and configurable start time. |  | Configuration |  |  |  | 使用SMIDI则是特定频率登录sample，如果是定制开发结果，则是SAP推送则立即登录lot，没有频率概览
complete | Assignment |  | 4.2.1.4.2 | Phase B |  |  | System shall be follow FIFO rules based on sample receiving date when assigning tasks. |  | Customisation |  |  |  | 自动分配任务详细规则？ | [8 empty] | 2
complete | Interface |  | 4.2.1.4.3 | Phase A |  |  | System shall assign tasks before the inspection lot only for JIT materials. And the results shall be pushed to sap if inspection lot is created. |  | Customisation |  |  |  | SMIDI或定制开发接口，将结果回传给SAP JIT检验存在先有sample再有检验批，所以当检验批下发后需要与已创建的sample关联； 是否需要拆分两条？
Complete |  |  | 4.2.1.4.4 |  |  | mark | frequency need to double confirm by TF and Henkel; to be confirmed.
complete |  |  | 4.2.1.5 |  |  |  | Standard testing schedule: The system should have capability to determine inspection task sequence based on preschedule once the sample arrives. | Must
complete | Assignment |  | 4.2.1.5.1 | Phase B |  |  | System shall assign task based on priority rules once sample arrives. |  | Customisation |  |  |  | 自动分配任务详细规则？ | [8 empty] | 2
complete |  |  | 4.2.1.6 |  |  |  | Non-standard testing/non-label sample Pre-schedule: The system should be capable of prearrange test schedule based on test request sequence or based on calendar. | Must
complete | Assignment |  | 4.2.1.6.1 | Phase B |  |  | System shall allow to create tasks based on calendar schedule. |  | Customisation |  |  |  | 自动分配任务详细规则？ | [8 empty] | 2
complete |  |  | 4.2.1.7 |  |  |  | Non-standard testing/non-label sample schedule: The system should be capable of determine testing schedule. Check for sample location from QCLAD, if already available use the label in the sample and start testing process. In case, sample not available at QC and not having a label, QCLAD should print and start the process else use the sample to logging to QCLAD. once sample is logged in, start testing process. | Must
complete | Report&Label |  | 4.2.1.7.1 | Phase A |  |  | System shall allow user to print label by manually input the information. | Must | Configuration |  |  |  | 配置标签模板和按钮 | [8 empty] | /
complete |  |  | 4.2.1.8 |  |  |  | System should be capable to maintain QC shift, user information to support scheduler feature. Number of shift and shift hour of each shift can be configurable by Lab supervisor. | Must
complete | Assignment |  | 4.2.1.8.1 | Phase A | Test Assign |  | System shall allow user maintain master data for shift schedule by week. Number of shift and shift hour of each shift shall be configurable in the master data at plant level. |  | Customisation |  |  |  | 定制开发，人员排班信息表，维护人员的每天的上下班时间 | [8 empty] | 14
complete |  |  | 4.2.1.8.2 |  |  | mark | note: Henkel need offer shift template
complete |  |  | 4.2.1.9 |  |  |  | The system should be capable to get/check user testing skill via Henkel’s skill matrix system and assign the right person. In case if skill matrix not available or the supervisor wants to modify QCLAD’s task assignment system should allow manual assignment. | Must
complete | Assignment |  | 4.2.1.9.1 | Phase B |  |  | System shall check skill when assigning tasks to operator. |  | Customisation |  |  |  | 手动或自动分配任务时，人员的选择只能选择具有该任务技能的人员，存在工厂没有OSDP系统，则跳过技能筛序； | [8 empty] | 3
complete | Interface |  | 4.2.1.9.2 | Phase B |  |  | System shall be able to support skill shall be sync with OSDP system if there is OSDP in plant. Refer to 4.5.1.14 |  | Customisation |  |  |  | 定制开发接口，将OSDP的信息同步到QCLAD中的培训信息表中
complete | Assignment |  | 4.2.1.9.3 | Phase A | Test Assign |  | System shall allow user to rearrange task manually. | Must | Configuration |  |  |  | 配置按钮
complete |  |  | 4.2.1.10 |  |  |  | For standard and non-standard testing, test status should be showed on dashboard, the detailed information, including the inspection lot(standard test), test request#(non-standard test), product number, product name, batch#, user ID, etc. The detailed information can be reviewed when click status/inspection lot. | Must
complete | Dashboard |  | 4.2.1.10.1 | Phase A |  |  | System shall have dashboard which display tests, test status, product number, product name, batch number, user ID. inspection lot, inspection lot(standard test), test. request#(non-standard test) |  | Out Of Scope |  |  |  | 标准功能即可实现 | [9 empty] | Using folder is ok
complete |  |  | 4.2.1.10.2 |  |  | mark | Henkel offer dashboard template, Tony
complete |  |  | 4.2.1.11 |  |  |  | The system should be capable of arrange test schedule for scheduled tests (shelf life study, aging test, etc.) based on test schedule @ specific frequency as monthly, weekly, specific time on every day... | Must
complete | Interface |  | 4.2.1.11.1 | Phase B |  |  | System shall create tasks for samples based on specific frequency. |  | Customisation |  |  |  | 自动分配任务详细规则？自动分配任务使用后台定时任务
|  |  | 4.3.1.1 |  |  | COA of RM auto-capture | The system shall provide functionality to recognize & download documents from incoming e-mail | Wont | Out Of Scope
4.3.1.1.1
|  |  | 4.3.1.2 |  |  |  | The system shall provide functionality to extract data from COA and store them in Henkel database | Wont | Out Of Scope
4.3.1.2.1
|  |  | 4.3.1.3 |  |  |  | The system shall provide functionality to check open SAP inspection lot and search respective data in database | Wont | Out Of Scope
4.3.1.3.1
|  |  | 4.3.1.4 |  |  |  | The system shall provide functionality to validate characteristics, results, and range (COA against SAP) | Wont | Out Of Scope
4.3.1.4.1
|  |  | 4.3.1.5 |  |  |  | The system shall provide functionality to record result and transfer, maintain data in SAP | Wont | Out Of Scope
4.3.1.5.1
|  |  | 4.3.1.6 |  |  |  | The system shall provide functionality to approach QC through email when abnormal happened or wrong data generated | Wont | Out Of Scope
4.3.1.6.1
|  |  | 4.3.1.7 |  |  |  | Henkel has several language and format based on vendor, the system should have capability to capture from any format. | Wont | Out Of Scope
4.3.1.7.1
complete |  |  | 4.3.2.1 |  |  | Data Capture of Testing Instrument | The system shall provide functionality to capture data from Henkel type A and B test instrument automatically | Must
complete | IM Integartion |  | 4.3.2.1.1 | Phase A |  |  | System shall be able to capture data from Henkel type A. |  | Interface
complete | IM Integartion |  | 4.3.2.1.2 | Phase A |  |  | System shall be able to capture data from Henkel type B. |  | Interface
complete |  |  | 4.3.2.2 |  |  |  | The system shall provide functionality to input the testing data manually | Must
complete | Sample |  | 4.3.2.2.1 | Phase A |  |  | System shall be able support to input the testing data manually. |  | Standard | [12 empty] | /
complete |  |  | 4.3.2.3 |  |  |  | The system shall provide functionality to integrate all the types and brands of instruments, simplifying and streamlining the operation | Must
complete | LES |  | 4.3.2.3.1 | Phase B |  |  | System shall be able to select and display the instrument in the LES. |  | Standard | [12 empty] | /
complete | IM Integartion |  | 4.3.2.3.2 | Phase A |  |  | System shall provide functionality to integrate all type A and type B instruments which can export readable file. |  | Configuration | [12 empty] | /
complete | LES |  | 4.3.2.3.3 | Phase B |  |  | System shall be able to fetch the results in LES and display the results. |  | Standard | [12 empty] | /
complete |  |  | 4.3.2.4 |  |  |  | The system shall provide functionality to automatically identify test sample information via test instruments without additional manually key in sample information into test instruments. | Must
complete |  |  | 4.3.2.4.1 | Phase B |  | mark | user need to identifying the sample id in instrument software so that LIMS can match data to samples.
complete | LES |  | 4.3.2.4.2 | Phase B |  |  | System shall be able to identify sample in LES by scan label. |  | Configuration | [12 empty] | /
complete | LES |  | 4.3.2.4.3 | Phase B |  |  | System shall be able to manually enter sample id in LES. |  | Configuration | [12 empty] | /
complete |  |  | 4.3.2.5 |  |  |  | The system vendor should train Henkel user about how to set up functionality to capture instrument data | Must
complete | IM Integartion |  | 4.3.2.5.1 | Phase A |  |  | System vendor should train Henkel user about how to set up functionality to capture instrument data. |  | Non-function | [12 empty] | /
complete |  |  | 4.3.2.6 |  |  |  | The system vendor has overall responsibility to check Henkel instrument connection capability and set up interface between instrument and system. | Must
complete | IM Integartion |  | 4.3.2.6.1 | Phase A |  |  | System vendor has overall responsibility to check Henkel instrument connection capability and set up interface between instrument and system. |  | Non-function | [12 empty] | /
complete |  |  | 4.4.1.1 |  |  | Laboratory Execution | Enable Workflow execution of Laboratory daily operation Quick overview of inspection plan on daily, weekly, monthly views Able to view the status of testing, details of inspection lot on clicking on each On clicking user is expected to see the status of SOP (which steps completed, on-going and not started) Kanban dashboards with storage location and quantity (with/within safety stock) with desired filters Dashboards showing lab equipment availability | Must
complete | Dashboard |  | 4.4.1.1.1 | Phase A |  |  | System shall support dashboard display overview of inspection lot on daily, weekly, monthly views. |  | Out Of Scope | [12 empty] | 2 | Using folder is ok
complete | Sample |  | 4.4.1.1.2 | Phase A |  |  | System shall be able to view the status of testing, details of inspection lot. |  | Configuration | [12 empty] | 1 | 配置lot字段、文件夹、权限
complete | Sample |  | 4.4.1.1.3 | Phase A |  |  | System shall be able to record standard cycle time and actual cycle time under test level. |  | Out Of Scope | [12 empty] | 2 | OOO
complete | LES |  | 4.4.1.1.4 | Phase B |  |  | System shall be able to dispaly the status of LES (which steps completed, inprogress and not started). |  | Standard | [12 empty] | /
complete | Dashboard |  | 4.4.1.1.5 | Phase A |  |  | System shall be able to display sample storage location and sample quantity. |  | Out Of Scope | [12 empty] | 1 | Using folder is ok
complete | Dashboard |  | 4.4.1.1.6 | Phase A |  |  | System shall support dashboard showing lab equipment availability. Equipment usage can be tracked trhough scanning before and after the usage. |  | Out Of Scope | [12 empty] | 3
complete |  |  | 4.4.1.2 |  |  |  | Break each SOP down into steps that lead through the process, including test method execution, instrument calibration, result check and calculation Henkel has different test methods, the system should have capablity to support all test method execution. Henkel test method instruction keeps in Henkel Remap system. The system should have a hyperlink to guide user to Remap system on clicking a test method. Master hyperlink guide user to Remap system. The system should allow site admin to maintain unique hyperlink for each different test method. | Must
complete |  |  | 4.4.1.2.1 |  |  | mark | Henkel need to offer 10 feasible SOP so that TF team can creat 10 LES in system.
complete | LES |  | 4.4.1.2.2 | Phase B |  |  | System shall support maintain SOP by steps in LES, including test method execution, instrument calibration, result check and calculation. |  | Standard | [12 empty] | /
complete | LES |  | 4.4.1.2.4 | Phase B |  |  | System shall allow user to access Remap system by hyperlink in analysis. |  | Configuration | [12 empty] | /
complete | LES |  | 4.4.1.2.4 | Phase B |  |  | System shall support all test method execution. |  | Standard | [12 empty] | /
complete | LES |  | 4.4.1.2.5 | Phase B |  |  | System shall allow specific user to mantain and view hyperlink in analysis. |  | Configuration | [12 empty] | /
complete |  |  | 4.4.1.3 |  |  |  | Step-wise approach to achieve Automation of routine tasks User should be able to start and record testing results from iPAD / Tablet Ability to upload documents during testing(like images..) | Must
complete | LES |  | 4.4.1.3.1 | Phase B |  |  | System shall support user to start and record testing results by step from iPAD or Tablet. |  | Standard | [12 empty] | /
complete | LES |  | 4.4.1.3.2 | Phase B |  |  | System shall be able to upload attachment during testing(like images..) |  | Standard | [12 empty] | /
complete |  |  | 4.4.1.4 |  |  |  | Enable Instrument Integration during execution of laboratory SOP. Provides the ability to retrieve values from remotely attached instruments | Must
complete | LES |  | 4.4.1.4.1 | Phase B |  |  | System shall support retrieve values from Type A and Type B instruments in LES. |  | Configuration | [12 empty] | /
complete |  |  | 4.4.1.4.1 |  |  | MARK | remotely attach instrument = type A and type B instrument
complete |  |  | 4.4.1.5 |  |  |  | Enable eSignatures and Cross Check between different users during execution | Must
complete | LES |  | 4.4.1.5.1 | Phase B |  |  | System shall support Cross Check between different users during execution in LES. |  | Standard | [12 empty] | /
complete |  |  | 4.4.1.5.2 |  |  | mark | what's e signature(like peer review)stands for? Re: Esignature is out of scope. Replace eSigniture with peer review.
complete |  |  | 4.4.1.6 |  |  |  | Enable audit trail on all steps during execution | Must
complete | LES |  | 4.4.1.6.1 | Phase B |  |  | System shall support audit on all steps during execution. |  | Standard | [12 empty] | /
complete |  |  | 4.4.1.7 |  |  |  | Allows execution of Lab Methods in remote locations, can be used in PC, tablet( Ipad, etc.) | Must
pending | LES |  | 4.4.1.7.1 | Phase B |  |  | System shall support execution of Lab Methods in remote locations, can be used in PC, tablet( Ipad, etc.) |  | Standard | [12 empty] | /
complete |  |  | 4.4.1.8 |  |  |  | Review the actual Lab Execution to ensure it has been executed correctly | Must
complete | LES |  | 4.4.1.8.1 | Phase B |  |  | System shall support review Lab Execution. |  | Standard | [12 empty] | /
complete |  |  | 4.4.1.9 |  |  |  | Generate follow-up actions from the Lab Execution review | Must
complete | LES |  | 4.4.1.9.1 | Phase B |  | mark | System shall allow specific user to reassign the test to another user. |  | Configuration | [12 empty] | /
complete | LES |  | 4.4.1.9.2 | Phase B |  |  | System shall require to enter comments when rejecting the result during Lab execution review. |  | Configuration | [12 empty] | /
complete |  |  | 4.4.1.10 |  |  |  | Re-generate the paper SOP from the configured Lab methods, including any execution outcomes, Access to all Lab Execution data for reporting and Display audit information, linked entities, review statuses | Must
complete | LES |  | 4.4.1.10.1 | Phase B |  |  | System shall support print Lab execution record. |  | Standard | [12 empty] | /
complete | LES |  | 4.4.1.10.2 | Phase B |  |  | System shall support configure lab execution record report template. |  | Standard | [12 empty] | /
complete |  |  | 4.4.1.11 |  |  |  | Enable workflow to execute Henkel MSA, maintain MSA plan, send reminder according to plan, send alerts once expired MSA happened. | Must
complete | Sample |  | 4.4.1.11.1 | Phase B |  |  | System shall support execute and maintain MSA plan. |  | Out Of Scope | [12 empty] | /
complete | Sample |  | 4.4.1.11.2 | Phase B |  |  | System shall support remind MSA according to plan and remind expiration. |  | Out Of Scope | [12 empty] | /
complete |  |  | 4.4.2.1 |  |  | Resampling | Four solutionsare possible to handle the resampling: • Create a new inspection lot in SAP • Create a new inspection lot in SAP with a link to the initial inspection lot, for example a user field populated with the initial lot. • Create another sample in the QCLAD, related to the inspection lot (job in the QCLAD) Reactivate in the QCLAD a validated sample and reenter the results on the initial test. Then the sample is authorised and all the results are sent again to SAP. The result values are updated in SAP | Must
pending | Interface |  | 4.4.2.1.1 | Phase B |  |  | Create another sample in the QCLAD, related to the inspection lot (job in the QCLAD) and all the results are sent again to SAP. The result values are updated in SAP. Check with Neelima System shall be able to trigger resample in QCLAD and create a new sample with unique ID, which results can be sent back to SAP. |  | Customisation
complete |  |  | 4.4.2.1.2 |  |  | Mark | Henkel need to check use which one solution for handling resampling.
complete |  |  | 4.5.1 |  |  | Interface to Smart factory, MES and SKill matrix | Enable Download of information from SAP to QCLAD and upload information from QCLAD to SAP Push/pull information from Henkel smart factory, MES, Henkel Skill Matrix. The information pulled/pushed should be available in QCLAD in case of analyzing. API calls need to be designed and agreed by different teams for pushing/pulling data based on the project scope. | Must
complete | Interface |  | 4.5.1.1 | Phase A |  |  | System shall support download inspection lot from SAP to QCLAD. 1）Create a sample in QCLAD based on the downloaded Inspection Lot, or change an existing sample (JIT process). 2）If the inspection lot in SAP also has multiple activities, then QCLAD needs to create multiple samples. 3）The test item in lot has a field for whether or not to skip the batch (dynamic message), and whether the SMIDI standard function can be written directly to the test table. |  | Interface | [12 empty] | 10
| Interface |  | 4.5.1.2 | Phase A |  | Mark | System shall support download Batch information from SAP to QCLAD. |  | Out Of Scope | [12 empty] | 0
complete | Interface |  | 4.5.1.3 | Phase A |  |  | System shall support download Inspection Plan from SAP to QCLAD. Needs to be synchronised and updated in real time. |  | Interface | [12 empty] | 3
complete | Interface |  | 4.5.1.4 | Phase A |  |  | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the MIC. Needs to be synchronised and updated in real time. |  | Interface | [12 empty] | 3
complete | Interface |  | 4.5.1.5 | Phase A |  |  | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the specification. Needs to be synchronised and updated in real time. |  | Interface | [12 empty] | 3
complete | Interface |  | 4.5.1.6 | Phase A |  |  | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the Material master data. Needs to be synchronised and updated in real time. |  | Interface | [12 empty] | 3
complete | Interface |  | 4.5.1.7 | Phase A |  |  | System shall support download GHS info from SAP to QCLAD. Refer to 4.8.5.8.2 |  | Out Of Scope | [12 empty] | 0
| Interface |  | 4.5.1.8 | Phase A |  |  | System shall support download Plant Code from SAP to QCLAD. |  | Interface | [12 empty] | 3
complete | Interface |  | 4.5.1.9 | Phase A |  |  | System shall support download QM notification from SAP to QCLAD. |  | Interface | [12 empty] | 3
complete | Interface |  | 4.5.1.10 | Phase A |  |  | System shall support to upload result value from QCLAD to SAP. 1）When there is a Retest operation done, the result of the last Retest needs to be returned to SAP. 2）once the LIMS post result back to SAP，SAP MIC status should be auto rejected or accepted? 3）system shall support post all the samples result back to SAP, including the resampled sample. 4）related to item 1, whether Smidi can configure that, once inspection lot is downloaded mapped with an existing sample in LIMS; if that sample is authorized with result, then Smidi can also trigger the result pushing to SAP? (JIT process) |  | Interface | [12 empty] | 6
complete | Interface |  | 4.5.1.11 | Phase A |  | Mark | System shall support to upload result value from SAP to QCLAD. |  | Out Of Scope | [12 empty] | 15
complete | Interface |  | 4.5.1.12 | Phase B |  |  | System shall push notify information(including resample and adjustment) to Henkel smart factory. |  | Interface | [12 empty] | 7
complete | Interface |  | 4.5.1.13 | Phase B |  |  | System shall pull result information from Henkel smart factory. |  | Interface | [12 empty] | 7
complete | Interface |  | 4.5.1.14 | Phase B |  |  | System shall support to upload result value from QCLAD to Henkel smart factory. |  | Interface | [12 empty] | 7
complete | Interface |  | 4.5.1.15 | Phase B |  |  | System shall support to upload sample states from QCLAD to Henkel smart factory. |  | Interface | [12 empty] | 14
complete | Interface |  | 4.5.1.16 | Phase B |  |  | System shall push/pull adjustment quantity information from/to Henkel smart factory. |  | Interface | [12 empty] | 9
|  |  | 4.5.1.17 | Phase B |  |  | System shall pull operator skill information from Henkel Skill Matrix. |  | Interface
complete |  |  | 4.5.2 |  |  | SAP process in existing applications | Currently MES and Smart factory have SAP interface to pull master and transactional data. Need to identify what to be pulled from SAP directly and can we reuse the data pulled by the applications to SAP instead of pulling again. Need to work out on the details. | Must
complete | Interface |  | 4.5.2.1 | Phase A |  |  | Refer to 4.5.1.1 & 4.5.1.2 & 4.5.1.3 above. |  | Interface
complete |  |  | 4.5.3 |  |  | Communication between SAP and QCLAD | nformation downloaded : • IDH#，Batch#, master data (plant#, lab#, material, shelf life, date of manufacturing, inspection interval, MIC#, etc.), inspection plan, skip lot rules, Quality Notification#, equipment maintenance master data • Details of required fields to be agreed between Henkel and vendor after the process agreement. Please don’t consider this as a final set of fields. QM Transactional data should be received/sent in near real time. Need to do discuss what to be managed in near real time and what to be managed with jobs to be discussed after the process agreement. | Must
complete | Interface |  | 4.5.3.1 |  |  |  | Refer to 4.5.1.1 & 4.5.1.2 & 4.5.1.3 above. |  | Interface
complete |  |  | 4.5.4 |  |  | Upload of information from the QCLAD to SAP/MES/Smart factory | The upload of the results is triggered by the validation of the laboratory. Once user approves the results pulled from lab equipment in QCLAD, it should be pushed to SAP in near real time. In-process testing result need to refer in-process testing workflow to update test result and decision into Henkel MES and smart factory system. If the laboratory reactivates the sample and the results, a result value can be sent several times to SAP, the result in SAP is updated (the characteristics are declared as long term characteristics in SAP). In case of any result values need to be modified with a pre-defined rules or other calculations, it should be allowed automatically The valuation can be setup in the QCLAD or in SAP. If it is setup in the QCLaD, it is associated to each result. | Must
complete | Sample |  | 4.5.4.1 |  |  |  | System shall allow result values can be modified with a pre-defined rules or other calculations automatically. |  | Standard | [12 empty] | /
complete | Sample |  | 4.5.4.2 |  |  |  | System shall support the specification limit can be setup in the QCLAD and is associated to each result. |  | Standard | [12 empty] | /
complete |  |  | 4.6.1.1 |  |  | Dashboard / Report (downloadable) | Sample status summary graph per Lab/Plant/Country/Henkel network/ global Sample status graph can be reviewed daily/weekly/monthly/yearly Sample status should have completed, in progress, received, cancelled Report should include all sample type, RM, semi-finish, Bulk, FG, standard test and non-standard test, etc. Report can be filtered by material, technology (product technology information should from SAP) | Must
complete | Dashboard |  | 4.6.1.1.1 | Phase A |  |  | System shall be able to display sample status by lab/plant/country/henkel network/global in dashboard. |  | Out Of Scope | [12 empty] | 2 | Using folder is ok
complete | Dashboard |  | 4.6.1.1.2 | Phase A |  |  | System shall be able to display sample status by daily/weekly/monthly/yearly in dashboard. |  | Out Of Scope | [12 empty] | 2 | Using folder is ok
complete | Dashboard |  | 4.6.1.1.3 | Phase A |  |  | System shall support different sample status, including completed, in progress, received, cancelled, retained. |  | Out Of Scope | [12 empty] | 2 | Using folder is ok
complete | Dashboard |  | 4.6.1.1.4 | Phase A |  |  | System shall include sample type in report, detailed sample type refers to RTM 4.5.1 items. |  | Out Of Scope | [12 empty] | 1 | Using folder is ok
complete | Sample |  | 4.6.1.1.5 | Phase A |  |  | System shall support report can be filtered by material, technology (product technology information should from SAP) in folder. |  | Configuration | [12 empty] | 1 | 文件夹配置
complete | [5 empty] | Mark | Henkel need to check what's the meaning of report with Neelima
complete |  |  | 4.6.1.2 |  |  |  | Daily sample status summary graph per Lab/Plant should be showed real time. | Must
complete | Dashboard |  | 4.6.1.2.1 | Phase A |  |  | System shall support to display dashboard with sample status in real time. |  | Out Of Scope | [13 empty] | Using folder is ok
complete |  |  | 4.6.1.3 |  |  |  | Scheduled job list (Task assignment job in specific time period) Scheduled job list is related to schedule work. Scheduled job list should be showed real time. | Must
complete | Dashboard |  | 4.6.1.3.1 | Phase A |  |  | System shall display task list in specific time period. |  | Out Of Scope | [12 empty] | 1 | Using folder is ok
complete | Dashboard |  | 4.6.1.3.2 | Phase A |  |  | System shall display task list related to work. |  | Out Of Scope | [12 empty] | 1 | Using folder is ok
complete | Dashboard |  | 4.6.1.3.3 | Phase A |  |  | System shall display task list in real time. |  | Out Of Scope | [13 empty] | Using folder is ok
complete |  |  | 4.6.1.4 |  |  |  | Overdue scheduled job report | Must
complete | Dashboard |  | 4.6.1.4.1 | Phase A |  |  | System shall display overdue task list. |  | Out Of Scope | [12 empty] | 1 | Using folder is ok
complete |  |  | 4.6.1.5 |  |  |  | Instrument status (available, out of service, Retired) Statistics (key: instrument ID, instrument Type, days in available, days out of service…) | Must
complete | Dashboard |  | 4.6.1.5.1 | Phase A |  |  | System shall display instrument list with status(Unaviable, Available, Maintance Due, Retired, Require Calibration, In Calibration). |  | Out Of Scope | [12 empty] | / | Using folder is ok
complete | Dashboard |  | 4.6.1.5.2 | Phase A |  |  | System shall support dashbord to display instrument list including (instrument ID, instrument Type, instrument Status, days in available and days out of service by daily, weekly, monthly or yearly) |  | Out Of Scope | [12 empty] | 3
complete |  |  | 4.6.1.5.3 |  |  | Mark | What’s the meaning of 'days in available, days out of service'? 怎么理解Days
complete |  |  | 4.6.1.6 |  |  |  | Instrument load and utilization, Actual Instrument Utilization=∑(Total Actual Instrument working Hours/ Total working Hours) Total working hours is related to shift arrangement. | Must
complete | Dashboard |  | 4.6.1.6.1 | Phase A |  |  | System shall support display instrument utilization by daily/weekly/monthly/yearly in dashboard. |  | Out Of Scope | [12 empty] | 3
complete | Dashboard |  | 4.6.1.6.2 | Phase A |  |  | Total Actual Instrument working Hours= End time by scanning minus Start time by scanning |  | Out Of Scope | [12 empty] | 1
complete | Dashboard |  | 4.6.1.6.3 | Phase A |  |  | Total working hours is related to shift arrangement,calculated as off-duty time minus on-duty time. |  | Out Of Scope | [12 empty] | 2
complete |  |  | 4.6.1.7 |  |  |  | Work load (Sample or analysis) statistics (per work hour, per plant, per analyst…) | Must
complete | Dashboard |  | 4.6.1.7.1 | Phase A |  |  | System shall support display work load by plant/duration. |  | Out Of Scope | [12 empty] | 2
complete |  |  | 4.6.1.8 |  |  |  | Work load can be number of inspection lot, number of sample, number of test, number of skip lot, number of skip test | Must
complete | Dashboard |  | 4.6.1.8.1 | Phase A |  |  | System shall support display work load with number of inspection lot, number of sample, number of test, number of skip lot, number of skip test in folder. |  | Out Of Scope | [13 empty] | Using folder is ok
complete |  |  | 4.6.1.9 |  |  |  | Report: extract data based on sample type, analysis, test schedule, login time, standard time…. | Must
complete | Sample |  | 4.6.1.9.1 | Phase A |  |  | System shall support export data based on sample type, analysis, test schedule, login time, standard time by folder. |  | Standard | [12 empty] | /
complete |  |  | 4.6.1.9.2 |  |  | Mark | what format of the report？The aim of extract data.
complete |  |  | 4.6.1.10 |  |  |  | QC release time: To be able to automatically calculate individual batch/test request complete time in specific time period QC Release Time=∑(Time End-Time Start) Time End: UD time of batch or test request completed time Time Start: Sample received time (actual time barcode scan in QC) of inspection lot | Must
complete | Dashboard |  | 4.6.1.10.1 | Phase A |  |  | System shall be able to automatically calculate QC release time for individual batch/test request. |  | Out Of Scope | [12 empty] | 1
complete | Dashboard |  | 4.6.1.10.2 | Phase A |  |  | Sample Release Time=Time End-Time Start |  | Out Of Scope | [12 empty] | 1
complete |  |  | 4.6.1.10.3 |  |  | Mark | Why need Σ？Henkel:remove Σ
complete |  |  | 4.6.1.10.4 |  |  | Mark | Time End: sample authorizd time
complete | Dashboard |  | 4.6.1.10.5 | Phase A |  |  | Time Start: sample received time (actual time barcode scan in QC) of inspection lot |  | Out Of Scope | [12 empty] | 1
|  |  | 4.6.1.11 |  |  |  | QC Productivity: Measure efficiency of QC efforts at a manufacturing site in specific time period 1. QC Testing Productivity by test =∑(# test)/#FTE The sum of # inspection test compare with #FTE for a give selection 2. QC Testing productivity by inspection lot =∑(# SAP inspection lot)/#FTE The sum of # inspection lot compare with #FTE for a give selection | Must
pending | Dashboard |  | 4.6.1.11.1 |  |  | Mark | Henkel need to check what's the report of Productivity Henkel:QC productivity can be valuated according to 3 formulas: QC efficiency 1=Direct QC test LH(IQC+IPQC+OQC,including retest)/QC attendence hours QC efficiency 2=(Direct QC test LH+non-standard QC test LH)/QC attendence hours QC efficiency 3=(Direct QC test LH+non-standard QC test LH+indirect QC LH)/QC attendence hours Standard testing - Direct QC Test Non standard testing - Indirect QC QC attendance hours - based on the shift management |  | Out Of Scope | [12 empty] | 3
complete |  |  | 4.6.1.12 |  |  |  | Instrument PM(preventive maintenance) performance, including, number of PM performed in QC Lab & on time PM% in specific time period | Must
complete | Instrument |  | 4.6.1.12.1 | Phase A |  |  | System shall allow user to add maintenance plan. Maintenance plan shall include PM(preventive maintenance) type. |  | Configuration |  |  |  | 配置phrase字段 | [8 empty] | 1
complete | Dashboard |  | 4.6.1.12.2 | Phase A |  |  | System shall display on time proportion for PM for each instrument by report. |  | Out Of Scope | [12 empty] | 2
complete |  |  | 4.6.1.13 |  |  |  | Instrument calibration performance: including, number of calibration performed in QC Lab & on time calibration% in specific time period | Must
complete | Dashboard |  | 4.6.1.13.1 | Phase A |  |  | System shall display the quantity of calibration record and on time proporation for maintenance by report. |  | Out Of Scope | [12 empty] | 3
complete |  |  | 4.6.1.14 |  |  |  | MSA performance: including, number of MSA performed in QC Lab & on time MSA% in specific time period | Must
complete | Sample |  | 4.6.1.14.1 | Phase A |  |  | System shall display the quantity of MSA task completed in system, completed shall be triggered by uploading MSA report to QCLAD. |  | Out Of Scope
complete | Dashboard |  |  | Phase A |  |  | System shall display on time proportion for MSA task by report. |  | Out Of Scope
complete |  |  | 4.6.1.15 |  |  |  | Consumable/Spare parts report: stock status and safety stock status in specific time period | Must
complete | Dashboard |  | 4.6.1.15.1 | Phase A |  |  | System shall display stock status and safety stock status(the stock is below the minumum stock and above the maximum stock) in specific time period by report. |  | Out Of Scope |  |  |  | 配置文件夹，如果定义的report是报告就算template；如果是文件夹就是配置 | [8 empty] | 2 | Using folder is ok
complete |  |  | 4.6.1.15.2 |  |  | Mark | status refers to what?
complete |  |  | 4.6.1.16 |  |  |  | Retain sample report: Analysis by storage location, stock status , number of expire sample stock status, disposed stock by date | Must
complete | Dashboard |  | 4.6.1.16.1 | Phase A |  |  | System shall display retain sample in dashboard by storage location, retain status , number of expired retains, disposed retains by date. |  | Out Of Scope | [12 empty] | 2 | Using folder is ok
pending |  |  | 4.6.1.16.2 |  |  | Mark | need dashboard. Henkel : design the dashborad
complete |  |  | 4.7.1.1 |  |  | Sample Tracking | The system shall maintain a history of sample life information about a sample's workflow. The workflow is a requirement for internal COC (Chain of Custody) that tracks all samples from the time they are received until disposal | Must
complete | Sample |  | 4.7.1.1.1 | Phase A |  |  | System shall support to track sample life history (Chain of Custody). | Must | Configuration |  |  |  | 配置查看custody | [8 empty] | 1 | 按钮和审计配置
complete | Sample |  | 4.7.1.1.2 | Phase A |  |  | System shall support to display samples and test results by batch number. |  | Standard | [12 empty] | /
complete |  |  | 4.7.1.2 |  |  |  | The system shall track users by log-in the data they enter and functions they perform | Must
complete | Security |  | 4.7.1.2.1 | Phase A |  |  | System shall support to track data entry history and modification history. |  | Configuration |  |  |  | 配置审计 | [8 empty] | /
complete |  |  | 4.7.1.3 |  |  |  | The user shall be able to view all the information in QCLaD dashboard about a sample including current status | Must
complete | Sample |  | 4.7.1.3.1 | Phase A |  |  | The user shall be able to view all the information about a sample including current status in QCLaD folder. |  | Standard |  |  |  | 文件夹 | [8 empty] | /
complete |  |  | 4.7.1.3.2 |  |  | Mark | Noted: can fulfill by folder configuration.
complete |  |  | 4.7.1.4 |  |  |  | The user shall be able to update the sample’s workflow information as it moves through the process | Must
complete |  |  | 4.7.1.4.1 |  |  | Mark | does 'update the sample’s workflow information' means modify samples 's attributes ? Dragon -- No, attributes is not been changed but the status may change. Similar to No.36
complete | Sample |  | 4.7.1.4.2 | Phase A |  |  | System shall update sample status automatically according to workflow. |  | Standard | [12 empty] | /
complete |  |  | 4.7.1.5 |  |  |  | The system shall track the current status of test(s) for a sample | Must
complete | Sample |  | 4.7.1.5.1 | Phase A |  |  | System shall supoort to display the current status of test(s) for a sample. |  | Standard |  |  |  | 标准功能 | [8 empty] | /
complete |  |  | 4.7.1.6 |  |  |  | The system shall display a history of a sample's workflow | Must
complete | Security |  | 4.7.1.6.1 | Phase A |  |  | System shall support to track a history of a sample lifecycle. |  | Configuration |  |  |  | 审计配置,打开审计追踪 | [8 empty] | /
complete |  |  | 4.7.1.6.2 |  |  | MARK | does workflow means lifecycle? Re：Lifecycle include multiple workflow
complete |  |  | 4.7.2.1 |  |  | Data View and Audit Trail | The system shall be capable of supporting multiple languages(based on the plant preferred local language) and English, to support Henkel global roll out | Must
complete | Sample |  | 4.7.2.1.1 | Phase A |  |  | System shall support multiple languages. (Chinese and English will be implemented in Dragon pilot phase.) |  | Customisation |  |  |  | 语言包
complete |  |  | 4.7.2.2 |  |  |  | The system shall provide functionality for users with appropriate permissions to configure a view of the QCLAD data; Permission can be configurable, by function or by user | Must
complete | Security |  | 4.7.2.2.1 | Phase A |  |  | System shall support data access control by function department or by user role. |  | Standard |  |  |  | group | [8 empty] | / | 设计权限、角色、按钮、组别
complete | Security |  | 4.7.2.2.2 | Phase A |  |  | System shall support to configure user's role and group. |  | Standard |  |  |  | group | [8 empty] | /
complete |  |  | 4.7.2.3 |  |  |  | The system shall provide real time electronic sample status and location tracking (Lab location and area). | Must
complete | Sample |  | 4.7.2.3.1 | Phase A |  |  | System shall support to display sample status and location in real time. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.4 |  |  |  | The system shall provide real time access to results for peer and supervisor review during sample testing (electronic / hard copy), hardcopy can be download/print from system | Must
complete | Sample |  | 4.7.2.4.1 | Phase A |  |  | system shall support to display results for peer and supervisor review in real time. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Sample |  | 4.7.2.4.2 | Phase A |  |  | hard copy print requirement refers to RTM 4.4.1.10.1. |  | Standard | [12 empty] | /
complete |  |  | 4.7.2.5 |  |  |  | The system shall provide functionality to perform trending and simple data analysis | Must
complete |  |  | 4.7.2.5.1 |  |  | MARK | Thermo SQC function instruction. Re:TF have upload instruction in SharePoint and replied it via email. Re:Henkel replied Not in the scope of QC LaD |  | Out Of Scope
complete |  |  | 4.7.2.6 |  |  |  | The system shall allow data generated to be exported in XML / CSV/ PDF format | Must
complete | Sample |  | 4.7.2.6.1 | Phase A |  |  | system shall support to export data through folder explorer in XML / CSV/ PDF format. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.7 |  |  |  | The system shall provide functionality to export data in a usable format to third party software (e.g. Excel) | Must
complete | Sample |  | 4.7.2.7.1 | Phase A |  |  | System shall support to export data through folder explorer in an usable format. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.7.2 |  |  | MARK | what's third party software? Re: We can download data from QCLaD to excel,pdf,word. We can upload data of third party software as a excel/pdf/word format to QCLaD manually.
complete |  |  | 4.7.2.8 |  |  |  | The system shall provide a simple interface / method for extraction of data into statistic report | Must
complete | Sample |  | 4.7.2.8.1 | Phase A |  |  | System shall provide a simple template or method for extraction of data. |  | Standard |  |  |  | 配置导出功能 | [8 empty] | /
complete |  |  | 4.7.2.8.2 |  |  | MARK | interface means integration? Why need interface in here. Re:Template
complete |  |  | 4.7.2.9 |  |  |  | The system shall provide tools to search for datasets or components by any combination of fields | Must
complete | Sample |  | 4.7.2.9.1 | Phase A |  |  | System shall support to search for datasets or components by combination of fields in folder explorer. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.10 |  |  |  | The system should provide tools for users to save one or more defined sets of structured search parameters for future use, linked to the user's profile | Must
complete | Sample |  | 4.7.2.10.1 | Phase A |  |  | System shall support user to create personal folder by saved defined one or more criteria to display certain data. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.11 |  |  |  | The system shall provide full audit trails. All audit trails shall be secure, computer generated, time stamped using the local time. It shall include the date and time, retention of original data, reason for change to original data and the individual performing the task. All data entry, recording of reporting processes and all changes to the reported data shall be recorded along with any deletion of data | Must
complete | Security |  | 4.7.2.11.1 | Phase A |  |  | System shall provide full audit trails. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Security |  | 4.7.2.11.2 | Phase A |  |  | System shall support all audit trails shall be secure, computer generated, time stamped using the local time. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.11.3 |  |  | Mark | Thermo check local time Re: have checked.
complete | Security |  | 4.7.2.11.4 | Phase A |  |  | System shall support audit trial shall include the date and time, retention of original data, reason for change to original data and the individual performing the task. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Security |  | 4.7.2.11.5 | Phase A |  |  | System shall be able to support all data entry, recording of reporting processes and all changes to the reported data shall be recorded along with any deletion of data. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.12 |  |  |  | The system shall require audit trail entries for all creation, modification and approval associated with static data | Must
complete | Security |  | 4.7.2.12.1 | Phase A |  |  | System shall support audit trail for all creation, modification and approval associated with static data. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.13 |  |  |  | The system shall allow the display, print or download any / all audit trails | Must
complete | Security |  | 4.7.2.13.1 | Phase A |  |  | System shall support to display, print or export any / all audit trails. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.7.2.14 |  |  |  | The system should be able to export the audit trail into a report | Must
complete | Security |  | 4.7.2.14.1 | Phase A |  |  | System shall support to export the audit trail into a report. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.8.1.1 |  |  | Laboratory equipment | Standard management of instruments and equipment in the lab including specifications, parameters, spare parts, calibration and maintenance. | Must
complete | Instrument |  | 4.8.1.1.1 | Phase A |  |  | System shall support maintain specification and parameters in equipment master data. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Instrument |  | 4.8.1.1.2 | Phase A |  |  | System shall allow maintain spare parts, calibration and maintenance. |  | Standard | [12 empty] | /
complete |  |  | 4.8.1.2 |  |  |  | Instrument calibration and maintenance scheduler. A module to maintain calibration schedules and maintenance schedule and providing warning messages. Use instrument calibration module. | Must
complete | Instrument |  | 4.8.1.2.1 | Phase A |  |  | System shall suport calibration and maintenance plan locally. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Instrument |  | 4.8.1.2.2 | Phase A |  |  | System shall remind user when instrument maintenance expire in folder. |  | Out Of Scope |  |  |  | 配置文件夹 | [8 empty] | 2 | OOO
complete |  |  | 4.8.1.2.3 |  |  | Mark | Need to check maintenance scheduler is in scope with Neelima. Henkel:Need the maintainance task to be schedulered, but sending notification to SAP is not in scope.
complete |  |  | 4.8.1.3 |  |  |  | Instrument history. An instrument history report detailing the failures and calibration / maintenance events for an instrument | Must
complete | Instrument |  | 4.8.1.3.1 | Phase A |  |  | System shall support to record instrument history , including failures, calibration, maintenance. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.8.1.4 |  |  |  | When the chemical/instrument is going to be expired, the system shall provide functionality to alert specified user(s) accordingly | Must
|  |  | 4.8.1.4.1 |  |  |  | System shall alert specific user when instrument is about to expire list in folder. |  | Out Of Scope |  |  |  | 配置仪器即将过期文件夹
complete |  |  | 4.8.1.5 |  |  |  | Result entry can be blocked for users that do not comply with the user testing skill requirements, QCLaD should has capability to check user’s testing skill from Henkel skill matrix tool if Henkel site use the tool | Must
complete | Sample |  | 4.8.1.5.1 | Phase A |  |  | System shall only allow tests assign to qualified users. |  | Configuration |  |  |  | 权限配置 | [8 empty] | /
complete | Interface |  | 4.8.1.5.2 | Phase B |  |  | System shall sync user’s testing skill from Henkel skill matrix tool. |  | Interface
complete |  |  | 4.8.1.6 |  |  |  | The system shall provide a way to alert the system defined users when the chemicals or instruments used for the test is/are expired Exception for expired calibration/maintenance can be managed by NCMR, enter NCMR number can continue use the instrument. | Must
complete | Stock |  | 4.8.1.6.1 | Phase A |  |  | System shall alert specific user when chemicals or instruments is/are expired list in folder. |  | Configuration |  |  |  | 配置库存即将过期文件夹 | [8 empty] | 2 | 配置文件夹、权限、按钮
complete | Instrument |  | 4.8.1.6.2 | Phase A |  |  | System shall allow specific user to active expired instrument. |  | Configuration |  |  |  | 配置权限 | [8 empty] | 2 | 配置功能
complete |  |  | 4.8.1.6.3 |  |  | MARK | Henkel need to check NCMR number is not require for instrument Henkel: NCMR is not required.
complete |  |  | 4.8.1.7 |  |  |  | The system shall have capability to maintain master data for consumable, spare parts, equipment, etc. | Must
complete | Stock |  | 4.8.1.7.1 | Phase A |  |  | System shall have capability to maintain master data for consumable, spare parts, equipment. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.8.2.1 |  |  | Personnel | Configure roles so that Administrator has control of user accounts / roles etc. Lab super user(s) control lab static data… | Must
complete | Security |  | 4.8.2.1.1 | Phase A |  |  | System shall allow specific user to maintain user accounts, roles and groups. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Security |  | 4.8.2.1.2 | Phase A |  |  | System shall allow specific user to maintain lab static data. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.8.2.2 |  |  |  | The system shall be configurable to allow the group of users to access to data only under his groups. | Must
complete | Security |  | 4.8.2.2.1 | Phase A |  |  | System shall allow the group of users to access to data only under his groups. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Security |  | 4.8.2.2.2 | Phase A |  |  | System shall support to configure user's group. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete |  |  | 4.8.2.3 |  |  |  | The system shall provide a way to manage QC technician testing skill against analysis, instrument and preparation including, testing result and testing skill expiry date. This should be based Henkel’s Skill matrix module | Must
|  |  | 4.8.2.3.1 |  |  |  | System shall support to manage user's training skill by analysis or instrument. |  | Out Of Scope |  |  |  | 配置training功能，适配OSDP接口
complete | Interface |  | 4.8.2.3.2 | Phase B |  |  | System shall sync user’s testing skill from Henkel skill matrix tool. |  | Interface
complete |  |  | 4.8.2.3.3 |  |  | MARK | skill expiry date out of scope in qclad? Henkel: Out of scope |  | Out Of Scope
complete |  |  | 4.8.3.1 |  |  | SOP | The system shall build a SOP library including description, method version, method ID and other fields. SOP’s shall have version control. | Must
complete | LES |  | 4.8.3.1.1 | Phase B |  |  | System shall support to maintain LES method, including description, method version, method ID. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | LES |  | 4.8.3.1.2 | Phase B |  |  | System shall support version control for LES methods. |  | Standard |  |  |  | 标准功能 | [8 empty] | /
complete |  |  | 4.8.3.1.3 |  |  | Mark | Henkel need to list other fields. Henkel: TF decide the fields required.
complete |  |  | 4.8.3.2 |  |  |  | The system shall have the ability to hold and generate custom calculations | Must
complete | LES |  | 4.8.3.2.1 | Phase B |  |  | System shall be able to maintain custom calculations. |  | Configuration |  |  |  | 配置计算公式 | [8 empty] | /
complete |  |  | 4.8.3.3 |  |  |  | SOP should have an approval process and only one version should be active | Must
complete | LES |  | 4.8.3.3.1 | Phase B |  |  | System shall support to upgrade version after approval. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | LES |  | 4.8.3.3.2 | Phase B |  |  | System shall have only one version active. |  | Standard | [12 empty] | /
complete |  |  | 4.8.4.1 |  |  | Specification management | Support for multi-level Product Specifications, which must align with product SAP setting | Must
complete | Sample |  | 4.8.4.1.1 | Phase A |  |  | System shall support for multi-level Product Specifications. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Interface |  | 4.8.4.1.2 | Phase A |  |  | System shall align MLP data with SAP. |  | Interface
complete |  |  | 4.8.4.2 |  |  |  | For non-standard testing, Version controlled Product Specifications that require approval before activation. | Must
complete | Sample |  | 4.8.4.2.1 | Phase A |  |  | System shall support to add approval plan for non-standard testing MLP, which requires approval before activation. |  | Configuration |  |  |  | 配置审批流 | [8 empty] | 1 | 审批流配置
complete |  |  | 4.8.5.1 |  |  | Stock & Inventory management | Includes information about its characteristics (labels, location, available amount, etc), ordering (supplier, expiry warning, minimum quantity (safety stock) alert, etc), inventory, parameters for use in calculations, etc. Stock in QCLaD, including retain samples, consumables, standards, reagents, instruments, spare parts, etc. The system shall have capability to set and configurate minimum quantity (safety stock). | Must
complete | Stock |  | 4.8.5.1.1 | Phase A |  |  | System shall support stock mangement to maintain informations including characteristics (labels, location, available amount), ordering (supplier, expiry warning, minimum quantity (safety stock) alert), inventory, parameters for use in calculations. |  | Configuration |  |  |  | 配置字段，加到form里 | [8 empty] | 2 | 配置字段、界面
complete | Stock |  | 4.8.5.1.2 | Phase A |  |  | System shall support stock mangement to maintain stock type including retain samples, consumables, standards, reagents, instruments, spare parts. |  | Configuration |  |  |  | 配置字段 | [8 empty] | 2 | 配置类型和工作流
complete |  |  | 4.8.5.1.3 |  |  | Mark | what parameters do we need ro use in calculations? Need to check with Henkel team. HENKEL:The same as 4.8.5.4.
complete | Stock |  | 4.8.5.1.4 | Phase A |  |  | System shall be able to set and configurate minimum quantity in stock mangement. |  | Standard |  |  |  | 标准功能 | [8 empty] | /
complete | Stock |  | 4.8.5.1.5 | Phase A |  |  | System shall be able to set and configurate maximum quantity in stock mangement. |  | Out Of Scope | [12 empty] | 2 | OOO
complete | Stock |  | 4.8.5.1.6 | Phase A |  |  | System shall support to print stock label. |  | Standard |  |  |  | 标准功能 | [8 empty] | /
complete | Stock |  | 4.8.5.1.7 | Phase A |  |  | System shall automatically deduct the stock quantity when consumption. |  | Configuration |  |  |  | 标准功能，如果扫码消耗库存，得开发；如果是原生操作就是标准的 | [8 empty] | 3
complete |  |  | 4.8.5.2 |  |  |  | The system shall provide a way to track the reference materials used (reference materials and stock solutions) to perform the test(s) on sample(s) through the use of barcoding system. | Must
complete | LES |  | 4.8.5.2.1 | Phase B |  |  | System shall allow user to record the reference materials used (reference materials and stock solutions) when performing the tests through barcode. |  | Configuration |  |  |  | 添加字段信息，扫码功能可能需要开发 | [8 empty] | /
complete |  |  | 4.8.5.3 |  |  |  | The system shall provide a way of tracking the storage location of samples stored in QC by providing material, batch information. | Must
complete | Retain |  | 4.8.5.3.1 | Phase A |  |  | System shall allow user to record and retrieve the storage location of samples stored in QC by providing material, batch information. |  | Standard |  |  |  | 自带功能 | [8 empty] | 2 | 留样模块配置
complete |  |  | 4.8.5.4 |  |  |  | The system shall provide a way for users to record the preparation of stock solutions from one (1) or more than one (1) consumable materials within the inventory. These prepared stock solutions will also be uniquely identified by the system and given an expiry date. | Must
complete | LES |  | 4.8.5.4.1 | Phase B |  |  | System shall allow users to prepare stock solutions from one or more consumable materials within the inventory in LES and automatically deduct the consumption and generate a label. |  | Configuration |  |  |  | 配置溶液配制LES | [8 empty] | /
complete | LES |  | 4.8.5.4.2 | Phase B |  |  | System shall be able to maintain an expiry date and uniquely identify for prepared stock solutions. |  | Configuration |  |  |  | LES配置 | [8 empty] | /
|  |  | 4.8.5.4.3 |  |  | Mark | What's meaning of the stock solutions? Henkel: System shall automatically deduct the consumption and generate a label clarify expiration date for the new reagent and also be shown in stock inventory.
complete |  |  | 4.8.5.5 |  |  |  | The system shall provide a way to maintain and view the expiry date record of each consumable material | Must
complete | Stock |  | 4.8.5.5.1 | Phase A |  |  | System shall be able to maintain the expiry date field of stock. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Stock |  | 4.8.5.5.2 | Phase A |  |  | System shall be able to display the expiry date field of stock in folder. |  | Configuration |  |  |  | 配置文件夹 | [8 empty] | 1 | 文件夹配置、权限、按钮
complete |  |  | 4.8.5.6 |  |  |  | Warning for expiry and near to the minimum storage level | Must
complete | Stock |  | 4.8.5.6.1 | Phase A |  |  | System shall be able to warining for expiry stock in folder. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Stock |  | 4.8.5.6.2 | Phase A |  |  | System shall be able to warining for Low amount storage in folder. |  | Standard |  |  |  | 自带功能 | [8 empty] | /
complete | Stock |  | 4.8.5.6.3 | Phase A |  |  | System shall be able to warining for Exceed amount storage in folder. |  | Out Of Scope |  |  |  | 配置字段 | [8 empty] | 3 | OOO
complete |  |  | 4.8.5.6.4 |  |  | MARK | Noted: dragon need maximum amount reminder HENKEL:Reminder for minimum and maximum stock based on the master data. TF added in rtm
complete |  |  | 4.8.5.7 |  |  |  | The system shall provide a way to automatically assign the validation of chemical reference standards/instrument maintenance task to specified user(s). | Must
complete |  |  | 4.8.5.7.1 |  |  | MARK | Is instrument maintenance out of scope ? Henkel:The same as 4.8.1.2.This one should be in scope.
complete | LES |  | 4.8.5.7.2 | Phase A |  |  | System shall create LES tasks for solution preparations automatically when stock is below safety stock or about to expire. |  | Customisation |  |  |  | 配置LES | [8 empty] | 2
complete | LES |  | 4.8.5.7.3 | Phase B |  |  | System shall create LES tasks for instrument maintenance automatically when maintenance date arrives. |  | Configuration |  |  |  | 配置workflow | [8 empty] | /
complete | LES |  | 4.8.5.7.4 | Phase A |  |  | System shall automatically assign the solution preparation LES tasks to specific user. |  | Customisation |  |  |  | 配置workflow | [8 empty] | 3
complete | LES |  | 4.8.5.7.5 | Phase B |  |  | System shall automatically assign the instrument maintenance LES tasks to specific user. |  | Configuration |  |  |  | 配置workflow | [8 empty] | /
complete |  |  | 4.8.5.7.6 |  |  | MARK | automatically assign rule, validation workflow
complete |  |  | 4.8.5.8 |  |  |  | Includes handling and storage precautions, security data, associated hazards and risks and GHS requirement. | Must
complete | Stock |  | 4.8.5.8.1 | Phase A |  |  | System shall support to maintain stock information , including handling and storage precautions, security data, associated hazards and risks and GHS requirement. |  | Configuration | [12 empty] | 3 | 字段配置、文件夹、界面、权限、按钮
complete | Interface |  | 4.8.5.8.2 | Phase A |  |  | System shall sync GHS information form SAP to substance in QCLAD. Refer to 4.5.1.5 |  | Out Of Scope
complete |  |  | 4.9.1 |  |  |  | Security, including audit trails, group and functional security management facilities, password protection of all login accounts. For Electronic Signature support, password checking is required when creating, modifying or deleting electronic records. | Must
complete | Security |  | 4.9.1.1 | Phase A |  |  | System shall support function for security, including audit trails, group and security management, password protection of all login accounts. |  | Standard | [12 empty] | /
complete |  |  | 4.9.1.2 |  |  | MARK | System shall support electronic signature, password checking is required when creating, modifying or removing electronic records. |  | Out Of Scope
complete |  |  | 4.9.2 |  |  |  | The system shall provide multi layered security allowing different user profiles and access privileges. The related access rights to be configured according to the role performed (e.g. system administrator, system user). Individual users may be assigned one or more profiles or individual access rights. | Must
complete | Security |  | 4.9.2.1 | Phase A |  |  | System shall support to configure multiple roles for user to manage permission to profiles and access privileges. |  | Standard | [12 empty] | /
complete | Security |  | 4.9.2.2 | Phase A |  |  | System shall support to maintain different roles. |  | Standard | [12 empty] | /
complete |  |  | 4.9.3 |  |  |  | The system shall provide tools to configure access controls at a dataset level or data group level, to restrict viewing and retrieval access to certain individuals or groups | Must
complete | Security |  | 4.9.3.1 | Phase A |  |  | System shall support configure access controls using role and master menu.(系统通过角色和菜单按钮控制可见权限） |  | Standard | [12 empty] | /
complete |  |  | 4.9.4 |  |  |  | The system must provide unique ID and password authentication processes to confirm and provide traceability to the identity of users. The password must be encrypted or obscured when displayed on screen. This is applicable only for non SSO users | Must
complete | Security |  | 4.9.4.1 | Phase A |  |  | System shall support maintain user account id and password. User id shall be unique. |  | Standard | [12 empty] | /
complete | Security |  | 4.9.4.2 | Phase A |  |  | System shall encrypt or obscured password when displayed on screen. |  | Standard | [12 empty] | /
complete |  |  | 4.9.5 |  |  |  | Single Sign On has to be integrated and used for all users with Henkel user ids. For Henkel operators, they will be accessing application through iPAD with application credentials and password as defined in the above. | Must
complete | Security |  | 4.9.5.1 | Phase A |  |  | System shall support single sign on for all users. |  | Standard | [12 empty] | /
complete |  |  | 4.9.5.2 |  |  | Mark | Henkel user id是想用windows汉高的密码直接登录QCLAD吗？ Henkel: Only for white collar is possible.For blue collar, they need user ID and password for QCLaD
complete | Security |  | 4.9.5.3 | Phase A |  |  | System shall allow user to login through iPad with user id and password. |  | Standard | [12 empty] | /
complete | Security |  | 4.9.5.4 | Phase A |  |  | System shall be able to limit user to login QCLAD using one account for one device or cilent at one time. |  | Standard | [12 empty] | /
complete |  |  | 4.9.5.5 |  |  | MARK | HENKEL: one account login to system in multiple devices at same time may required . Need further discuss internally Henkel:One account for one device or cilent at one time. |  | Standard
complete |  |  | 4.9.6 |  |  |  | User accounts must be suspended after a configurable number of consecutive unsuccessful attempts to enter a password into the QCLAD system until a Security Administrator resets the password | Must
complete | Security |  | 4.9.6.1 | Phase A |  |  | System shall be able to freeze user's account after configurable login failure attempts. |  | Standard | [12 empty] | /
complete | Security |  | 4.9.6.2 | Phase A |  |  | System shall allow specific user to unlock the account or reset the password. |  | Standard | [12 empty] | /
complete |  |  | 4.9.7 |  |  |  | The system shall provide Administrator level account holders with the ability to terminate a user session on the system | Must
complete | Security |  | 4.9.7.1 | Phase A |  |  | System shall support system Administrator to terminate a user session on the system. |  | Configuration |  |  |  | PT功能 | [8 empty] | 2 | 新增功能配置
complete |  |  | 4.9.8 |  |  |  | The system shall provide global admin/user, regional admin/user and site admin/user roles. Each plant should work independently, and their activities, capabilities based on the plant level. | Must
complete | Security |  | 4.9.8.1 | Phase A |  |  | System shall support maintain global admin/user role. |  | Standard | [12 empty] | /
complete | Security |  | 4.9.8.2 | Phase A |  |  | System shall support maintain regional admin/user role. |  | Standard | [12 empty] | /
complete | Security |  | 4.9.8.3 | Phase A |  |  | System shall support maintain site admin/user role. |  | Standard | [12 empty] | /
complete | Security |  | 4.9.8.4 | Phase A |  |  | System shall support to work independently, perform activities, capabilities at plant level. |  | Standard | [12 empty] | /
complete |  |  | 4.9.8.5 |  |  | MARK | 1、TF Give an example of Site permissions division 2、Henkel Provide a list of permissions for a role, such as the permissions and scope of data that the role needs to view/modify; 1、TF 给个Site权限划分的example 2、Henkel 提供角色的权限清单，例如该角色需要查看/修改数据的权限和范围；
|  |  | 4.10.1 |  |  | Project management | • Responsible for project management for all in scope work including qualified project team set up, project schedule, timeline, milestone, deliverables, implementation, cooperation with HENKEL and relevant contractors, etc. • Roles and responsibilities of different parties • Expectations from Henkel has to be defined, documented after agreement between both parties • Requirements to be signed off between both parties • Escalation rule should be clearly defined for global scope. • All communication to plant team strictly with the core team members knowledge. Any other communication without involving core team leads, will not be considered legitimate. • Dragon pilot and global roll out should be managed by same global team with their regional/country counterparts. | Must | Business Proc Only
4.10.1.1
|  |  | 4.10.2 |  |  | Implementation | • Cooperate with HENKEL to analyse, implement and customize the system for HENKEL • Software installation and hardware landscape establishment • Implementation and delivery of a system that fully integrated with Henkel Systems • Assisting HENKEL to establish solution and support technical issue & final configuration, also assisting to establish testing scenarios and user acceptance test • Remedy test problems • Implementation of necessary program changing to fit for purpose work processes and Henkel QCLAD template • System vendor should recommend required hardware type and brand to Henkel based on Henkel local site condition | Must | Business Proc Only
4.10.2.1
|  |  | 4.10.3.1 |  |  | Training | • Initial training to key users for pre-project preparations with a set of training materials | Must | Business Proc Only
4.10.3.1.1
|  |  | 4.10.3.2 |  |  |  | • Training language should be available in English or user preferred local language based on the language preference of the plant to be rolled out. | Must | Business Proc Only
4.10.3.2.1
|  |  | 4.10.4 |  |  | License | • Providing all necessary software licenses • Software license purchased by each party has to be well defined | Must | Business Proc Only
4.10.4.1
|  |  | 4.10.5 |  |  | Post support/Hypercare | • Providing support which detail SLA specified in MA contract • Providing post go-live maintenance and support • Roles and responsibilities of different parties during post Go live, roll out and maintenance. • Hypercare should be conducted after system go live, system vendor should be support 60 man days to make the system running smoothly at Henkel lobal sites. | Must | Business Proc Only
4.10.5.1
|  |  | 4.10.6 |  |  | Project documents | • Providing all relevant documentations with document categorise detailed • Provide system user manual in English and Henkel site local language | Must | Business Proc Only
4.10.6.1
4.11.1
| Dashboard |  | 4.11.1.1 | Phase A |  |  | 需要有两个仪表盘，一个为带有过滤条件的静态仪表盘，一个是默认条件但是定时刷新的动态仪表盘；两个仪表盘中显示的内容一致 Two dashboards are required, a static dashboard with filtered conditions and a dynamic dashboard with default conditions with timed refreshes; the content displayed in both dashboards is the same |  | Customisation | [12 empty] | 2
| Dashboard |  | 4.11.1.2 | Phase A |  |  | 带有过滤条件的静态仪表盘的过滤条件为：plant, work center, business team(group) The static dashboard with filters has the following filters:plant, work center, business team(group) |  | Customisation | [12 empty] | 1
| Dashboard |  | 4.11.1.3 | Phase A |  |  | 默认条件的动态仪表盘的过滤条件为：当前登录人员所在的plant, work center, business team(group) Dynamic dashboards with default conditions are filtered by plant, work centre, business team(group) where the currently logged in person is located. |  | Customisation | [12 empty] | 1
| Dashboard |  | 4.11.1.4 | Phase A |  |  | 仪表盘中需显示：Date of the day、of that day, the lists of on-duty operators, only showing the operator ID The dashboard shall display: Date of the day, of that day, the lists of on-duty operators, only showing the operator ID |  | Customisation | [12 empty] | 1
| Dashboard |  | 4.11.1.5 | Phase A |  |  | 仪表盘中需显示：of the criteria, the statistic of all the tasks ： 当天收样但未审核完成的样品数量 当天之前收样但未审核完成的样品数量 测试已完成的样品数量completed 测试中的样品数量in-testing 未开始的样品数量not started the count of delayed sample the count of urgent sample The dashboard shall display: of the criteria, the statistic of all the tasks : Count of samples received on the same day that were not reviewed and completed Count of samples received prior to the day that were not audited and completed Count of samples completed Count of samples in-testing Count of not started Count of delayed sample Count of urgent sample |  | Customisation | [12 empty] | 3
| Dashboard |  | 4.11.1.6 | Phase A |  |  | 仪表盘中需显示：the list of delayed sample The dashboard shall display: list of delayed sample |  | Customisation | [12 empty] | 1
| Dashboard |  | 4.11.1.7 | Phase A |  |  | 仪表盘中需显示：the list of urgent sample The dashboard shall display: list of urgent sample |  | Customisation | [12 empty] | 1
| Dashboard |  | 4.11.1.8 | Phase A |  |  | 仪表盘中需显示：the column chart in which x axis has the Sample Count, and y axis has the product line.且柱状图中按照样品状态（未开始，测试中，测试已完成）分颜色显示 The dashboard shall display:the column chart in which x axis has the Sample Count, and y axis has the product line. and the column chart is coloured according to the status of the samples (Not Started, Test in Progress, Test Completed). |  | Customisation | [12 empty] | 3
| Dashboard |  | 4.11.1.9 | Phase A |  |  | 仪表盘中需显示：anotther column chart in which x axis has the Sample Count, and y axis has the inspection type (IQC, OQC, IPQC)，且柱状图中按照样品状态（未开始，测试中，测试已完成）分颜色显示 The dashboard shall display: anotther column chart in which x axis has the Sample Count, and y axis has the inspection type (IQC, OQC, IPQC), and the column chart should be colour-coded according to the sample status (Not Started, Test in Progress, Test Completed). |  | Customisation | [12 empty] | 3
Note on D7: This is colmun is typically used to refer to the URS or RFP requirement number
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It should be used also for standard testing. Ex: Truck RM, 903 - IPQC, non MES plants. Need a configuration to identify these scenarios
Note on H13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: System shall be able to create sample based on events scheduled within QCLAD
Note on H14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Which has an inspection lot(automatic)
Note on H24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Date and time
Note on H26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to add a mandatory comment for the cancellation.
Note on H29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Do we need to mention some examples of configurable attributes to ensure both teams are on same page? Reply: Thermofisher will provide the details for henkel to choose
Note on H37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Provision for traceability of split samples with a parent sample should be available
Note on H41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be access driven, only specific users with right roles can create or modify
Note on H43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: If the test is failed and need to retest - Based on the sample number, multiple inspection points to be created in SAP for all standard testing flows. This is to record all failure as well as success of parameters in SAP.
Note on J45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Why is this item customisation as it is standard functionality Reply: All with interface is customisation for us
Note on H49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Specification limit to be pulled from SAP inspection plan
Note on H57: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It can be barcode or QRCode
Note on H67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It is the same thing with non-routine testing raised by non-QCLaD users.
Note on H68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sample receipt and test as per the workflow. Sample receipt will start with label scanning.
Note on H70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What all attributes can be modified should be configurable and access driven.
Note on H77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For RM, in case CoA data already available in SAP inspection lot, the details should be displayed even if the data entry is not required in QCLAD Reply: Details: Data recorded within inspection lot, MIC, Spec, Test result
Note on H81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The instructions of calculations, lab instruments to be pulled from SOP. Reply: Approved by Thermofisher 2024/06/18
Note on H92: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Multiple test, samples can be from different materials, material types(Raw material, Semi finished goods, finished goods) Reply: Approved by Thermofisher 2024/06/18
Note on H96: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Only for active samples.
Note on H99: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What data to be captured need to be aligned with Henkel team Reply: Need more discussion
Note on H115: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test method
Note on H118: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need to record the information who/what/when changed for audit purpose
Note on H123: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Recording one result should be 1 user responsibility but test can be started by one person and continued by another person. Reply: Confimed with Thermofisher 2024/06/18
Note on H132: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Peer review should be configurable at material group level Reply: There should be configurable option.
Note on H148: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Return to tester - reviewer should be able to select the operator and sample status have to be changed back to test status
Note on H173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Loading of reports should be in seconds. If user selects a range which will take time system should give warning of response time so that user can change the date range or wait for the delay
Note on H181: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Or store the file in a configurable shared drive Reply: Manually or automatically Reply: Automatically to a sharefolder
Note on H300: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: For Type C and type D only manual entry. It should also override the results recorded from Type A and Type B in case there are any issues in data capture.
Note on H303: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: what is export readable file? Reply: That means readable files generated by Type B instrument software should be exported to QCLaD for test result Reply: If Type B instrument can generate a file, the integration should be possible. For Type A, there wont be any file
Note on H315: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: System shall display standard cycle time, operator id who is performing the task, items consumed in the test process and its quantity. We also need to check whether it is possible to get actual cycle time of sample testing. Reply: For cycle time of test under MIC level, the system should be able to compare standard cycle time to actual cycle time. Reply: Update
Note on H325: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should be "click and view" the hyperlink as hyperlink url to be added in master data as part of SOP/workflow. Reply: Updated
Note on H328: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: System should allow scanning of labels or QR code from iPAD or tablet. Reply: Ipad cannot scan label or QR directly, need a tablet with a scanning camera. Reply: What they mention tablet is a Ipad slightly bigger than the normal one for better handling and it has the scanning function. Henkel need to understand whether we can utilize the existing Ipads and scanning guns to realize the operation of QCLaD.
Note on H338: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: what does remote location means? Reply: Maybe refer to client? Reply: This is what we want to confirm with you . Our understanding is system support remote operation Reply: Confirmed, the sample entry and test instrument may not be in the same room.
Note on H364: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We need to maintain a flag in material master data to identify whether the material result is captured by Ecoa or not. If yes, we only to display the results in SAP inspection lot. If no, the manual entry of SAP inspection result is required. Reply: conifrmed
Note on H483: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Specification and parameters have to be maintained in equipment master data whereas the details of spare parts, calibration and maintenance requirements to be available in their respective SOPs. Reply: Update
Note on H492: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Instrument is out of scope in alerting users of expiry Reply: Yes，update
Note on H494: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: System should not allow the user to take a testing task if the operator is not qualified Reply: Agreed. Reply: Update
Note on H501: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The fields for master data to be agreed by both teams Reply: Agree
Note on H509: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: User's training module should be a part of OSDP. It is out of scope based on our pre-alignment with Anson
Note on H517: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do we need to mention where all the custom calculations are required? Reply: Custom calculations means there are some intermediate result for some tests. The final result should be calculated according to the intermediate results and a configurable formula. Reply: We will reach an agreement during implementation.
Note on H521: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: what is multi level product specification? Do we need to mention the details? Reply: Like internal spec for Summer and spec for winter. Reply: We can omit multi-level product specification part.
Note on H530: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: do we also need maximum quantity? Reply: Yes, for flammable and explosive reagents Reply: TF need to add maximum part also Reply: update
Note on H537: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The understanding, by giving the material and batch, we should be able to retrieve the storage location for consumables, retain sample Reply: Exactly Reply: update
Note on H541: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Stock solution is an intermediate solution created from two or more consumables Reply: Yes
Note on H554: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: what is the basis of automatic assignment? Reply: Can be found in task list Reply: Solution preparation will also be maintained in skill matrix.
Note on H555: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: need to add the maintenance of instruments in OSDP as one skill. This should be available for each equipment
Note on H558: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: GHS information to be pulled from SAP system Reply: update

## Definition
Field | Value | Description
Type | Standard | Population a record with values eg user roles, instruments, configuration times, login template
Type | Configure | Altering the functionality of the standard product using in built tools e.g. Forms Designer, Workflow, new teables / fields
Type | Extension | Extending the functionality of the standard produce with a service module / customer specific coding (C#, VGL) using the available triggers
Type | Customise | Altering functionality of the standard product using programming tools e.g. c# in a supportable way as enabled by the SampleManager product architecture | Note: Where the type is out of scope it means that there is no additional effort for Thermo Fisher, if the priority is won't then already agreed requirement is not needed by BRB, if Must, Should or Could the functionality already exists or else the effort will be with QLD DAF.
Type | Out of scope | This is outside of the scope of the project effort to be delivered by ThermoFisher resource
Priority | Wont | Will not be included in the project
Priority | Should | Recommended to include in the scope
Priority | Could | Could be included if business benefit is justified
Priority | Must | Must be in scope as agree by BRG or existing functionality to be replicated/maintained

## Revision History
Document Identifier: |  |  | #REF!
Revision History
Version | Date | Revised By | Description of Changes | Reason for Change

## Guidelines
Guidelines for Requirements Trace Matrix (RTM)
This Guidelines Worksheet can be removed from working copies of the RTM if desired
Introduction
The RTM is a key document in the delivery phase of the Global Methodology. It can be used as a tool for a variety of purposes including project management and validation. Primarily and simply the RTM is a spreadsheet that lists the user requirements and matches them to the proposed solutions.
According to GAMP4 the Functional Specification (FS) defines the system to meet the users needs as defined in a User Requirements Specification (URS). This RTM can act as a FS insomuch as user requirements can be directly linked to Configuration or Design Specification references
References
Ref. No. | Reference |  | Document
1 | GAMP4 Guide for Validation of Automated Systems (2001) |  | GAMP Guidelines for FS
2 | P/GL/ELEC/INTERNAL/METHODOLOGY/GUIDELINES/ SER-GLP-G005 - Document presentation guidelines |  | Document presentation guidelines
3 | P/GL/ELEC/INTERNAL/METHODOLOGY/TEMPLATES/ Functional Spec Template |  | FS document template.
Guidelines
Document Information
Fields are provided at the top right hand corner of the spreadsheet to record information about the document, namely:
Document Ref - Electronic file reference for the document
Version: Each version of the RTM should be numbered according to the Global methodology guidelines [Ref. 2]
Date: Each version should be dated in the format specified by the Global methodology (DD-MMM-YYYY)
Columns
This template has a number of pre-defined column headers set-up which are described in the table below. Three of these column headers are manditory namely: - Requirement Number (Req. No.) - Requirement - Design Specification Reference (if being used for validation purposes)
The other columns are optional and can be adapted or removed as suits the project being carried out. In the same vein additional columns may be added (eg Test Script Reference, Product Functional Spec Reference, Responsible Person etc).
The most important thing about the RTM is that it is a working document and can be used for different purposes throughout the course of a project. As such it is bound to change and should always be adapted to fit the needs of the customer and the particular project being carried out.
| Column | Description
| Req. No. (manditory) | Each requirement must be assigned a unique reference number. It is recommended to us a straigtforward incremented number rather than some complex scheme (requirements can always be found using the search and filter facilities of the spreadsheet). New requirements should be added to the end of the list. Additional columns may be added to cross reference to other numbering schemes (as maybe used in the URS)
| Functional Area / Workshop | This column can be used to group requirements together into related areas (functional or workflow) or into groups for dicussion at relevant workshops
| Requirement (manditory) | A short description of the requirement. It should be in sufficient detail to provide an understanding of the requirement, but at high enough level to preclude 'designing' a solution
| Priority | Requirements should be prioritised with the users. The recommended method is to utilise MoSCoW prioritisation (Must, Should, Could, Won't)
| Type | A classification of the type of solution proposed to meet the requirement. These can provide the basis for project estimation and planning. Typical values for software based solutions will be: - Standard - Configuration - Extension - Customisation - Interface Other values for non-software based solutions could be: - Business process only - Change business process - Out of Scope / Later Phase - Link (to another requirement)
| X-Ref | Cross reference to a duplicate or closely related requirement
| Include | This column can be used to flag if a requirement is to be included or excluded
| Design Ideas | This column is used to record design ideas or approaches to meet the requirment based on the type classification as discussed during any workshops. It should be a short description sufficient to allow prototyping.
| Fields Tables | List of any new or modified database tables or fields required to configure the system to address the requirement
| Complexity | An estimate of the complexity of any particular configuration, extension or customisation solution. This may be limited to Hi/Med/Low or be more descriptive (eg Complex Invasive, Simple Invasive, Complex External etc.)
| P/Type | Label for prototype phase in which the proposed solution is prototyped (typical values PT1, PT2 etc)
| Addresses Requirement | Does the prototype solution address the requirement (Y/N). This needs to be jointly agreed with the users
| Design Conclusion | A summary of the final design proposal following any prototype assessment
| Design Spec Ref. (mandatory) | Reference to appropriate Design Specification or Configuration Specification documents.
| Test Script Ref. | Reference to appropriate test script or user acceptance test.
| Expanded Details | Space for extra detail on the requirement or the solution. This column can be used to link to additional worksheets if necessary.
| Estimate | Used for project planning purposes