## Henkel - RACI Matrix
| The person who does something as part of their job or role to do a specific task or activity. The person who is expected to justify actions taken or decisions made to deliver the completed task or activity. Groups or people whose opinions are sought by the person responsible for the task or activity. Those groups or people that should be kept up-to-date on progress with the task or activity. | Wendy -PM | Hongtao - TL | Zhenjuan -TL | Test Team | Shravan - GPM | Nishi - PMO | Shuang - SL | Xiang - Director | Project Manager | SME / Product Owner | Test Team | Global PM | PMO
| Project Activity | Thermo Fisher Team | [7 empty] | Henkel Team
SN | Phase A & B
1 | Project Management | R | C | C | I | C | I | A | I | R | C |  | I | I
2 | Communication to Leadership | C | I | C | I | R | I | A | I | A | I |  | R | I
3 | Raise Change Request | R | C | C | I | I | C | A | I | A | C |  | I | I
4 | Change Request Approval | A | I | I | I | I | R | C | I | I | I |  | I | A
5 | Workshop and RTM | A | R | C | I | C | I | C | I | A | R |  | I | I
6 | Design and Development | A | R | C | I | I | I | I | I | A | C |  | I | I
7 | Static Data | A | R | C | I | I | I | I | I | A | R |  | I | I
8 | Installation Package creation | C | R | C | I | I | I | I | I | A | I |  | I | I
9 | Managing China Resources | C | R | I | I | I | C | A | I | R
10 | Create and Manage Schedule | R | A | C | I | I | I | I | I | R | I |  | I | I
11 | Create Status Report | A | R | C | I | C | I | C | I | A | I |  | I | I
12 | Running PSC meetings | C | C | C | I | C | C | R | A | R | C |  | I | I
13 | Collaboration with Global Team | C | C | C | I | R | A | C | I | A | I |  | I | R
14 | SIT | A | C | C | R | I | I | I | I | A | C | R | I | I
15 | UAT | A | C | C | C | I | I | I | I | A | R | R | I | I
16 | Go Live | A | R | C | C | I | I | I | I | A | R | R | I | I
17 | Hypercare | A | R | C | C | I | I | I | I | A | R | C | I | I
18 | Documentation | A | R | C | C | I | I | I | I | A | R | R | I | I
Phase B
19 | Enhancement Request | C | C | C | C | I | I | I | I | A | R | I | I | I
20 | Request approval | R | C | C | I | I | I | I | I | A | I | I | I | R
3 | Design and Development | A | R | C | I | I | I |  |  | A | C | I | I | I
21 | Daily Standup and Manage | A | R | C | I | I | I | I | I | I | I | I | I | I
22 | Sprint Planning and manage | R | A | C | I | I | I | I | I | A | R | I | I | I
23 | Sprint Review and confirmation | A | R | C | I | I | I | I | I | A | R | I | I | I
24 | Testing | A | C | C | R | I | I | I | I | I | C | R | I | I
25 | Documentation | A | R | C | C | I | I | I | I | A | R | C | I | I