## Slide 1: HENKEL AG & Co. KGaA QCLAD Kickoff
Henkel and Thermo Fisher Team
3 - 7 Jun 2024

## Slide 2
HENKEL AG & Co. KGaA
Anson Alexander - Quality Regional Head, APAC
Szymon Bilski - Head QM/MMA/PTP A
Maline Sun - Quality Head, GCN
Lisa Zhou - Plant Quality Head
Neelima Rajesh - Global Project Manager
Joana Cavalheiro Gomes - Global QC Governance Lead
Melvin Ang - Business Value Owner
Frank Shen - Project Manager
David Li - Project Lead APAC
Samanta Zhang - Plant Dx Lead
Joanna Wang - Lab Quality Head
Tony Zhuang - Lab Quality Head
Akshay Gaikwad - Quality SME, India
Eagle Wang - Digital projects coordinator, Dragon
2
Proprietary & Confidential | 03 Jun 2024
Notes: Need to confirm with Henkel

## Slide 3
Thermo Fisher Scientific
Tracy Bohm - Commercial Sales Director APJ
Wu Xiang - APAC Service Director
Liu Ye - Sr Business Manager
Zhang Hanwen - Strategic Marketing Manager
Zheng Meng - Key account manager
Liang Shuang - China service manager
Nishi Kozhikkalathil - APAC PMO
Shravan Tiwari - Global PM
Huo Hanni (Wendy) - Project manager
Qiu Hongtao - Technical Lead
Gu Cheng - Consultant
Xiao Mengran - Consultant
Zhang Zhenjuan - Technical lead
Niu Zhao - Support Lead
3
Proprietary & Confidential | 03 Jun 2024

## Slide 4: Project Organization HENKEL
  Bjoern Jackisch (AO)
  Marie Christine Martinez (AOQ)
  Nick Meisen (AOD)
  Jaume Cornellana(Dx)
Steering Committee
  Neelima Rajesh (Global PM)
  Frank Shen ( PM)
  David Li (APAC)
Project Management
  Plant Quality Team
  Lisa Zhou
  Tony Zhuang
  Joanna Wang
Workstream 1
  Quality COE & Cross Regional SME
  Alexis Metz
  Katja
  Akshay Gaikwad
Workstream 3
  Dx Team
  Samanta Zhang (Plant network)
  Ashu Singh (SAP)
  Asbjørn (Cloud)
  TBD
Workstream 2
Project Core Team
  SME’s
  Dx Team
  Yenli Khor (SAP QM)
  Kun Zhang (SFS)
  Avinash Nirgude (OSDP)
  Mirko Feisel (SAP CPI)
  SME’s
  Eagle Wang
Extended Team
  Anson Alexander (AOQ)
  Maline Sun (AOQ)
  Melvin Ang (AOD)
  Szymon Bliski (Dx)
Project Management Office (PMO)
  Jona C Gomes
  Neelima Rajesh
Product Governance
  Savita (SFS)
  Arun Gopal (OSDP)
3rd party vendors
4
Proprietary & Confidential | 03 Jun 2024

## Slide 5: Project Governance Structure
Technical Support Lead
Nicole Niu
Consultant Team
Lead: Qiu Hongtao
Gu Cheng
Xiao Mengran
Implementation Team
Lead: Zhang Zhenjuan
Lead：Rakssha Ramesh
Akhil Prabhakaran
Amritha Baskar
Training Team
Li Li Zhang
Infrastructure Architect
Jason Ji
Services Manager
Shuang Liang
Support Team
Steven Shi
PM
Wendy Huo
Global Technical Advisors
Don Ross
Simon Bolder
Global PM
Shravan Tiwari
Global PMO
(Thermo Fisher)
Service Director APAC
Xiang Wu
Notes: Shuang

## Slide 6
Escalation Plan
Project team (Henkel, Thermo Fisher)
----------------------------------------------------------------
Henkel: Lisa Zhou, Tony Zhuang, Joanna Wang, Frank Shen, Neelima Rajesh
Thermo Fisher : Qiu Hongtao, Wendy Huo, Gu Cheng, Xiao Mengran, Zhang Zhenjuan
Core project team + Henkel PMs + Thermo Fisher PMs
-----------------------------------------------------------
Henkel: Anson Alexander, Maline Sun, Szymon Bilski, Neelima Rajesh, Joana C Gomes, Lisa Zhou, Melvin Ang
Thermo Fisher : Wu Xiang, Tracy Bohm, Christian Mueller
Henkel sponsors + Thermo Fisher Country Leader & PMO
-----------------------------------------------------------
Henkel: Henkel: Anson Alexander, Maline Sun, Szymon Bliski, Melvin Ang, Neelima Rajesh
Thermo Fisher : Liang Shuang, Nishi Kozhikkalathil
Henkel sponsors, Stakeholders (AO, DX) + Thermo Fisher Directors
-----------------------------------------------------------
Henkel: Xiawei Wang, Nick Miesen, Jaume Cornellana
Thermo Fisher : Xiang Wu
Henkel stakeholders + Thermo Fisher Sr. Directors
-----------------------------------------------------------
Henkel: Bjoern Jackish and Thorsten Camin
Thermo Fisher : Devendra Deshmukh
Weekly Meeting
Steering Committee Meeting
Escalation Level 1
Escalation Level 2
Escalation Level 3
Notes: Shuang

## Slide 7
Sample Management
  Sample whole lifecycle
  Non-Routine Test
Lab Execution System
  CoA creation
Interface Integration
Master data sync
SAP – Phase A
Smart factory – Phase B
Skill Matrix (OSDP) – Phase B
Instrument integration (Type A & Type B) – Phase A & B
  Daily test operation workflow execution
  QC Lab SOP/test method execution
  Calculation & data processing
Project Scope
Report Dashboard
Sample status summary
Instrument load, sample workload statistics
Lab Management
KPI monitoring
Sample Scheduler
Pre-task/test scheduled before sample arrived
Manual/Automatic task/resource arrangement
Resource & Inventory Maintenance
Instrument Maintenance
Consumables
Notes: Shuang

## Slide 8: Project Phases
Pilot Phase A
*Specific functionality for Phase A
Pilot Phase B
Phase 1
*Specific functionality for Phase B
Phase 2
*Implement LIMS within first to 6 months
*Target to deploy in all (4) Labs in Dragon site
*All these functions can be used by all Labs
*Implement within 5 months
*Configure and deploy rest of the enhancements as multiple sprint releases for the all (4) Labs in Dragon site.
* Additional labs static data will be managed by Henkel
Extend Dragon rollout to global sites.
Management and delivery via Global Team from Henkel and Thermo Fisher
Notes: Wendy

## Slide 9: Project RACI Matrix
 | The person who does something as part of their job or role to do a specific task or activity. The person who is expected to justify actions taken or decisions made to deliver the completed task or activity. Groups or people whose opinions are sought by the person responsible for the task or activity. Those groups or people that should be kept up-to-date on progress with the task or activity. | Wendy -PM | Hongtao - TL | Zhenjuan -TL | Test Team | Shravan - GPM | Nishi - PMO | Shuang - SL | Xiang - Director | Project Manager | SME / Product Owner | Test Team | Global PM | PMO
 | Project Activity | Thermo Fisher Team |  |  |  |  |  |  |  | Henkel Team |  |  |  | 
SN | Phase A & B |  |  |  |  |  |  |  |  |  |  |  |  | 
1 | Project Management | R | C | C | I | C | I | A | I | R | C |  | I | I
2 | Communication to Leadership | C | I | C | I | R | I | A | I | A | I |  | R | I
3 | Raise Change Request | R | C | C | I | I | C | A | I | A | C |  | I | I
4 | Change Request Approval | A | I | I | I | I | R | C | I | I | I |  | I | A
5 | Workshop and RTM | A | R | C | I | C | I | C | I | A | R |  | I | I
6 | Design and Development | A | R | C | I | I | I | I | I | A | C |  | I | I
7 | Static Data | A | R | C | I | I | I | I | I | A | R |  | I | I
8 | Installation Package creation | C | R | C | I | I | I | I | I | A | I |  | I | I
9 | Managing China Resources | C | R | I | I | I | C | A | I | R |  |  |  | 
10 | Create and Manage Schedule | R | A | C | I | I | I | I | I | R | I |  | I | I
11 | Create Status Report | A | R | C | I | C | I | C | I | A | I |  | I | I
12 | Running PSC meetings | C | C | C | I | C | C | R | A | R | C |  | I | I
13 | Collaboration with Global Team | C | C | C | I | R | A | C | I | A | I |  | I | R
14 | SIT | A | C | C | R | I | I | I | I | A | C | R | I | I
15 | UAT | A | C | C | C | I | I | I | I | A | R | R | I | I
16 | Go Live | A | R | C | C | I | I | I | I | A | R | R | I | I
17 | Hypercare | A | R | C | C | I | I | I | I | A | R | C | I | I
18 | Documentation | A | R | C | C | I | I | I | I | A | R | R | I | I
19 | Enhancement Request | C | C | C | C | I | I | I | I | A | R | I | I | I
20 | Request approval | R | C | C | I | I | I | I | I | A | I | I | I | R
21 | Daily Standup and Manage | A | R | C | I | I | I | I | I | I | I | I | I | I
22 | Sprint Planning and manage | R | A | C | I | I | I | I | I | A | R | I | I | I
23 | Sprint Review and confirmation | A | R | C | I | I | I | I | I | A | R | I | I | I
24 | Testing | A | C | C | R | I | I | I | I | I | C | R | I | I
25 | Documentation | A | R | C | C | I | I | I | I | A | R | C | I | I
Notes: Wendy

## Slide 10: Project Timeline
Training – Data Configuration, LIMS Admin, Workflows, Report Designer
UAT
June
July
Aug
Sep
Oct
Nov
Dec
Jan
Feb
Mar
Kick Off
Go Live
Configuration and SIT
Dev Server Readiness
Hypercare
Static Data load assistance
Other project documentation
Apr
Workshop
Phase A
Phase B
FRS
All Phases
Configuration , Testing and deployment using Sprint methodology
UAT Server Readiness
Prod Server
Readiness

## Slide 11: Project Implementation Process
Thermo
Henkel
Key users
50%
Key users
100%
Kickoff
Training/Demo
Requirements Gathering
Installation/Configuration/
Dev（PPA）
Basic data entry
SIT
Training
Go Live
Both parties
Key users 10%
Key users 100%
End user 30%
1.25 months
3.5 months
1 month
Project Plan
RTM
CS1.0
FS1.0
User Manual 1.0
Acceptance Agreement
UAT
Basic data entry
Configuration/Dev
(PPB）
CS2.0
FS2.0
User Manual 2.0
UAT Support
Key users
100%
Key users 100%
Key users : Members from each lab who are well versed in the business workflows, IT Admin, and Product Owner.
Deployment
Test
Go Live Hypercare
2 months
4.25 months
All users
100%
Acceptance
All users
100%
UAT Preparation
11

## Slide 12: Requirement Gathering Approach and Timeline
Approach:
  Discuss workflows and specific URS Items (sampling scheduler) as part of kickoff workshop for 2.5 days. Try to identify other items related to the workflows in the URS and mark them with appropriate status to track and follow-up.
  Add the requirement details in the RTM document (existing draft version) and referencing to the URS items.
  Mark status as complete for the confirmed requirements in the RTM document.
  Any parked items will be marked as TBD (to be discussed) and listed in another document for follow up. This will be responsibility for both the teams.
  Action items will be maintained and communicated to the both the teams.
Timeline:
  Confirm 95% of the workflows and sampling scheduler URS items by 7th June.
  Confirm the gaps in requirements and efforts based on the modules within one week of time.
  Follow up with Henkel team for detailed requirement gathering for the remaining requirements for other modules within one month of time.
  Perform gap analysis for the requirements, efforts and discuss with the Henkel team by end of July.
  Signoff the requirement trace matrix (RTM) by end of July.
Language:
  English
Notes: Wendy

## Slide 13: Project Execution Methodology and Tools
Waterfall for Pilot Phase A
Requirement gathering for Pilot phase A and B with Dragon and Global team
Design and Implementation
SIT and UAT
Go live and post go live support
Hybrid Agile for Pilot Phase B
Sprints will commence after the Requirement finalization
Sprint Planning - review of the product backlog & Sprint Backlog
Daily Scrum - Summarize focus and goals
Sprint Review – presentation/ demonstration of completed work
Sprint Retrospective – for continual improvement
Henkel's DevOps will be used to manage Epics and Story points

## Slide 14: Key Challenges
No. | Description | Mitigation | Responsibility
1 | Excessive customization requirements | Strictly control the number of customization requests. Explore reasonable overall requirements that can accommodate both local and group needs. | Thermo Fisher + Henkel
2 | Communication challenges between local and global group teams | Establish effective communication mechanisms to facilitate smooth communication between local and group teams. | Thermo Fisher + Henkel
3 | After the requirements finalization, the project scope may experience periodic changes due to new change requests | Provide detailed and comprehensive requirements descriptions. the requirement gathering phase will be divided into modules and confirmed separately, one module at a time. | Thermo Fisher + Henkel
4 | Frequent adjustments to project work have a negative impact on the quality of deliverables | Detailed evaluations need to be conducted for all changes in project progress. | Thermo Fisher + Henkel
5 | In order to meet the deadline for the Go Live, testing was rushed, which ultimately affected the quality | After both project managers have confirmed the impact, it is necessary to submit the decision to the project management for approval. | Thermo Fisher + Henkel
6 | Changes and deviations have occurred during the testing phase | Deviations need to be tracked and reported in real-time based on the level of involvement | Thermo Fisher + Henkel
7 | The quality of static data collection varies significantly | User resources need to be confirmed in advance | Thermo Fisher + Henkel
8 | The workload on key resources which will create a bottleneck | Clear roles and responsibilities need to be assigned to business administrators and key users | Thermo Fisher + Henkel
9 | Document review and approval cycle and time resulted in project delays | Follow shared document approach, changing linear review to simultaneous multi-person review, to save time, and an agreed review cycle | Henkel
Proprietary & Confidential | 03 Jun 2024
Notes: Wendy

## Slide 15: Communication Plan – Pilot Phase A
Event | Sponsor | Participants | Frequency | Deliverables
Weekly Meeting (EN/CN) | Project manager | Core project team from both parties | Weekly | Meeting minutes with roadblocks, dependencies and action items.
Milestones Initiation and Achievement (EN/CN) | Project manager | Core project team from both parties (involvement of supervisors/leadership when required) | Milestone basis | Milestone summary notes email to all stakeholders
Project Steering Committee Meeting (EN) | Project manager | PSC members | Monthly | PSC deck with progress summary, decisions, issues and risks, approval, and strategic alignment
Technical/Business Solution Discussion (EN/CN) | Consultant lead/Technical lead | Technical members (to be arranged according to the actual business needs) | On adhoc basis | Record meeting discussions
Other (EN/CN) | Corresponding person in charge | To be arranged according to actual business needs | On adhoc basis | Record meeting discussions
Notes: Shravan

## Slide 16: Communication Plan – Pilot Phase B
Event | Participants | Frequency | Deliverables
Sprint Planning (EN/CN) | Project Team members | Every Sprint Start | Sprint Backlog & Sprint plan
Team Standup (EN/CN) | Project Team members | Daily | Task progress updates, roadblocks, what next
Sprint Review (EN/CN) | Project Team members | Every Sprint Completion | Demonstrated User Stories & Incremental Progress & Updated Product Backlog
Sprint Retrospective (EN/CN) | Project Team members | Post Sprint Completion | Lessons Learned - What went well, What needs improvement
Project Steering Committee Meeting (EN) | PSC members | On adhoc basis | PSC deck with progress summary, decisions, issues and risks, approval, and strategic alignment
Technical/Business Solution Discussion (EN/CN) | Project team members as needed | On adhoc basis | Record meeting discussions
Notes: Shravan

## Slide 17: Global PM and PMO Alignment
Global PM
Shravan
China PM
Wendy
EMEA PMO
Giovanni
Germany PM
Qingyang
APAC PMO
Nishi
Central point of contact for all the project global stakeholders across all regions.
Bi-Weekly review with internal project manager on resources, roadblocks and dependencies for Pilot Phase.
Assisting team for monthly progress update and feedback between Henkel and Themo Fisher team.
PMO provides feedback to make sure that reasonable controls such as QMS processes are in place for the project effort, deliverables, quality and timeline.
Notes: Shravan and Nishi

## Slide 18
Documents for the project
RTM – Requirements Traceability Matrix
Functional Specification
Configuration Summary
User Guidance Manual for Sample Manager – Standard document
Instrument connection repository
18

## Slide 19
Lab Walk Through
19

## Slide 20
SampleManager Training (Data Configuration)
20

## Slide 21: Sample Manager Demo/Training
Data Structure
Sample Process Demo (IPQC)
Schedule Sample
Sample Storage and Retention
21

## Slide 22
22

## Slide 23: Sample Manager Demo/Training
Stock Management (Inventory)
Instrument Management
Security and Access Management
23

## Slide 24
24

## Slide 25: Requirement Workshop
25

## Slide 26: Requirement Clarification & Workflow Finalization
No | Main Workflow Items
1 | Standard Raw Material (RM) testing for incoming
2 | Standard in process testing for semi finished and finished goods
3 | Standard finished goods outgoing test.
4 | Consumables incoming test.
5 | Package material incoming test (Note: Dragon package material has IDH#, no batch# manage in SAP)
6 | Instrument calibration sample test
Group A: Garen, Mengran
26

## Slide 27: Requirement Clarification & Workflow Finalization
No | Main workflow Item
1 | Test for MSA
2 | Certification test for QC technician
3 | Test for SCMS/NCMR /CCMS investigation (Based on SCMS, NCMR, CCMS type) Note: SCMS: supplier complaint management system; NCMR: nonconformance management system; CCMS: customer complaint management system
4 | Test for NCMR-self life extension (RM, SFG, FG, Package material, consumable & Instrument calibration sample)
5 | Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project (Including, Stability studies (shelf-life study, aging test, reliability test, etc.))
No | Support Workflow
1 | Moving sample/material to storage location
2 | Perform skip lot testing (configure by user)
Group B: Hongtao, Cheng
27

## Slide 28: Requirements Gathering on URS
Sampling Scheduler
  Pilot Phase A: Shift management
  Pilot Phase B: Scheduler
Summary for workshop and next plan
URS gap review
28

## Slide 29: Workshop Deliverables
Draft version of RTM
Confirmation of the requirement topics discussed during kick off workshop
Agreement on Project Governance by both parties
  Project Management Plan (not standard format to be decided later, high-level milestone plan with goals and responsibilities )
Detailed requirement gathering plan
Kickoff deck
Issues (parked items, action items) log
Workshop summary notes
29

## Slide 30: Next Action
30
Detailed requirement gathering
Gap Analysis
Project plan with detailed items
Preparation items ready by Henkel
  On-boarding Thermo Fisher members
  Infrastructure ready such as Dev server, VPN, and remote connection, DevOps etc.
RTM Completion and Sign off
Sign off the FRS 1.0 completion and signoff

## Slide 31
31