## Sheet1
No | Date | Start Date | End Date | Days | Modules | Research Content | Notes | Participants | Deviation record
1 | First Week 2024.06.11-2024.06.14 | 2024.06.11 | 2024.06.11 | 1 | getting the problem ready |  |  | TF |  | Tuesday send out the topics and the key users expectation Every Tuesday come to Dragon (next Wedenesday) Every Week send out the RTM
|  | 2024.06.12 | 2024.06.12 | 1 | 4.1Sample Management | Basic business research Sample Login/Sample Receipt Reference the corresponding workflow Sample Testing/Results Entry Authorization Reference the corresponding workflow Reporting Henkel Sample Type Non-testing work requirements Special testing requirement management | inspection types, numbering rules, etc; Creation of the request inspection form, sample receiving, sample inventory and management. Assignment of inspection tasks, completion of result forms, result review, etc. Report preparation, report review and approval, special circumstances. | QC Key users/1 day
|  | 2024.06.13 | 2024.06.13 | 1 | Remote communication | new workflow？ Update RTM | if there is any problem | QC Key users/0.5day |  | set up meeting next Monday and send the plan to Neelima
|  | 2024.06.14 | 2024.06.14 | 1 | Summary/Wrap up |  | Summarize and confirm the weekly requirements gathering, discuss unclear requirements in specific topics
2 | Second Week 2024.06.17-2024.06.21 | 2024.06.17 | 2024.06.17 | 1 | Update RTM |  |  | TF
|  | 2024.06.18 | 2024.06.18 | 1 | Update RTM Alignment about Training & Instrument Survey
|  | 2024.06.19 | 2024.06.19 | 1 | Update RTM Remote communication(Dragon) 4.5Interface (global)
|  | 2024.06.20 | 2024.06.20 | 1 | 4.4LAB EXECUTION SYSTEM 4.8Laboratory Management 4.7Sample Tracking and Audit 4.3Data Capture of RM CoA & Instrument | Laboratory Execution Resampling Laboratory equipment Personnel SOP Specification management Stock & Inventory management Sample Tracking Data View and Audit Trail COA of RM auto-capture（out of scope） Data Capture of Testing Instrument | Collection and verification of LES templates. Laboratory support management. Audit Trail | QC Key users/1 day
|  | 2024.06.21 | 2024.06.21 | 1 | Summary/Wrap up Workflow discussion by TF |  | Summarize and confirm the weekly requirements gathering, discuss unclear requirements in specific topics
3 | Third Week 2024.06.24-2024.06.28 | 2024.06.24 | 2024.06.24 | 1 | getting the questions/problem ready |  |  | TF&Henkel Key users
|  | 2024.06.25 | 2024.06.25 | 1 | 4.2Sampling Scheduler(completed) 4.6 Reports and Dashboard 4.9Security and User Access Management 4.10Project Requirements Discuss the remaining questions/tasks from last week by remote meeting | Dashboard / Report (downloadable) | Dashboard system security | QC Key users/1 day
|  | 2024.06.25 | 2024.06.25 | 1 | 4.5Interface (global) | Interface to Smart factory, MES and SKill matrix SAP process in existing applications Communication between SAP and QCLAD Upload of information from the QCLAD to SAP/OSDP/Smart factory | if there is any problem System Integration(offer requirement) | Neelima and her team Zhenjuan
|  | 2024.06.26 | 2024.06.26 | 1 | Update RTM Remote communication |  | if there is any problem | QC Key users/0.5day
|  | 2024.06.27 | 2024.06.27 | 1 | Update RTM |  | Update RTM
|  | 2024.06.28 | 2024.06.28 | 1 | Summary/Wrap up | Summary | Summarize and confirm the weekly requirements gathering, discuss unclear requirements in specific topics
4 | Fourth Week 2024.07.01-2024.07.05 | 2024.07.01 | 2024.07.02 | 2 | Data gathering research - Part A (20 instruments) Update RTM | Data gathering research | 1. The list of instruments that Henkel is preparing to interface with LIMS. 2. Thermo Fisher is conducting research to confirm the feasibility and connection methods of instrument connectivity. | QC, equipment administrator
|  | 2024.07.05 | 2024.07.05 | 1 | Summary/Wrap up | Re-communicate to finalize unclear requirements Summary | Summarize and confirm the requirments of the weekly requirement gathering, discuss topics related to unclear requirements
5 | Fifth Week 2024.07.08-2024.07.12 | 2024.07.09 | 2024.07.10 | 2 | Data gathering research - Part B (rest instruments) | Data gathering research | TF will conduct research on the rest of instruments | QC, equipment administrator
5 |  | 2024.07.08 | 2024.07.12 | 5 | / | RTM review and signoff | RTM review and signoff
20 台