## Updated Gap Analysis
No | Key tasks/Milestones | Content | Deliverables | PPA Original | PPA Estimation After workshop | PPA Gap | PPB Original | PPB Estimation After workshop | PPB Gap | SOW No.
1. | Kick-off & General Project Effort | Workshop | Project management alignment, etc | 6 | 6 |  |  |  |  | 1
2. | SampleManager Training | User training | SampleManager Standard Course | 22 | 22 |  |  |  |  | 21
3. | Requirements Gathering Workshops and Architecture analysis | Requirements Gathering, RTM signoff | RTM | 16 | 21 | 5 |  |  |  | 2
|  | Instrument Investigation | Instrument Survey | 8 | 8 |  |  |  |  | 3
4. | Installation and deployment on Dev, Test and Prod servers | Environment installation (Test, PROD) | Finish the installation | 2 | 2 |  | 2 | 2 |  | 18
5. | Function implementation | Sample | System with functions implemented | 63 | 34 |  | 10 | 4 |  | 4,5
|  | Stock |  |  | 13 |  |  |  |  | 4,5
|  | Instrument |  |  | 4 |  |  |  |  | 4,5
|  | Retain |  |  | 2 | 11 |  |  | -6 | 4,5
|  | Security |  |  | 2 |  |  |  |  | 4,5
|  | Training |  |  | 0 |  |  |  |  | 4,5
|  | Other |  |  | 19 |  |  |  |  | 4,5 | Remove two OOO items
|  | Report (6, not statistics) |  | 18 | 18 |  |  |  |  | 9
|  | Label (8) |  | 10 | 10 |  |  |  |  | 10
|  | Workflow (4 + 10) |  | 7 | 24 | 17 | 23 | 26 | 3 | 6 | Add function: Test result copy
|  | Dashboard (1 static) |  | 3 | 16 | 13 |  |  |  | 11
|  | Shift& Scheduler |  | 6 | 16 | 10 | 6 | 23 | 17 | 7
6. | Interfaces | A:SAP | Interfaces modules | 28 | 34 | 6 | 39 | 51 | 12 | 14
B:Vegam, OSDP
7. | Basic Data Entry | Static Data Assistance | Finish the Data entry | 10 | 10 |  | 5 | 5 |  | 12
|  | LES |  |  |  |  | 30 | 30 |  | 8
8. | Instrument Integration | Instrument Integration (A：3+5 | Instrument Integration | 17 | 17 |  | 36 | 36 |  | 13
|  | / B：2+10) | [7 empty] | 16
9. | Documentation | RTM, Functional Specification, Configuration Summary, User Manual for SampleManager, and Instrument connection repository | Deliver the documents | 10 | 10 |  | 6 | 6 |  | 15
10. | System Integration Testing | System Integration Testing | Finish System Integration Testing | 8 | 8 |  | 12 | 12 |  | 17
11. | UAT and Go Live Support | UAT and Go Live Support | Hypercare | 10 | 10 |  |  |  |  | 19
12. | Project Management | Project Plan, Communication, Resource management, Quality Ensurrance, Progress management, Risks, etc. | Weekly status Report | 34 | 34 |  | 28 | 28 |  | 20
13. | Total |  |  | 278 | 340 | 62 | 197 | 223 | 26

## Workflow
New |  |  |  |  | Old
Main Workflow |  | Phase | New Estimate |  | Main Workflow |  | Old SOW | Phase
1 | Standard RM test for Incoming | A | 7 |  | 1 | Standard Raw Material (RM) testing for incoming | 4 | A
2 | Standard in process testing for semi finished and finished goods | A | 7 + 3 | Add a new function: Test result copy | 2 | Standard in process testing for semi finished and finished goods | 4 | B
3 | Standard finished goods outgoing test. | A | 4 |  | 3 | Standard finished goods outgoing test. | 2 | A
4 | Consumables incoming test | A | 3 |  | 4 | Consumables incoming test | 2 | A
5 | Package material incoming test (Note: Dragon package material has IDH#, no batch# manage in SAP) | B | 4 |  | 5 | Package material incoming test (Note: Dragon package material has IDH#, no batch# manage in SAP) | 2 | A
6 | Instrument calibration sample test | B | 4 |  | 6 | Instrument calibration sample test | 2 | B
7 | Test for MSA(pending) | / | / |  | 7 | Test for MSA | 2 | B
8 | Certification test for QC technician | B | 3 |  | 8 | Certification test for QC technician | 2 | B
9 | Test for SCMS/NCMR /CCMS investigation (Based on SCMS, NCMR, CCMS type) | B | 4 |  | 9 | Test for SCMS/NCMR /CCMS investigation (Based on SCMS, NCMR, CCMS type) | 2 | B
| Note: SCMS: supplier complaint management system;NCMR: nonconformance management system;CCMS: custome complaint management system |  |  |  |  | Note: SCMS: supplier complaint management system;NCMR: nonconformance management system;CCMS: custome complaint management system
10 | Test for NCMR-Shelf life extension (RM, SFG, FG, Package material, consumble & Instrument calibration sample) | B | 4 |  | 10 | Test for NCMR-Shelf life extension (RM, SFG, FG, Package material, consumble & Instrument calibration sample) | 2 | B
11 | Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project (Including, Stability studies (shelf-life study, aging test, reliability test, etc.)) | B | 4 |  | 11 | Testing for Customer/Supplier/PD/TCS/Other sites/MOC/NPI / Improvement project (Including, Stability studies (shelf-life study, aging test, reliability test, etc.)) | 2 | B
Support Workflow |  |  |  |  | Support Workflow
12 | Moving sample/material to storage location(pending) | B | 2 |  | 12 | Moving sample/material to storage location | 1 | A
13 | Perform skip lot testing (configure by user) | B | 1 |  | 13 | Perform skip lot testing (configure by user) | 1 | A
[5 empty] | 14 | Capture ECoA result and keep in SAP/QCLaD | 2 | B

## SAP
No. | RTM Reference | Henkel requirements | Priority | Can be done by SMIDI | SMIDI + Customisation - Day | Customisation- Day | Commends
1 | 4.5.1.1 | System shall support download inspection lot from SAP to QCLAD. 1）Create a sample in QCLAD based on the downloaded Inspection Lot, or change an existing sample (JIT process). 2）If the inspection lot in SAP also has multiple activities, then QCLAD needs to create multiple samples. 3）The test item in lot has a field for whether or not to skip the batch (dynamic message), and whether the SMIDI standard function can be written directly to the test table. |  | 1) Yes 2) YES 3) YES | 0 | 10
2 | 4.5.1.2 | System shall support download Batch information from SAP to QCLAD. Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. solution 1:Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. solution 2:Add fields from Batch information to QAIVC table，Pending confirmation by Henkel. |  | Yes, solution 1 | 4 | 0 | solution 1-SMIDI：Add fields from Batch information to QAIVC table,Write directly to the sample table，Need confirmation by Henkel,-- 0days solution 2:Batch information is a separate entity that needs to be downloaded to the Batch table in QCLAD. -- 4days solution 3-Cus：Put the Batch field into the JSON string downloaded by lot and write it directly to the sample table；-- 0days
3 | 4.5.1.3 | System shall support download Inspection Plan from SAP to QCLAD. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
4 | 4.5.1.4 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the MIC. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
5 | 4.5.1.5 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the specification. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
6 | 4.5.1.6 | The system shall support the downloading of Inspection plans from SAP to QCLAD whose Inspection Plan contains the Material master data. Needs to be synchronised and updated in real time. |  | No | 3 | 3 | customer want to sync in real time, but In SMIDI is impossible.
7 | 4.5.1.7 | System shall support download Plant from SAP to QCLAD. Plant is a separate entity that needs to be downloaded to the Plant table in QCLAD. |  | No | 3 | 3 | SMIDI cannot get info from seperate table
8 | 4.5.1.8 | System shall support download QM notification from SAP to QCLAD. QM notification is a separate entity that needs to be downloaded to the QM notification table in QCLAD. |  | No | 3 | 3 | SMIDI cannot get info from seperate table
9 | 4.5.1.9 | System shall support to upload result value from QCLAD to SAP. 1）When there is a Retest operation done, the result of the last Retest needs to be returned to SAP. 2）once the LIMS post result back to SAP，SAP MIC status should be auto rejected or accepted? 3）system shall support post all the samples result back to SAP, including the resampled sample. 4）related to item 1, whether Smidi can configure that, once inspection lot is downloaded mapped with an existing sample in LIMS; if that sample is authorized with result, then Smidi can also trigger the result pushing to SAP? (JIT process) |  | 1) No 2) Yes 3）Yes 4）Yes | 5 | 6 | 1) No, read these results is impossible. Only the first test result can be send back. 2) Yes, configure in SAP 3) Depending on the SAP setup this is possible.
|  |  |  | SOW:28days | SMIDI:28 + Cus:27 = 55 | 34
|  |  |  | Extra Effort | 27 | 6

## Dashboard
No. | RTM Reference | Henkel requirements | Days
1 | 4.11.1.1 | Two dashboards are required, a static dashboard with filtered conditions and a dynamic dashboard with default conditions with timed refreshes; the content displayed in both dashboards is the same | 2
2 | 4.11.1.2 | The static dashboard with filters has the following filters:plant, work center, business team(group) | 1
3 | 4.11.1.3 | Dynamic dashboards with default conditions are filtered by plant, work centre, business team(group) where the currently logged in person is located. | 1
4 | 4.11.1.4 | The dashboard shall display: Date of the day, of that day, the lists of on-duty operators, only showing the operator ID | 1
5 | 4.11.1.5 | The dashboard shall display: of the criteria, the statistic of all the tasks : Count of samples received on the same day that were not reviewed and completed Count of samples received prior to the day that were not audited and completed Count of samples completed Count of samples in-testing Count of not started Count of delayed sample Count of urgent sample | 3
6 | 4.11.1.6 | The dashboard shall display: list of delayed sample | 1
7 | 4.11.1.7 | The dashboard shall display: list of urgent sample | 1
8 | 4.11.1.8 | The dashboard shall display:the column chart in which x axis has the Sample Count, and y axis has the product line. and the column chart is coloured according to the status of the samples (Not Started, Test in Progress, Test Completed). | 3
9 | 4.11.1.9 | The dashboard shall display: anotther column chart in which x axis has the Sample Count, and y axis has the inspection type (IQC, OQC, IPQC), and the column chart should be colour-coded according to the sample status (Not Started, Test in Progress, Test Completed). | 3
|  | SOW:3days | 16

## Dashboard details
No. | RTM Reference | Henkel requirements | Days
1 | 4.11.1.1 | Two dashboards are required, a static dashboard with filtered conditions and a dynamic dashboard with default conditions with timed refreshes; the content displayed in both dashboards is the same | 2
2 | 4.11.1.2 | The static dashboard with filters has the following filters:plant, work center, business team(group) 1. 与1.3相同是静态Dashboard的功能 | 1
3 | 4.11.1.3 | Dynamic dashboards with default conditions are filtered by plant, work centre, business team(group) where the currently logged in p erson is located. 1. Plant filter on the top 2. Work center filter below Plant filter 3. Business Team filter - 对应到Team 下拉三角形 | 1
4 | 4.11.1.4 | The dashboard shall display: Date of the day, of that day, the lists of on-duty operators, only showing the operator ID 1. 显示当天日期 2. 显示业务组的当天在班的成员ID | 1
5 | 4.11.1.5 | The dashboard shall display: of the criteria, the statistic of all the tasks : Count of samples received on the same day that were not reviewed and completed Count of samples received prior to the day that were not audited and completed Count of samples completed Count of samples in-testing Count of not started Count of delayed sample Count of urgent sample 仪表盘中需显示： 当天收样但未审核完成的样品数量 当天之前收样但未审核完成的样品数量 测试已完成的样品数量completed --系统内状态 测试中的样品数量in-testing（sample状态为Available，sample下 test存在In Progress，Completed、Authorised状态的）-- 系统外状态，需要逻辑处理 未开始的样品数量not started（sample状态为Available，且sample下的test没有In Progress、Completed、Authorised 、Rejected状态的）-- 系统外状态，需要逻辑处理 the count of delayed sample -- 需要额外先把预计完成时间算出来 the count of urgent sample -- 需要额外字段标识 | 3
6 | 4.11.1.6 | The dashboard shall display: list of delayed sample | 1
7 | 4.11.1.7 | The dashboard shall display: list of urgent sample | 1
8 | 4.11.1.8 | The dashboard shall display:the column chart in which x axis has the Sample Count, and y axis has the product line. and the column chart is coloured according to the status of the samples (Not Started, Test in Progress, Test Completed). 1. 横坐标数量，纵坐标产线 2. 且柱状图中按照样品状态（未开始-额外逻辑处理，测试中-额外逻辑处理，测试已完成）分颜色显示 | 3
9 | 4.11.1.9 | The dashboard shall display: anotther column chart in which x axis has the Sample Count, and y axis has the inspection type (IQC, OQC, IPQC), and the column chart should be colour-coded according to the sample status (Not Started, Test in Progress, Test Completed). 1. 横坐标数量，纵坐标inspection Type 2. 且柱状图中按照样品状态（未开始-额外逻辑处理，测试中-额外逻辑处理，测试已完成）分颜色显示 | 3
|  | SOW:3days | 16
Don't need this